## Sheet1
EV Equipment Code | EV Equipment Region | EV Equipment Serial Number | EV Equipment Technology | EV Events Equipment Event ID | EV Events Event Type | EV Events Project ID | EV Events Plan Event Start Date | EV Events Plan Event End Date
| NAM North America | 818826 | Steam Turbine | 106707 | Minor Inspection | 503080 | 2030-04-01 | 2030-05-01
| NAM North America | 810777 | Steam Turbine | 114081 | Minor Inspection |  | 2026-10-01 | 2026-10-06
| NAM North America | 810777 | Steam Turbine | 120926 | Major Inspection (MI) |  | 2029-10-01 | 2029-11-05
| Asia | G26102-HRSG | HRSG | 136659 | Minor Inspection | 524085 | 2026-04-13 | 2026-05-27
| NAM North America | 818828 | Generator | 140184 | Minor Inspection | 503080 | 2030-04-01 | 2030-05-01
| NAM North America | 818670 | Steam Turbine | 140687 | Stand Alone Small Upgrade | 526354 | 2027-01-01 | 2027-01-26
| NAM North America | 818824 | Steam Turbine | 147598 | Minor Inspection | 555632 | 2028-04-03 | 2028-05-03
| Latin America | SY0052820 | Steam Turbine | 148581 | Minor Inspection | 552706 | 2026-03-03 | 2026-03-21
| Latin America | SY0052821 | Steam Turbine | 148585 | Minor Inspection | 562804 | 2027-03-02 | 2027-03-24
| NAM North America | 818670 | Steam Turbine | 150725 | Major Inspection (MI) | 532263 | 2027-03-25 | 2027-05-10
| Asia | 821600 | Generator | 156867 | Minor Inspection | 536562 | 2026-11-18 | 2026-12-08
| Asia | 980000 | Generator | 162788 | Major Inspection (Rotor Out) | 541038 | 2027-06-14 | 2027-07-02
| Europe | 818627 | Steam Turbine | 163066 | Major Inspection (MI) |  | 2029-06-01 | 2029-07-10
| NAM North America | 818826 | Steam Turbine | 163195 | Minor Inspection |  | 2030-04-01 | 2030-05-01
| NAM North America | 815249 | Steam Turbine | 165274 | Major Inspection (MI) |  | 2028-05-10 | 2028-06-07
| Asia | 937265 | Generator | 166075 | Major Inspection (Rotor Out) | 543391 | 2028-01-13 | 2028-01-31
| Asia | G26102-HRSG | HRSG | 169212 | Major Inspection (MI) |  | 2030-01-11 | 2030-02-08
| NAM North America | 818737 | Steam Turbine | 173085 | Minor Inspection | 548101 | 2026-03-01 | 2026-05-01
| NAM North America | 818737 | Steam Turbine | 173720 | Minor Inspection | 548469 | 2026-05-01 | 2026-05-31
| Latin America | 982097 | Steam Turbine | 175847 | Minor Inspection | 561478 | 2028-03-01 | 2028-03-29
| Latin America | 980035 | Gas Turbine | 175848 | Major Inspection (MI) | 561477 | 2028-03-01 | 2028-03-29
| Latin America | 980036 | Gas Turbine | 175849 | Major Inspection (MI) | 561476 | 2028-03-01 | 2028-03-29
| Asia | G26102-HRSG | HRSG | 183188 | Minor Inspection | 560520 | 2026-06-05 | 2026-07-06
| Europe | G500-HRSG | HRSG | 183311 | Major Inspection (MI) |  | 2029-05-03 | 2029-05-28
| Europe | G501-HRSG | HRSG | 183312 | Minor Inspection | 560162 | 2026-05-10 | 2026-05-15
| Europe | G501-HRSG | HRSG | 183313 | Major Inspection (MI) |  | 2029-12-29 | 2030-01-23
| NAM North America | 818738 | Generator | 186272 | Minor Inspection | 548469 | 2026-04-11 | 2026-05-31
| NAM North America | 818738 | Generator | 187238 | Minor Inspection | 561519 | 2026-05-01 | 2026-05-31
| Asia | 3183Y770 | Steam Turbine | 190433 | Minor Inspection | 559155 | 2029-05-01 | 2029-05-31
| Latin America | SY0052821 | Steam Turbine | 191682 | Minor Inspection | 560048 | 2027-03-02 | 2027-03-20
| NAM North America | 818737 | Steam Turbine | 193786 | Minor Inspection | 561519 | 2026-05-01 | 2026-05-31
| NAM North America | 818738 | Generator | 194062 | Minor Inspection | 561773 | 2026-05-01 | 2026-05-31
| NAM North America | 818670 | Steam Turbine | 195376 | Major Inspection (MI) |  | 2027-05-15 | 2027-06-15
| Europe | 818628 | Generator | 196266 | Large Call-Out |  | 2027-05-04 | 2027-05-17
| NAM North America | 818670 | Steam Turbine | 196404 | Major Inspection (MI) |  | 2027-05-15 | 2027-06-10
2-104X225 | NAM North America | 813842 | Generator | 191097 | Minor Inspection | 559659 | 2028-04-03 | 2028-05-16
5A2 | NAM North America | 335X845 | Generator | 157911 | Minor Inspection | 537446 | 2026-03-16 | 2026-03-27
6A3 | NAM North America | 446X085 | Generator | 149741 | Major Inspection (Rotor Out) | 531654 | 2028-03-01 | 2028-04-15
6A3 | NAM North America | 335X479 | Generator | 150950 | Major Inspection (Field Rewind) | 532376 | 2026-09-21 | 2026-10-29
6A3 | Asia | 336X480 | Generator | 156838 | Major Inspection (Rotor Out) | 536531 | 2028-01-12 | 2028-01-30
6A3 | Latin America | 446X021 | Generator | 158000 | Major Inspection (Stator Rewind) |  | 2026-01-05 | 2026-02-13
6A3 | Latin America | 446X021 | Generator | 158001 | Major Inspection (Stator Rewind) | 535304 | 2026-03-31 | 2026-05-11
6A3 | Asia | 336X480 | Generator | 162793 | Minor Inspection | 541042 | 2030-09-07 | 2030-09-21
6A3 | Latin America | 446X021 | Generator | 165664 | Major Inspection (Robotic) | 543136 | 2030-02-28 | 2030-03-28
6A3 | NAM North America | 335X492 | Generator | 165957 | Major Inspection (Rotor Out) | 543314 | 2028-02-07 | 2028-03-20
6A3 | NAM North America | 335X478 | Generator | 165959 | Major Inspection (Robotic) | 543315 | 2029-04-18 | 2029-05-16
6A3 | NAM North America | 335X479 | Generator | 165961 | Minor Inspection | 543316 | 2030-10-01 | 2030-10-15
6A3 | NAM North America | 336X483 | Generator | 180860 | Major Inspection (Stator Rewind) | 552835 | 2028-04-19 | 2028-06-05
6A6 | NAM North America | 446X084 | Generator | 115432 | Minor Inspection | 505733 | 2028-09-30 | 2028-10-14
6A6 | NAM North America | 446X101 | Generator | 150346 | Minor Inspection | 532073 | 2028-04-01 | 2028-04-15
6A6 | NAM North America | 446X100 | Generator | 150347 | Minor Inspection | 532074 | 2029-04-01 | 2029-04-15
6A6 | Latin America | 446X046 | Generator | 150809 | Major Inspection (Rotor Out) | 532305 | 2028-04-16 | 2028-05-14
6A6 | Asia | 446X079 | Generator | 165846 | Minor Inspection | 536560 | 2026-06-23 | 2026-07-07
6A6 | Asia | 446X077 | Generator | 165847 | Major Inspection (Robotic) | 543238 | 2027-12-30 | 2028-01-27
6A6 | MENA | 446X204 | Generator | 166340 | Major Inspection (Robotic) | 543554 | 2030-11-30 | 2030-12-28
6A6 | MENA | 446X203 | Generator | 166341 | Major Inspection (Robotic) | 543555 | 2030-06-11 | 2030-07-09
6A6 | NAM North America | 316X964 | Generator | 168821 | Major Inspection (Robotic) | 543736 | 2028-09-24 | 2028-10-29
6A6 | Asia | 446X078 | Generator | 184334 | Major Inspection (Rotor Out) | 554960 | 2027-03-17 | 2027-04-14
6A6 | Asia | 446X078 | Generator | 184338 | Major Inspection (Rotor Out) | 554963 | 2027-03-17 | 2027-04-14
6B.03 | NAM North America | 850254 | Gas Turbine | 148003 | Major Inspection (MI) | 530495 | 2028-09-06 | 2028-10-04
6B.03 | Asia | 850281 | Gas Turbine | 149824 | Hot Gas Path Inspection (HGPI) | 546356 | 2027-09-01 | 2027-09-19
6B.03 | NAM North America | 850254 | Gas Turbine | 158268 | Borescope Inspection (BI) | 537721 | 2026-08-05 | 2026-08-17
6B.03 | Latin America | 850282 | Gas Turbine | 161417 | Major Inspection (MI) | 539929 | 2027-01-11 | 2027-02-14
6B.03 | Latin America | 850282 | Gas Turbine | 165822 | Hot Gas Path Inspection (HGPI) | 543229 | 2030-04-21 | 2030-05-05
6B.03 | Latin America | 850283 | Gas Turbine | 165824 | Hot Gas Path Inspection (HGPI) | 543230 | 2030-10-16 | 2030-10-30
6B.03 | Latin America | 850283 | Gas Turbine | 180660 | Major Inspection (MI) | 552680 | 2027-08-01 | 2027-08-31
6B.03 | Latin America | 850283 | Gas Turbine | 180666 | Major Inspection (MI) | 552686 | 2027-09-06 | 2027-10-08
6B.03 | Latin America | 850284 | Gas Turbine | 180829 | Major Inspection (MI) | 552815 | 2028-02-02 | 2028-03-01
6F.01 | China | 860003 | Gas Turbine | 110560 | Large Call-Out | 505066 | 2027-12-27 | 2028-01-15
6F.01 | China | 860004 | Gas Turbine | 110648 | Hot Gas Path Inspection (HGPI) | 505068 | 2026-12-12 | 2027-01-03
6F.01 | China | 860004 | Gas Turbine | 114068 | Combustion Inspection (CI) | 505070 | 2030-04-16 | 2030-04-28
6F.01 | China | 860005 | Gas Turbine | 121101 | Hot Gas Path Inspection (HGPI) | 505067 | 2029-03-05 | 2029-03-27
6F.01 | China | 299555 | Gas Turbine | 149597 | Hot Gas Path Inspection (HGPI) | 539708 | 2026-01-05 | 2026-02-03
6F.01 | China | 299556 | Gas Turbine | 149598 | Hot Gas Path Inspection (HGPI) | 532763 | 2026-07-27 | 2026-08-23
6F.01 | Latin America | 860006 | Gas Turbine | 150395 | Hot Gas Path Inspection (HGPI) | 550658 | 2028-10-15 | 2028-10-29
6F.01 | China | 299671 | Gas Turbine | 150711 | Hot Gas Path Inspection (HGPI) | 554419 | 2027-03-07 | 2027-04-03
6F.01 | China | 860011 | Gas Turbine | 150712 | Major Inspection (MI) | 545380 | 2028-04-20 | 2028-05-18
6F.01 | Europe | 860018 | Gas Turbine | 151185 | Major Inspection (MI) | 536894 | 2027-04-01 | 2027-04-30
6F.01 | Europe | 860019 | Gas Turbine | 151186 | Major Inspection (MI) | 536896 | 2027-02-28 | 2027-03-31
6F.01 | China | 860003 | Gas Turbine | 152799 | Borescope Inspection (BI) |  | 2026-02-05 | 2026-02-06
6F.01 | China | 860004 | Gas Turbine | 152800 | Borescope Inspection (BI) |  | 2026-09-25 | 2026-09-26
6F.01 | China | 860005 | Gas Turbine | 152801 | Borescope Inspection (BI) | 563571 | 2026-12-02 | 2026-12-03
6F.01 | China | 299671 | Gas Turbine | 155527 | Borescope Inspection (BI) | 535567 | 2026-03-01 | 2026-03-04
6F.01 | China | 299556 | Gas Turbine | 155528 | Borescope Inspection (BI) | 535568 | 2026-03-08 | 2026-03-10
6F.01 | China | 299555 | Gas Turbine | 155529 | Borescope Inspection (BI) | 535569 | 2026-12-21 | 2026-12-25
6F.01 | China | 299555 | Gas Turbine | 160588 | Large Call-Out | 539301 | 2026-01-11 | 2026-01-20
6F.01 | China | 299671 | Gas Turbine | 160589 | Large Call-Out | 539251 | 2027-06-05 | 2027-07-10
6F.01 | China | 299556 | Gas Turbine | 160593 | Large Call-Out | 539254 | 2026-08-05 | 2026-08-15
6F.01 | China | 860902 | Gas Turbine | 165429 | Major Inspection (MI) | 559331 | 2030-07-31 | 2030-08-28
6F.01 | Latin America | 860007 | Gas Turbine | 165467 | Hot Gas Path Inspection (HGPI) | 554490 | 2028-01-19 | 2028-02-02
6F.01 | China | 860901 | Gas Turbine | 165646 | Hot Gas Path Inspection (HGPI) | 543121 | 2026-11-25 | 2027-01-05
6F.01 | China | 860003 | Gas Turbine | 165702 | Hot Gas Path Inspection (HGPI) | 555895 | 2029-03-01 | 2029-03-20
6F.01 | China | 299556 | Gas Turbine | 165843 | Major Inspection (MI) | 558889 | 2030-04-15 | 2030-05-29
6F.01 | China | 299555 | Gas Turbine | 165844 | Major Inspection (MI) | 558888 | 2029-11-05 | 2029-12-19
6F.01 | China | 860016 | Gas Turbine | 167669 | Major Inspection (MI) | 549831 | 2028-10-23 | 2028-11-20
6F.01 | China | 860017 | Gas Turbine | 167670 | Hot Gas Path Inspection (HGPI) | 552966 | 2029-04-01 | 2029-04-15
6F.01 | China | 860017 | Gas Turbine | 179075 | Large Call-Out | 551822 | 2026-03-25 | 2026-04-14
6F.01 | China | 299671 | Gas Turbine | 192114 | Large Call-Out | 560333 | 2026-03-10 | 2026-03-24
6F.01 | China | 860003 | Gas Turbine | 192214 | Hot Gas Path Inspection (HGPI) |  | 2028-08-24 | 2028-09-07
6F.03 | Asia | 875155 | Gas Turbine | 132162 | Borescope Inspection (BI) | 521964 | 2026-11-01 | 2026-11-04
6F.03 | Asia | 875179 | Gas Turbine | 132918 | Hot Gas Path Inspection (HGPI) | 535382 | 2027-01-01 | 2027-01-20
6F.03 | Asia | 875178 | Gas Turbine | 132919 | Hot Gas Path Inspection (HGPI) | 534517 | 2026-08-22 | 2026-09-04
6F.03 | Latin America | 875152 | Gas Turbine | 150358 | Combustion Inspection (CI) | 550103 | 2028-04-10 | 2028-04-30
6F.03 | Latin America | 875152 | Gas Turbine | 150359 | Major Inspection (MI) | 547794 | 2028-07-18 | 2028-08-15
6F.03 | Asia | 875178 | Gas Turbine | 150408 | Hot Gas Path Inspection (HGPI) | 543158 | 2027-01-20 | 2027-02-03
6F.03 | Asia | 875179 | Gas Turbine | 150409 | Hot Gas Path Inspection (HGPI) | 543159 | 2027-07-20 | 2027-08-03
6F.03 | Asia | 875155 | Gas Turbine | 150713 | Hot Gas Path Inspection (HGPI) | 543123 | 2028-01-01 | 2028-01-14
6F.03 | Europe | 875175 | Gas Turbine | 151460 | Hot Gas Path Inspection (HGPI) | 563072 | 2030-09-01 | 2030-09-20
6F.03 | Europe | 875180 | Gas Turbine | 151461 | Hot Gas Path Inspection (HGPI) | 558358 | 2030-03-03 | 2030-03-22
6F.03 | Asia | 875174 | Gas Turbine | 152716 | Major Inspection (MI) | 534999 | 2027-11-05 | 2027-12-03
6F.03 | Asia | 875173 | Gas Turbine | 152717 | Major Inspection (MI) | 535000 | 2026-10-15 | 2026-11-10
6F.03 | Asia | 875173 | Gas Turbine | 155680 | Borescope Inspection (BI) | 535707 | 2026-04-04 | 2026-04-05
6F.03 | Asia | 875174 | Gas Turbine | 155683 | Borescope Inspection (BI) | 535710 | 2026-10-12 | 2026-10-17
6F.03 | Asia | 875178 | Gas Turbine | 160258 | Borescope Inspection (BI) | 538944 | 2026-07-17 | 2026-07-20
6F.03 | Asia | 875176 | Gas Turbine | 160635 | Borescope Inspection (BI) | 539277 | 2026-04-19 | 2026-04-20
6F.03 | Asia | 875177 | Gas Turbine | 160636 | Borescope Inspection (BI) | 539278 | 2026-04-21 | 2026-04-22
6F.03 | China | 875138 | Gas Turbine | 160642 | Borescope Inspection (BI) | 539279 | 2026-10-20 | 2026-10-23
6F.03 | China | 875139 | Gas Turbine | 160683 | Borescope Inspection (BI) |  | 2026-11-23 | 2026-11-26
6F.03 | Asia | 875178 | Gas Turbine | 165711 | Major Inspection (MI) | 543160 | 2030-03-19 | 2030-04-16
6F.03 | Asia | 875176 | Gas Turbine | 165720 | Major Inspection (MI) | 543164 | 2030-03-06 | 2030-04-03
6F.03 | Asia | 875177 | Gas Turbine | 165721 | Major Inspection (MI) | 543165 | 2030-01-27 | 2030-02-24
6F.03 | Latin America | 875152 | Gas Turbine | 165865 | Combustion Inspection (CI) |  | 2030-10-23 | 2030-10-30
6F.03 | Europe | 875156 | Gas Turbine | 166467 | Hot Gas Path Inspection (HGPI) | 543629 | 2028-08-24 | 2028-09-07
6F.03 | Europe | 875167 | Gas Turbine | 166469 | Hot Gas Path Inspection (HGPI) | 543630 | 2028-09-09 | 2028-09-28
6F.03 | China | 875138 | Gas Turbine | 167024 | Major Inspection (MI) | 556817 | 2028-02-13 | 2028-03-12
6F.03 | China | 875139 | Gas Turbine | 167025 | Major Inspection (MI) | 559107 | 2029-04-16 | 2029-05-14
6F.03 | Asia | 875183 | Gas Turbine | 168213 | Combustion Inspection (CI) | 552708 | 2028-10-30 | 2028-11-06
6F.03 | Asia | 875183 | Gas Turbine | 168214 | Hot Gas Path Inspection (HGPI) |  | 2030-02-01 | 2030-02-15
6F.03 | China | 875903 | Gas Turbine | 168281 | Hot Gas Path Inspection (HGPI) | 546315 | 2027-08-02 | 2027-09-02
6F.03 | China | 875902 | Gas Turbine | 168282 | Hot Gas Path Inspection (HGPI) | 546314 | 2026-10-12 | 2026-11-10
6F.03 | Asia | 875179 | Gas Turbine | 179301 | Major Inspection (MI) | 551902 | 2030-08-29 | 2030-09-26
6F.03 | Latin America | 875152 | Gas Turbine | 182037 | Major Inspection (MI) |  | 2028-10-29 | 2028-11-26
6F.03 | Latin America | 875181 | Gas Turbine | 184640 | Hot Gas Path Inspection (HGPI) | 560721 | 2029-10-01 | 2029-10-15
6F.03 | China | 875139 | Gas Turbine | 194527 | Large Call-Out | 562208 | 2027-03-22 | 2027-04-15
6F.03 | Europe | 875175 | Gas Turbine | 195707 | Combustion Inspection (CI) | 563073 | 2027-09-05 | 2027-09-08
6FA | MENA | 337X642 | Generator | 145428 | Major Inspection (Robotic) | 501398 | 2028-03-01 | 2028-03-14
6FA | MENA | 337X638 | Generator | 145429 | Minor Inspection | 502344 | 2029-02-03 | 2029-02-17
6FA | MENA | 337X639 | Generator | 145430 | Minor Inspection | 502345 | 2030-11-28 | 2030-12-12
6FA | Asia | 338X216 | Generator | 155759 | Minor Inspection | 535750 | 2027-04-01 | 2027-04-22
6FA | Asia | 337X614 | Generator | 155973 | Major Inspection (Robotic) | 535868 | 2026-10-08 | 2026-11-05
6FA | Asia | 337X615 | Generator | 156620 | Minor Inspection | 536364 | 2026-03-12 | 2026-03-26
6FA | Asia | 337X654 | Generator | 156866 | Major Inspection (Robotic) | 536561 | 2026-10-19 | 2026-11-16
6FA | MENA | 337X642 | Generator | 157952 | Major Inspection (Robotic) | 537466 | 2028-10-01 | 2028-10-29
6FA | MENA | 337X630 | Generator | 158955 | Minor Inspection | 538138 | 2029-02-27 | 2029-03-27
6FA | MENA | 337X631 | Generator | 158956 | Minor Inspection | 538139 | 2030-03-19 | 2030-04-16
6FA | Asia | 337X682 | Generator | 159163 | Major Inspection (Rotor Out) | 538245 | 2028-05-01 | 2028-05-31
6FA | Europe | 337X616 | Generator | 164607 | Major Inspection (Rotor Out) | 542456 | 2026-04-01 | 2026-05-31
6FA | Europe | 337X617 | Generator | 164620 | Large Call-Out | 542454 | 2028-07-24 | 2028-09-02
6FA | Europe | 337X616 | Generator | 164621 | Major Inspection (Rotor Out) | 542453 | 2026-06-15 | 2026-08-15
6FA | Asia | 337X655 | Generator | 165434 | Minor Inspection | 542969 | 2027-10-01 | 2027-10-29
6FA | Asia | 337X615 | Generator | 165875 | Minor Inspection | 543255 | 2027-10-21 | 2027-11-21
6FA | Asia | 337X615 | Generator | 165876 | Major Inspection (Robotic) | 543256 | 2030-08-09 | 2030-09-06
6FA | Asia | 337X614 | Generator | 165878 | Minor Inspection | 543257 | 2029-07-30 | 2029-08-27
6FA | Europe | 337X625 | Generator | 165890 | Major Inspection (Robotic) | 543262 | 2028-04-03 | 2028-11-30
6FA | MENA | 337X643 | Generator | 166217 | Major Inspection (Robotic) | 543489 | 2028-10-01 | 2028-10-25
6FA | MENA | GG10515 | Generator | 166281 | Major Inspection (Robotic) | 543519 | 2028-07-01 | 2028-07-29
6FA | MENA | GG10517 | Generator | 166284 | Major Inspection (Robotic) | 543520 | 2029-01-03 | 2029-01-31
6FA | MENA | GG10516 | Generator | 166286 | Major Inspection (Robotic) | 543521 | 2028-08-31 | 2028-09-28
6FA | MENA | GG10518 | Generator | 166288 | Major Inspection (Robotic) | 543522 | 2029-02-07 | 2029-03-07
6FA | MENA | 337X664 | Generator | 166394 | Major Inspection (Robotic) | 543578 | 2026-08-05 | 2026-09-02
6FA | MENA | 337X665 | Generator | 166395 | Major Inspection (Robotic) | 543579 | 2026-10-19 | 2026-11-16
6FA | MENA | 337X663 | Generator | 166396 | Major Inspection (Robotic) | 543580 | 2027-02-02 | 2027-03-02
6FA | MENA | 337X661 | Generator | 166397 | Major Inspection (Robotic) | 543581 | 2028-02-07 | 2028-03-06
6FA | MENA | 337X662 | Generator | 166399 | Major Inspection (Robotic) | 543582 | 2027-10-18 | 2027-11-15
6FA | Europe | 338X219 | Generator | 166486 | Minor Inspection | 507603 | 2028-03-06 | 2028-03-28
6FA | Europe | 337X659 | Generator | 167012 | Minor Inspection | 544050 | 2028-05-28 | 2028-06-11
6FA | Europe | 337X629 | Generator | 167017 | Minor Inspection | 544051 | 2030-11-16 | 2030-11-30
6FA | Europe | 337X620 | Generator | 167023 | Minor Inspection | 544052 | 2027-05-30 | 2027-06-21
6FA | MENA | 337X633 | Generator | 168336 | Minor Inspection | 545197 | 2028-07-27 | 2028-08-10
6FA | MENA | 337X634 | Generator | 168337 | Minor Inspection | 545198 | 2028-12-10 | 2028-12-24
6FA | Europe | 337X623 | Generator | 172173 | Minor Inspection | 547505 | 2026-11-03 | 2026-12-02
6FA | Europe | 337X624 | Generator | 172176 | Minor Inspection | 547507 | 2026-11-03 | 2026-12-02
6FA | Europe | 337X621 | Generator | 174334 | Minor Inspection | 548885 | 2029-09-03 | 2029-09-28
6FA | Europe | 337X622 | Generator | 174336 | Minor Inspection | 548886 | 2029-09-03 | 2029-09-28
6FA | Asia | 337X684 | Generator | 184202 | Major Inspection (Robotic) | 554839 | 2028-08-01 | 2028-08-31
6FA | Asia | 337X683 | Generator | 184204 | Major Inspection (Robotic) | 554840 | 2029-05-01 | 2029-05-31
6FA | MENA | 337X664 | Generator | 192719 | Minor Inspection | 560709 | 2029-11-26 | 2029-12-10
6FA | Europe | 337X619 | Generator | 193494 | Major Inspection (Robotic) | 561244 | 2029-05-21 | 2029-06-19
6FA | Asia | 337X614 | Generator | 196092 | Minor Inspection | 550639 | 2028-11-27 | 2028-12-04
6FA | Asia | 337X615 | Generator | 196093 | Minor Inspection | 550642 | 2028-12-18 | 2028-12-25
6FA.01 | Asia | 819731 | Gas Turbine | 106349 | Combustion Inspection (CI) | 502722 | 2026-01-20 | 2026-01-27
6FA.01 | Asia | 297160 | Gas Turbine | 132909 | Combustion Inspection (CI) | 536364 | 2026-03-12 | 2026-03-26
6FA.01 | Asia | 297159 | Gas Turbine | 150576 | Major Inspection (MI) | 535868 | 2026-10-08 | 2026-11-05
6FA.01 | Asia | 297160 | Gas Turbine | 150577 | Hot Gas Path Inspection (HGPI) | 543255 | 2027-10-21 | 2027-11-21
6FA.01 | Asia | 297159 | Gas Turbine | 150578 | Combustion Inspection (CI) | 550639 | 2028-11-27 | 2028-12-04
6FA.01 | Asia | 297160 | Gas Turbine | 150579 | Combustion Inspection (CI) | 550642 | 2028-12-18 | 2028-12-25
6FA.01 | Asia | 819731 | Gas Turbine | 150709 | Combustion Inspection (CI) | 535831 | 2027-01-20 | 2027-01-27
6FA.01 | Asia | 819731 | Gas Turbine | 155521 | Borescope Inspection (BI) | 535561 | 2026-11-17 | 2026-11-18
6FA.01 | Asia | 819731 | Gas Turbine | 162859 | Large Call-Out | 541075 | 2026-02-15 | 2026-03-17
6FA.01 | Asia | 297160 | Gas Turbine | 165877 | Major Inspection (MI) | 543256 | 2030-08-09 | 2030-09-06
6FA.01 | Asia | 297159 | Gas Turbine | 165879 | Hot Gas Path Inspection (HGPI) | 543257 | 2029-07-30 | 2029-08-13
6FA.03 | MENA | 875026 | Gas Turbine | 104378 | Combustion Inspection (CI) | 501309 | 2027-08-26 | 2027-09-02
6FA.03 | MENA | 875043 | Gas Turbine | 105180 | Hot Gas Path Inspection (HGPI) | 501398 | 2028-03-01 | 2028-03-15
6FA.03 | MENA | 875028 | Gas Turbine | 105459 | Hot Gas Path Inspection (HGPI) | 501405 | 2026-04-08 | 2026-04-22
6FA.03 | MENA | 875031 | Gas Turbine | 105900 | Hot Gas Path Inspection (HGPI) | 502344 | 2029-02-03 | 2029-02-17
6FA.03 | MENA | 875035 | Gas Turbine | 105901 | Hot Gas Path Inspection (HGPI) | 502345 | 2030-11-28 | 2030-12-12
6FA.03 | Asia | 875014 | Gas Turbine | 106436 | Hot Gas Path Inspection (HGPI) | 502809 | 2027-07-24 | 2027-08-07
6FA.03 | Latin America | 875148 | Gas Turbine | 106579 | Major Inspection (MI) | 502952 | 2027-05-03 | 2027-06-01
6FA.03 | Latin America | 875150 | Gas Turbine | 106647 | Major Inspection (MI) | 503020 | 2029-08-06 | 2029-09-04
6FA.03 | Asia | 875036 | Gas Turbine | 107531 | Hot Gas Path Inspection (HGPI) |  | 2028-08-17 | 2028-08-31
6FA.03 | Europe | 875100 | Gas Turbine | 108464 | Hot Gas Path Inspection (HGPI) | 507603 | 2028-03-06 | 2028-03-28
6FA.03 | Asia | 875036 | Gas Turbine | 109761 | Hot Gas Path Inspection (HGPI) |  | 2028-08-17 | 2028-08-31
6FA.03 | China | 875146 | Gas Turbine | 110000 | Hot Gas Path Inspection (HGPI) | 505060 | 2027-09-20 | 2027-10-11
6FA.03 | Europe | 875016 | Gas Turbine | 114491 | Major Inspection (MI) | 516214 | 2028-05-01 | 2028-05-25
6FA.03 | China | 875079 | Gas Turbine | 114789 | Hot Gas Path Inspection (HGPI) | 535618 | 2029-10-15 | 2029-10-29
6FA.03 | Asia | 875036 | Gas Turbine | 116631 | Hot Gas Path Inspection (HGPI) | 506187 | 2026-05-05 | 2026-05-19
6FA.03 | Asia | 875037 | Gas Turbine | 121311 | Hot Gas Path Inspection (HGPI) | 506188 | 2026-04-16 | 2026-04-30
6FA.03 | MENA | 875031 | Gas Turbine | 131308 | Combustion Inspection (CI) | 521337 | 2026-04-01 | 2026-04-10
6FA.03 | MENA | 875035 | Gas Turbine | 131309 | Hot Gas Path Inspection (HGPI) | 521338 | 2026-04-01 | 2026-04-25
6FA.03 | China | 875086 | Gas Turbine | 132925 | Hot Gas Path Inspection (HGPI) | 529820 | 2026-10-18 | 2026-11-09
6FA.03 | Latin America | 875131 | Gas Turbine | 150360 | Major Inspection (MI) | 532097 | 2027-06-01 | 2027-06-29
6FA.03 | Asia | 875052 | Gas Turbine | 150499 | Major Inspection (MI) | 536561 | 2026-10-19 | 2026-11-16
6FA.03 | Asia | 875058 | Gas Turbine | 150500 | Hot Gas Path Inspection (HGPI) | 542969 | 2027-10-01 | 2027-10-29
6FA.03 | Asia | 875126 | Gas Turbine | 150543 | Hot Gas Path Inspection (HGPI) | 536527 | 2027-10-01 | 2027-10-14
6FA.03 | Asia | 875127 | Gas Turbine | 150544 | Hot Gas Path Inspection (HGPI) | 536529 | 2027-10-18 | 2027-11-01
6FA.03 | Asia | 875081 | Gas Turbine | 150621 | Major Inspection (MI) | 538245 | 2028-05-01 | 2028-05-31
6FA.03 | Latin America | 875150 | Gas Turbine | 150692 | Major Inspection (MI) | 543060 | 2027-10-09 | 2027-11-07
6FA.03 | China | 875087 | Gas Turbine | 150928 | Hot Gas Path Inspection (HGPI) | 546035 | 2027-10-08 | 2027-10-30
6FA.03 | MENA | 875027 | Gas Turbine | 151138 | Hot Gas Path Inspection (HGPI) | 545197 | 2028-07-27 | 2028-08-10
6FA.03 | MENA | 875030 | Gas Turbine | 151139 | Hot Gas Path Inspection (HGPI) | 545198 | 2028-12-10 | 2028-12-24
6FA.03 | MENA | 875026 | Gas Turbine | 151141 | Hot Gas Path Inspection (HGPI) | 538138 | 2029-02-27 | 2029-03-13
6FA.03 | MENA | 875031 | Gas Turbine | 151143 | Combustion Inspection (CI) |  | 2028-05-05 | 2028-05-12
6FA.03 | Europe | 875062 | Gas Turbine | 151168 | Major Inspection (MI) |  | 2026-09-13 | 2026-10-11
6FA.03 | Europe | 875078 | Gas Turbine | 151182 | Major Inspection (MI) |  | 2026-03-30 | 2026-04-27
6FA.03 | Europe | 875029 | Gas Turbine | 151232 | Major Inspection (MI) | 543262 | 2028-04-03 | 2028-11-30
6FA.03 | MENA | 875059 | Gas Turbine | 151236 | Combustion Inspection (CI) | 542463 | 2026-02-09 | 2026-02-17
6FA.03 | MENA | 875066 | Gas Turbine | 151237 | Major Inspection (MI) | 543578 | 2026-08-05 | 2026-09-02
6FA.03 | MENA | 875065 | Gas Turbine | 151238 | Major Inspection (MI) | 543580 | 2027-02-02 | 2027-03-02
6FA.03 | MENA | 875067 | Gas Turbine | 151239 | Major Inspection (MI) | 543579 | 2026-10-19 | 2026-11-16
6FA.03 | MENA | 875059 | Gas Turbine | 151240 | Major Inspection (MI) | 543581 | 2028-02-07 | 2028-03-06
6FA.03 | Europe | 875124 | Gas Turbine | 151269 | Hot Gas Path Inspection (HGPI) |  | 2026-06-01 | 2026-06-15
6FA.03 | Europe | 875125 | Gas Turbine | 151270 | Hot Gas Path Inspection (HGPI) |  | 2026-12-29 | 2027-01-12
6FA.03 | Latin America | 875131 | Gas Turbine | 154040 | Borescope Inspection (BI) | 534666 | 2026-10-19 | 2026-10-21
6FA.03 | Europe | 875029 | Gas Turbine | 155291 | Large Call-Out | 535429 | 2027-04-05 | 2028-02-29
6FA.03 | Asia | 875014 | Gas Turbine | 155524 | Borescope Inspection (BI) | 535564 | 2026-11-19 | 2026-11-20
6FA.03 | China | 875079 | Gas Turbine | 155535 | Borescope Inspection (BI) | 535573 | 2026-10-15 | 2026-10-17
6FA.03 | China | 875080 | Gas Turbine | 155538 | Borescope Inspection (BI) | 535574 | 2026-10-18 | 2026-10-20
6FA.03 | China | 875087 | Gas Turbine | 155539 | Borescope Inspection (BI) | 535575 | 2026-12-01 | 2026-12-03
6FA.03 | China | 875085 | Gas Turbine | 155541 | Borescope Inspection (BI) | 535577 | 2026-05-26 | 2026-05-27
6FA.03 | China | 875086 | Gas Turbine | 155542 | Borescope Inspection (BI) | 535578 | 2026-05-28 | 2026-05-30
6FA.03 | Asia | 875102 | Gas Turbine | 155758 | Hot Gas Path Inspection (HGPI) | 535750 | 2027-04-01 | 2027-04-22
6FA.03 | Asia | 875081 | Gas Turbine | 155762 | Borescope Inspection (BI) | 535753 | 2026-07-25 | 2026-07-26
6FA.03 | Asia | 875082 | Gas Turbine | 155764 | Borescope Inspection (BI) | 535755 | 2026-10-03 | 2026-10-04
6FA.03 | Asia | 875084 | Gas Turbine | 155766 | Borescope Inspection (BI) | 535757 | 2026-02-12 | 2026-02-13
6FA.03 | China | 875085 | Gas Turbine | 156618 | Hot Gas Path Inspection (HGPI) | 538971 | 2027-10-08 | 2027-11-01
6FA.03 | MENA | 875043 | Gas Turbine | 157951 | Major Inspection (MI) | 537466 | 2028-10-01 | 2028-10-29
6FA.03 | MENA | 875028 | Gas Turbine | 158957 | Hot Gas Path Inspection (HGPI) | 538139 | 2030-03-19 | 2030-04-02
6FA.03 | Asia | 875036 | Gas Turbine | 159778 | Borescope Inspection (BI) | 538745 | 2027-05-24 | 2027-05-25
6FA.03 | Asia | 875037 | Gas Turbine | 159779 | Borescope Inspection (BI) | 538746 | 2027-05-26 | 2027-05-27
6FA.03 | Asia | 875052 | Gas Turbine | 160431 | Borescope Inspection (BI) | 539108 | 2026-10-15 | 2026-10-16
6FA.03 | Asia | 875058 | Gas Turbine | 160433 | Borescope Inspection (BI) | 539110 | 2026-11-17 | 2026-11-18
6FA.03 | China | 875146 | Gas Turbine | 160690 | Borescope Inspection (BI) | 563653 | 2026-06-08 | 2026-06-11
6FA.03 | China | 875147 | Gas Turbine | 160700 | Borescope Inspection (BI) | 539321 | 2026-09-21 | 2026-09-24
6FA.03 | Europe | 875009 | Gas Turbine | 164599 | Major Inspection (MI) | 542453 | 2026-06-15 | 2026-10-17
6FA.03 | Europe | 875010 | Gas Turbine | 164600 | Major Inspection (MI) | 542454 | 2028-07-24 | 2028-09-02
6FA.03 | Latin America | 875120 | Gas Turbine | 165508 | Major Inspection (MI) | 545522 | 2030-01-01 | 2030-01-29
6FA.03 | Latin America | 875149 | Gas Turbine | 165569 | Hot Gas Path Inspection (HGPI) | 543061 | 2030-08-05 | 2030-08-24
6FA.03 | Asia | 875127 | Gas Turbine | 166097 | Major Inspection (MI) | 552018 | 2030-08-01 | 2030-08-26
6FA.03 | Asia | 875126 | Gas Turbine | 166098 | Major Inspection (MI) | 552017 | 2030-07-01 | 2030-07-26
6FA.03 | Europe | 875166 | Gas Turbine | 166200 | Hot Gas Path Inspection (HGPI) | 543469 | 2029-05-06 | 2029-05-20
6FA.03 | MENA | 875045 | Gas Turbine | 166218 | Major Inspection (MI) | 543489 | 2028-10-01 | 2028-10-25
6FA.03 | MENA | 875121 | Gas Turbine | 166282 | Major Inspection (MI) | 543519 | 2028-07-01 | 2028-07-29
6FA.03 | MENA | 875129 | Gas Turbine | 166283 | Major Inspection (MI) | 543520 | 2029-01-03 | 2029-01-31
6FA.03 | MENA | 875128 | Gas Turbine | 166285 | Major Inspection (MI) | 543521 | 2028-08-31 | 2028-09-28
6FA.03 | MENA | 875130 | Gas Turbine | 166287 | Major Inspection (MI) | 543522 | 2029-02-07 | 2029-03-07
6FA.03 | MENA | 875064 | Gas Turbine | 166398 | Major Inspection (MI) | 543582 | 2027-10-18 | 2027-11-15
6FA.03 | MENA | 875066 | Gas Turbine | 166400 | Combustion Inspection (CI) |  | 2028-02-14 | 2028-02-21
6FA.03 | MENA | 875067 | Gas Turbine | 166401 | Combustion Inspection (CI) |  | 2028-08-25 | 2028-09-01
6FA.03 | MENA | 875065 | Gas Turbine | 166402 | Combustion Inspection (CI) |  | 2028-09-15 | 2028-09-22
6FA.03 | Europe | 875057 | Gas Turbine | 167009 | Combustion Inspection (CI) | 549091 | 2026-09-15 | 2026-10-04
6FA.03 | Europe | 875024 | Gas Turbine | 167010 | Combustion Inspection (CI) | 560490 | 2028-05-10 | 2028-05-17
6FA.03 | Europe | 875054 | Gas Turbine | 167011 | Hot Gas Path Inspection (HGPI) | 544050 | 2028-05-28 | 2028-06-11
6FA.03 | Europe | 875025 | Gas Turbine | 167013 | Combustion Inspection (CI) | 560491 | 2028-09-10 | 2028-09-17
6FA.03 | Europe | 875054 | Gas Turbine | 167014 | Combustion Inspection (CI) |  | 2030-07-26 | 2030-08-02
6FA.03 | Europe | 875057 | Gas Turbine | 167015 | Combustion Inspection (CI) |  | 2030-09-02 | 2030-09-09
6FA.03 | Europe | 875025 | Gas Turbine | 167016 | Hot Gas Path Inspection (HGPI) | 544051 | 2030-11-16 | 2030-11-30
6FA.03 | Europe | 875013 | Gas Turbine | 167022 | Hot Gas Path Inspection (HGPI) | 544052 | 2027-05-30 | 2027-06-21
6FA.03 | MENA | 875035 | Gas Turbine | 169163 | Combustion Inspection (CI) | 546019 | 2028-10-01 | 2028-10-20
6FA.03 | Europe | 875022 | Gas Turbine | 172172 | Hot Gas Path Inspection (HGPI) | 547505 | 2026-11-03 | 2026-12-02
6FA.03 | Europe | 875023 | Gas Turbine | 172175 | Hot Gas Path Inspection (HGPI) | 547507 | 2026-11-03 | 2026-12-02
6FA.03 | Europe | 875020 | Gas Turbine | 174333 | Hot Gas Path Inspection (HGPI) | 548885 | 2029-09-03 | 2029-09-28
6FA.03 | Europe | 875021 | Gas Turbine | 174335 | Hot Gas Path Inspection (HGPI) | 548886 | 2029-09-03 | 2029-09-28
6FA.03 | Europe | 875054 | Gas Turbine | 174655 | Combustion Inspection (CI) | 549092 | 2026-04-27 | 2026-05-16
6FA.03 | Europe | T6FA04 | Gas Turbine | 177674 | Stand Alone Small Upgrade | 552421 | 2026-08-03 | 2026-08-24
6FA.03 | Asia | 875084 | Gas Turbine | 184201 | Major Inspection (MI) | 554839 | 2028-08-01 | 2028-08-31
6FA.03 | Asia | 875082 | Gas Turbine | 184203 | Major Inspection (MI) | 554840 | 2029-05-01 | 2029-05-31
6FA.03 | Europe | 297148 | Gas Turbine | 192700 | Hot Gas Path Inspection (HGPI) |  | 2030-10-02 | 2030-10-16
6FA.03 | MENA | 875064 | Gas Turbine | 192717 | Combustion Inspection (CI) |  | 2029-07-26 | 2029-08-02
6FA.03 | MENA | 875059 | Gas Turbine | 192718 | Combustion Inspection (CI) |  | 2029-09-02 | 2029-09-09
6FA.03 | MENA | 875066 | Gas Turbine | 192720 | Hot Gas Path Inspection (HGPI) | 560709 | 2029-11-26 | 2029-12-10
6FA.03 | Europe | 875012 | Gas Turbine | 193493 | Major Inspection (MI) | 561244 | 2029-05-21 | 2029-06-19
6FA.03 | Asia | 875140 | Gas Turbine | 195074 | Combustion Inspection (CI) | 563419 | 2029-12-14 | 2029-12-21
6FA.03 | China | 875146 | Gas Turbine | 195447 | Large Call-Out | 563552 | 2026-09-25 | 2026-10-09
6FA.03 | Asia | 875140 | Gas Turbine | 195530 | Combustion Inspection (CI) | 563258 | 2026-11-15 | 2026-11-30
6FA.03 | Asia | 875014 | Gas Turbine | 195601 | Large Call-Out | 563197 | 2026-08-15 | 2026-10-17
6FA.03 | Europe | 875025 | Gas Turbine | 196040 | Combustion Inspection (CI) | 563390 | 2027-04-05 | 2027-05-21
6FA.03 | Europe | 875024 | Gas Turbine | 196041 | Hot Gas Path Inspection (HGPI) | 563345 | 2027-10-04 | 2027-11-08
6FA.03 | Asia | 875140 | Gas Turbine | 196123 | Hot Gas Path Inspection (HGPI) | 563418 | 2028-05-07 | 2028-05-21
7A6 | NAM North America | 436X240 | Generator | 108764 | Major Inspection (Rotor Out) | 515758 | 2029-09-12 | 2029-10-12
7A6 | NAM North America | 436X240 | Generator | 111513 | Minor Inspection | 507355 | 2027-09-15 | 2027-10-06
7A6 | NAM North America | 436X241 | Generator | 112894 | Major Inspection (Robotic) | 515764 | 2026-10-07 | 2026-10-24
7A6 | Asia | 337X636 | Generator | 116630 | Major Inspection (Robotic) | 506187 | 2026-05-05 | 2026-05-19
7A6 | NAM North America | 436X241 | Generator | 119315 | Major Inspection (Rotor Out) | 515763 | 2030-09-11 | 2030-10-11
7A6 | Asia | 337X637 | Generator | 121312 | Major Inspection (Robotic) | 506188 | 2026-04-16 | 2026-04-30
7A6 | MENA | 436X274 | Generator | 135159 | Minor Inspection | 522942 | 2028-01-06 | 2028-01-21
7A6 | NAM North America | 336X882 | Generator | 140721 | Major Inspection (Robotic) | 526378 | 2028-03-01 | 2028-04-04
7A6 | Latin America | 336X820 | Generator | 142591 | Minor Inspection | 527326 | 2026-04-23 | 2026-05-11
7A6 | NAM North America | 336X921 | Generator | 143920 | Major Inspection (Rotor Out) | 528278 | 2028-04-19 | 2028-06-12
7A6 | NAM North America | 336X858 | Generator | 153665 | Major Inspection (Robotic) | 503038 | 2029-10-01 | 2029-11-04
7A6 | NAM North America | 436X082 | Generator | 157912 | Minor Inspection | 537448 | 2026-05-02 | 2026-05-09
7A6 | MENA | 436X022 | Generator | 158669 | Minor Inspection | 537975 | 2026-11-23 | 2026-12-08
7A6 | MENA | 436X275 | Generator | 159070 | Minor Inspection | 538189 | 2028-06-03 | 2028-06-17
7A6 | NAM North America | 336X919 | Generator | 159437 | Major Inspection (Robotic) | 538470 | 2028-04-04 | 2028-04-24
7A6 | NAM North America | 336X916 | Generator | 159638 | Major Inspection (Rotor Out) | 538625 | 2026-05-14 | 2026-06-21
7A6 | NAM North America | 336X769 | Generator | 161109 | Minor Inspection | 539682 | 2026-10-19 | 2026-11-02
7A6 | NAM North America | 436X082 | Generator | 165197 | Major Inspection (Robotic) | 542857 | 2029-10-19 | 2029-11-16
7A6 | NAM North America | 436X081 | Generator | 165200 | Major Inspection (Robotic) | 542858 | 2029-08-21 | 2029-09-18
7A6 | Asia | 337X636 | Generator | 165444 | Minor Inspection | 538745 | 2026-06-25 | 2026-06-26
7A6 | NAM North America | 336X856 | Generator | 165690 | Major Inspection (Robotic) | 503036 | 2029-10-01 | 2029-11-04
7A6 | NAM North America | 336X860 | Generator | 165692 | Major Inspection (Robotic) | 503037 | 2030-10-01 | 2030-11-04
7A6 | NAM North America | 336X864 | Generator | 165784 | Major Inspection (Robotic) | 543213 | 2029-06-20 | 2029-07-18
7A6 | Latin America | 436X272 | Generator | 165833 | Major Inspection (Robotic) | 543232 | 2028-11-10 | 2028-11-24
7A6 | NAM North America | 336X969 | Generator | 165952 | Minor Inspection | 543312 | 2028-05-15 | 2028-05-31
7A6 | NAM North America | 336X969 | Generator | 165954 | Major Inspection (Robotic) | 543313 | 2030-09-21 | 2030-10-19
7A6 | NAM North America | 436X018 | Generator | 166188 | Major Inspection (Robotic) | 543457 | 2027-09-20 | 2027-10-14
7A6 | NAM North America | 336X823 | Generator | 166189 | Major Inspection (Robotic) | 543458 | 2028-03-25 | 2028-04-22
7A6 | NAM North America | 436X035 | Generator | 166193 | Minor Inspection | 504526 | 2026-09-11 | 2026-09-25
7A6 | NAM North America | 436X268 | Generator | 166194 | Minor Inspection | 504522 | 2028-07-22 | 2028-08-05
7A6 | NAM North America | 436X035 | Generator | 166195 | Major Inspection (Robotic) | 504524 | 2030-07-10 | 2030-08-07
7A6 | NAM North America | 336X805 | Generator | 166353 | Major Inspection (Rotor Out) | 543560 | 2027-03-25 | 2027-04-23
7A6 | NAM North America | 336X804 | Generator | 166356 | Major Inspection (Robotic) | 543561 | 2028-04-13 | 2028-05-29
7A6 | NAM North America | 336X800 | Generator | 166360 | Major Inspection (Robotic) | 543562 | 2028-09-24 | 2028-10-29
7A6 | NAM North America | 436X029 | Generator | 166374 | Major Inspection (Rotor Out) | 543569 | 2026-09-24 | 2026-10-22
7A6 | NAM North America | 336X920 | Generator | 166417 | Major Inspection (Robotic) | 543592 | 2029-05-08 | 2029-05-22
7A6 | NAM North America | 336X918 | Generator | 166443 | Minor Inspection | 543615 | 2028-04-20 | 2028-05-06
7A6 | NAM North America | 336X917 | Generator | 166447 | Minor Inspection | 543616 | 2029-11-07 | 2029-11-21
7A6 | NAM North America | 436X280 | Generator | 166488 | Minor Inspection | 543640 | 2028-10-04 | 2028-10-29
7A6 | NAM North America | 336X918 | Generator | 168474 | Large Call-Out | 545307 | 2026-04-20 | 2026-05-05
7A6 | NAM North America | 436X081 | Generator | 169317 | Minor Inspection | 545964 | 2026-05-15 | 2026-05-22
7A6 | NAM North America | 290T296 | Generator | 171240 | Minor Inspection |  | 2026-03-02 | 2026-04-17
7A6 | NAM North America | 290T296 | Generator | 171255 | Major Inspection (Stator Rewind) | 547081 | 2026-05-01 | 2026-06-20
7A6 | NAM North America | 290T586 | Generator | 172044 | Major Inspection (Rotor Out) | 547322 | 2026-02-06 | 2026-06-11
7A6 | NAM North America | 336X770 | Generator | 179790 | Minor Inspection | 552218 | 2028-03-01 | 2028-03-15
7A6 | NAM North America | 290T502 | Generator | 181270 | Major Inspection (Rotor Out) | 552953 | 2028-05-03 | 2028-06-12
7A6 | NAM North America | 290T501 | Generator | 181272 | Major Inspection (Rotor Out) | 552955 | 2028-03-28 | 2028-05-01
7A6 | NAM North America | 336X803 | Generator | 182188 | Minor Inspection | 530398 | 2026-06-18 | 2026-06-26
7A6 | NAM North America | 336X822 | Generator | 182771 | Minor Inspection | 553931 | 2029-01-22 | 2029-02-05
7A6 | NAM North America | 336X890 | Generator | 184537 | Minor Inspection | 555093 | 2026-09-14 | 2026-09-20
7A6 | NAM North America | 336X892 | Generator | 184538 | Minor Inspection | 555095 | 2026-09-14 | 2026-09-20
7A6 | NAM North America | 336X888 | Generator | 184543 | Minor Inspection | 555097 | 2026-09-14 | 2026-09-20
7A6 | NAM North America | 336X889 | Generator | 184548 | Minor Inspection | 555099 | 2026-09-15 | 2026-09-15
7A6 | NAM North America | 290T455 | Generator | 186710 | Minor Inspection | 556599 | 2027-02-11 | 2027-02-25
7A6 | NAM North America | 290T455 | Generator | 186712 | Minor Inspection | 556235 | 2027-03-21 | 2027-04-10
7A6 | NAM North America | 290T529 | Generator | 187593 | Major Inspection (Rotor Out) | 557259 | 2029-07-03 | 2029-07-31
7A6 | MENA | 436X023 | Generator | 191344 | Major Inspection (Robotic) | 559850 | 2028-04-02 | 2028-04-27
7A6 | MENA | 436X022 | Generator | 191361 | Major Inspection (Robotic) | 559865 | 2029-03-07 | 2029-04-01
7A6 | Latin America | 336X817 | Generator | 192323 | Minor Inspection | 560624 | 2026-10-01 | 2026-10-19
7A6 | Latin America | 336X817 | Generator | 193303 | Minor Inspection | 561109 | 2026-10-01 | 2026-10-19
7A6 | Latin America | 336X819 | Generator | 194074 | Minor Inspection | 561846 | 2027-02-01 | 2027-03-02
7A6 | Latin America | 336X817 | Generator | 194432 | Minor Inspection | 561108 | 2026-10-01 | 2026-10-19
7A6 | Latin America | 336X819 | Generator | 194433 | Minor Inspection | 561479 | 2027-02-01 | 2027-03-02
7A6 | Latin America | 336X818 | Generator | 195021 | Major Inspection (Rotor Out) | 562885 | 2027-06-03 | 2027-07-07
7A6 | Latin America | 336X818 | Generator | 195442 | Major Inspection (Rotor Out) | 562884 | 2027-06-03 | 2027-07-07
7A6 | NAM North America | 290T429 | Generator | 195640 | Major Inspection (Rotor Out) | 563031 | 2027-11-08 | 2027-12-09
7A7 | NAM North America | 316X979 | Generator | 164567 | Minor Inspection | 542424 | 2028-03-25 | 2028-04-08
7A7 | NAM North America | 338X101 | Generator | 166047 | Minor Inspection | 543368 | 2027-08-23 | 2027-09-10
7E.03 | NAM North America | 297731 | Gas Turbine | 143919 | Major Inspection (MI) | 528278 | 2028-04-19 | 2028-06-12
7E.03 | NAM North America | 282590 | Gas Turbine | 151101 | Major Inspection (MI) | 541668 | 2026-02-05 | 2026-06-25
7E.03 | NAM North America | 299471 | Gas Turbine | 151177 | Major Inspection (MI) | 547017 | 2027-06-16 | 2027-07-14
7E.03 | NAM North America | 299691 | Gas Turbine | 166046 | Hot Gas Path Inspection (HGPI) | 543368 | 2027-08-23 | 2027-09-10
7E.03 | NAM North America | 282590 | Gas Turbine | 166440 | Hot Gas Path Inspection (HGPI) | 543613 | 2030-06-01 | 2030-06-15
7E.03 | NAM North America | 299420 | Gas Turbine | 166487 | Hot Gas Path Inspection (HGPI) | 543640 | 2028-10-04 | 2028-10-29
7E.03 | NAM North America | 299471 | Gas Turbine | 174387 | Major Inspection (MI) | 548916 | 2027-06-16 | 2027-07-14
7E.03 | NAM North America | 299471 | Gas Turbine | 183269 | Major Inspection (MI) | 554281 | 2027-03-01 | 2027-03-29
7FA.03 | MENA | 298659 | Gas Turbine | 103897 | Hot Gas Path Inspection (HGPI) | 501589 | 2028-12-21 | 2029-01-04
7FA.03 | NAM North America | 297465 | Gas Turbine | 106354 | Combustion Inspection (CI) | 502727 | 2026-03-02 | 2026-03-24
7FA.03 | NAM North America | 297604 | Gas Turbine | 106514 | Major Inspection (MI) | 502887 | 2027-03-01 | 2027-05-05
7FA.03 | NAM North America | 297405 | Gas Turbine | 106600 | Major Inspection (MI) | 502973 | 2028-04-01 | 2028-05-09
7FA.03 | NAM North America | 297918 | Gas Turbine | 106649 | Major Inspection (MI) | 503022 | 2027-03-01 | 2027-04-08
7FA.03 | NAM North America | 297726 | Gas Turbine | 107708 | Major Inspection (MI) | 514523 | 2026-09-21 | 2026-10-30
7FA.03 | NAM North America | 297650 | Gas Turbine | 108841 | Major Inspection (MI) | 504915 | 2026-02-02 | 2026-02-28
7FA.03 | NAM North America | 297622 | Gas Turbine | 109072 | Major Inspection (MI) | 505365 | 2027-08-28 | 2027-11-12
7FA.03 | Latin America | 298026 | Gas Turbine | 109815 | Hot Gas Path Inspection (HGPI) | 507836 | 2026-01-14 | 2026-01-27
7FA.03 | NAM North America | 297620 | Gas Turbine | 111532 | Major Inspection (MI) | 512081 | 2027-10-01 | 2027-11-07
7FA.03 | Latin America | 298025 | Gas Turbine | 111839 | Hot Gas Path Inspection (HGPI) | 507744 | 2026-01-12 | 2026-01-27
7FA.03 | NAM North America | 298791 | Gas Turbine | 111983 | Hot Gas Path Inspection (HGPI) | 506454 | 2027-10-04 | 2027-11-05
7FA.03 | NAM North America | 298058 | Gas Turbine | 112163 | Major Inspection (MI) | 505671 | 2030-02-25 | 2030-03-25
7FA.03 | NAM North America | 298210 | Gas Turbine | 114930 | Hot Gas Path Inspection (HGPI) | 505683 | 2027-01-25 | 2027-02-08
7FA.03 | Latin America | 299000 | Gas Turbine | 115147 | Hot Gas Path Inspection (HGPI) | 513531 | 2026-01-27 | 2026-02-12
7FA.03 | NAM North America | 297031 | Gas Turbine | 115293 | Hot Gas Path Inspection (HGPI) | 505711 | 2026-01-19 | 2026-02-13
7FA.03 | NAM North America | 298809 | Gas Turbine | 116092 | Hot Gas Path Inspection (HGPI) | 514783 | 2027-04-05 | 2027-04-20
7FA.03 | Latin America | 298998 | Gas Turbine | 117068 | Hot Gas Path Inspection (HGPI) | 513310 | 2026-01-22 | 2026-02-07
7FA.03 | NAM North America | 298792 | Gas Turbine | 117522 | Hot Gas Path Inspection (HGPI) | 506452 | 2027-04-05 | 2027-05-07
7FA.03 | Latin America | 298999 | Gas Turbine | 118356 | Hot Gas Path Inspection (HGPI) | 513524 | 2026-02-07 | 2026-02-21
7FA.03 | NAM North America | 297916 | Gas Turbine | 119324 | Major Inspection (MI) | 513740 | 2026-03-01 | 2026-04-20
7FA.03 | NAM North America | 297616 | Gas Turbine | 119910 | Hot Gas Path Inspection (HGPI) | 510562 | 2030-08-31 | 2030-09-14
7FA.03 | NAM North America | 297649 | Gas Turbine | 119951 | Hot Gas Path Inspection (HGPI) | 504914 | 2026-02-02 | 2026-02-28
7FA.03 | NAM North America | 297552 | Gas Turbine | 121419 | Hot Gas Path Inspection (HGPI) | 509983 | 2029-03-01 | 2029-03-31
7FA.03 | NAM North America | 298810 | Gas Turbine | 121601 | Hot Gas Path Inspection (HGPI) | 514782 | 2027-04-05 | 2027-04-20
7FA.03 | NAM North America | 297917 | Gas Turbine | 121755 | Major Inspection (MI) | 513739 | 2026-10-01 | 2026-11-09
7FA.03 | NAM North America | 297616 | Gas Turbine | 122485 | Major Inspection (MI) | 505727 | 2026-11-03 | 2026-12-17
7FA.03 | NAM North America | 297621 | Gas Turbine | 122637 | Major Inspection (MI) | 505350 | 2027-08-28 | 2027-11-12
7FA.03 | NAM North America | 297205 | Gas Turbine | 123055 | Hot Gas Path Inspection (HGPI) | 503596 | 2028-03-20 | 2028-04-09
7FA.03 | NAM North America | 298057 | Gas Turbine | 124142 | Major Inspection (MI) | 505670 | 2030-10-14 | 2030-11-11
7FA.03 | NAM North America | 297616 | Gas Turbine | 124834 | Hot Gas Path Inspection (HGPI) | 505732 | 2028-04-11 | 2028-05-01
7FA.03 | NAM North America | 297197 | Gas Turbine | 125165 | Major Inspection (MI) | 504076 | 2028-04-15 | 2028-05-10
7FA.03 | Latin America | 299003 | Gas Turbine | 125846 | Hot Gas Path Inspection (HGPI) | 516738 | 2026-11-23 | 2026-12-07
7FA.03 | Latin America | 299001 | Gas Turbine | 126073 | Hot Gas Path Inspection (HGPI) | 516945 | 2026-11-06 | 2026-11-20
7FA.03 | Latin America | 298994 | Gas Turbine | 126555 | Major Inspection (MI) | 533199 | 2026-11-24 | 2026-12-22
7FA.03 | Latin America | 299114 | Gas Turbine | 126757 | Hot Gas Path Inspection (HGPI) | 517572 | 2026-11-06 | 2026-11-20
7FA.03 | NAM North America | 297607 | Gas Turbine | 137018 | Hot Gas Path Inspection (HGPI) | 524381 | 2026-03-02 | 2026-03-28
7FA.03 | MENA | 298664 | Gas Turbine | 139824 | Major Inspection (MI) | 525947 | 2026-01-15 | 2026-02-07
7FA.03 | NAM North America | 297752 | Gas Turbine | 144330 | Major Inspection (MI) | 551653 | 2028-05-08 | 2028-06-27
7FA.03 | NAM North America | 297751 | Gas Turbine | 144332 | Major Inspection (MI) | 551652 | 2028-05-08 | 2028-06-25
7FA.03 | NAM North America | 297414 | Gas Turbine | 144334 | Hot Gas Path Inspection (HGPI) | 542786 | 2027-03-21 | 2027-04-10
7FA.03 | NAM North America | 298209 | Gas Turbine | 144337 | Hot Gas Path Inspection (HGPI) | 542813 | 2026-09-28 | 2026-10-12
7FA.03 | NAM North America | 298211 | Gas Turbine | 144338 | Major Inspection (MI) | 542814 | 2027-09-14 | 2027-10-14
7FA.03 | NAM North America | 298353 | Gas Turbine | 144339 | Hot Gas Path Inspection (HGPI) | 528496 | 2026-04-27 | 2026-06-08
7FA.03 | NAM North America | 298356 | Gas Turbine | 144340 | Hot Gas Path Inspection (HGPI) | 535216 | 2026-10-21 | 2026-11-05
7FA.03 | NAM North America | 298355 | Gas Turbine | 144341 | Hot Gas Path Inspection (HGPI) | 538205 | 2027-05-19 | 2027-06-02
7FA.03 | NAM North America | 297607 | Gas Turbine | 144356 | Hot Gas Path Inspection (HGPI) | 542833 | 2026-03-26 | 2026-04-09
7FA.03 | Asia | 297360 | Gas Turbine | 144360 | Major Inspection (MI) | 529688 | 2026-01-01 | 2026-01-30
7FA.03 | Asia | 297361 | Gas Turbine | 144361 | Major Inspection (MI) | 535939 | 2026-04-01 | 2026-06-10
7FA.03 | NAM North America | 297891 | Gas Turbine | 144371 | Major Inspection (MI) | 538232 | 2028-02-21 | 2028-03-22
7FA.03 | NAM North America | 297892 | Gas Turbine | 144372 | Major Inspection (MI) | 538231 | 2028-02-21 | 2028-03-22
7FA.03 | Latin America | 297478 | Gas Turbine | 144377 | Major Inspection (MI) | 537958 | 2028-11-18 | 2028-12-16
7FA.03 | NAM North America | 298610 | Gas Turbine | 144378 | Hot Gas Path Inspection (HGPI) | 558856 | 2030-03-10 | 2030-03-24
7FA.03 | NAM North America | 298643 | Gas Turbine | 144381 | Major Inspection (MI) | 542877 | 2027-03-06 | 2027-05-04
7FA.03 | MENA | 298662 | Gas Turbine | 144389 | Major Inspection (MI) | 537961 | 2026-02-12 | 2026-03-07
7FA.03 | MENA | 298663 | Gas Turbine | 144390 | Major Inspection (MI) | 537962 | 2026-03-12 | 2026-04-06
7FA.03 | MENA | 298666 | Gas Turbine | 144391 | Major Inspection (MI) | 537963 | 2028-12-06 | 2029-01-03
7FA.03 | NAM North America | 297688 | Gas Turbine | 144393 | Major Inspection (MI) | 542845 | 2027-08-04 | 2027-10-09
7FA.03 | NAM North America | 297766 | Gas Turbine | 144399 | Major Inspection (MI) | 538254 | 2027-03-08 | 2027-04-06
7FA.03 | NAM North America | 297765 | Gas Turbine | 144400 | Major Inspection (MI) | 538258 | 2027-10-01 | 2027-10-29
7FA.03 | NAM North America | 297767 | Gas Turbine | 144402 | Major Inspection (MI) | 538323 | 2027-10-01 | 2027-10-27
7FA.03 | NAM North America | 298833 | Gas Turbine | 144406 | Hot Gas Path Inspection (HGPI) | 547286 | 2026-11-01 | 2026-11-24
7FA.03 | NAM North America | 297905 | Gas Turbine | 144421 | Major Inspection (MI) | 542891 | 2026-09-14 | 2026-10-11
7FA.03 | NAM North America | 297907 | Gas Turbine | 144422 | Major Inspection (MI) | 542892 | 2027-10-18 | 2027-11-14
7FA.03 | NAM North America | 297906 | Gas Turbine | 144423 | Major Inspection (MI) | 548484 | 2027-05-03 | 2027-05-30
7FA.03 | NAM North America | 297466 | Gas Turbine | 144428 | Hot Gas Path Inspection (HGPI) | 546954 | 2027-03-15 | 2027-03-31
7FA.03 | NAM North America | 297467 | Gas Turbine | 144429 | Major Inspection (MI) | 546955 | 2027-04-01 | 2027-04-30
7FA.03 | NAM North America | 298396 | Gas Turbine | 144860 | Borescope Inspection (BI) | 528673 | 2026-01-23 | 2026-01-29
7FA.03 | NAM North America | 298393 | Gas Turbine | 145029 | Hot Gas Path Inspection (HGPI) | 528795 | 2029-09-10 | 2029-10-10
7FA.03 | NAM North America | 298436 | Gas Turbine | 145031 | Hot Gas Path Inspection (HGPI) | 528796 | 2028-03-06 | 2028-04-06
7FA.03 | NAM North America | 298437 | Gas Turbine | 145033 | Hot Gas Path Inspection (HGPI) | 528797 | 2027-09-13 | 2027-10-13
7FA.03 | NAM North America | 298032 | Gas Turbine | 145247 | Major Inspection (MI) | 536414 | 2028-03-01 | 2028-04-14
7FA.03 | NAM North America | 298297 | Gas Turbine | 145404 | Hot Gas Path Inspection (HGPI) | 529082 | 2026-03-29 | 2026-05-07
7FA.03 | NAM North America | 298296 | Gas Turbine | 145406 | Hot Gas Path Inspection (HGPI) | 529084 | 2026-11-16 | 2026-12-20
7FA.03 | NAM North America | 298914 | Gas Turbine | 145483 | Major Inspection (MI) | 535679 | 2028-02-05 | 2028-03-19
7FA.03 | NAM North America | 298915 | Gas Turbine | 145485 | Major Inspection (MI) | 535680 | 2028-02-05 | 2028-03-01
7FA.03 | NAM North America | 298088 | Gas Turbine | 145490 | Hot Gas Path Inspection (HGPI) | 538270 | 2027-10-01 | 2027-10-15
7FA.03 | NAM North America | 298086 | Gas Turbine | 145491 | Hot Gas Path Inspection (HGPI) | 538269 | 2027-09-21 | 2027-10-05
7FA.03 | Latin America | 299148 | Gas Turbine | 145493 | Combustion Inspection (CI) |  | 2026-03-13 | 2026-03-20
7FA.03 | Latin America | 299149 | Gas Turbine | 145494 | Major Inspection (MI) | 536083 | 2027-09-01 | 2027-09-26
7FA.03 | Latin America | 299147 | Gas Turbine | 145495 | Major Inspection (MI) | 536085 | 2028-03-02 | 2028-03-25
7FA.03 | Latin America | 299148 | Gas Turbine | 145496 | Major Inspection (MI) | 536084 | 2028-01-10 | 2028-02-01
7FA.03 | NAM North America | 297749 | Gas Turbine | 145498 | Major Inspection (MI) | 531099 | 2026-04-11 | 2026-05-27
7FA.03 | NAM North America | 298251 | Gas Turbine | 145732 | Stand Alone Large Upgrade | 529229 | 2026-03-03 | 2026-04-30
7FA.03 | Latin America | 299095 | Gas Turbine | 146326 | Hot Gas Path Inspection (HGPI) | 535698 | 2027-11-17 | 2027-12-09
7FA.03 | Latin America | 299096 | Gas Turbine | 146327 | Hot Gas Path Inspection (HGPI) | 535699 | 2027-10-25 | 2027-11-16
7FA.03 | Latin America | 299097 | Gas Turbine | 146328 | Hot Gas Path Inspection (HGPI) | 535661 | 2027-09-27 | 2027-10-16
7FA.03 | Latin America | 298994 | Gas Turbine | 146533 | Hot Gas Path Inspection (HGPI) | 540911 | 2029-12-02 | 2029-12-30
7FA.03 | Latin America | 298995 | Gas Turbine | 146534 | Hot Gas Path Inspection (HGPI) | 540910 | 2028-10-02 | 2028-10-30
7FA.03 | Latin America | 298042 | Gas Turbine | 146535 | Major Inspection (MI) | 537613 | 2027-03-01 | 2027-03-30
7FA.03 | Latin America | 298043 | Gas Turbine | 146536 | Major Inspection (MI) | 537612 | 2027-03-01 | 2027-03-30
7FA.03 | NAM North America | 297328 | Gas Turbine | 147494 | Hot Gas Path Inspection (HGPI) | 542395 | 2028-03-25 | 2028-04-08
7FA.03 | NAM North America | 297811 | Gas Turbine | 147497 | Major Inspection (MI) | 542429 | 2027-01-09 | 2027-04-03
7FA.03 | NAM North America | 297810 | Gas Turbine | 147499 | Major Inspection (MI) | 542428 | 2027-01-09 | 2027-04-03
7FA.03 | NAM North America | 297387 | Gas Turbine | 147525 | Hot Gas Path Inspection (HGPI) | 542821 | 2026-10-01 | 2026-10-30
7FA.03 | NAM North America | 297590 | Gas Turbine | 147526 | Combustion Inspection (CI) |  | 2028-03-11 | 2028-03-18
7FA.03 | NAM North America | 298471 | Gas Turbine | 147527 | Hot Gas Path Inspection (HGPI) | 542836 | 2026-05-01 | 2026-05-31
7FA.03 | NAM North America | 298472 | Gas Turbine | 147528 | Hot Gas Path Inspection (HGPI) | 542835 | 2026-05-01 | 2026-05-31
7FA.03 | NAM North America | 298201 | Gas Turbine | 147529 | Hot Gas Path Inspection (HGPI) | 542839 | 2028-12-08 | 2028-12-22
7FA.03 | NAM North America | 298200 | Gas Turbine | 147530 | Hot Gas Path Inspection (HGPI) | 542840 | 2028-12-08 | 2028-12-22
7FA.03 | NAM North America | 297666 | Gas Turbine | 147536 | Hot Gas Path Inspection (HGPI) | 531419 | 2029-03-05 | 2029-03-22
7FA.03 | NAM North America | 297667 | Gas Turbine | 147538 | Major Inspection (MI) | 531420 | 2029-03-05 | 2029-04-03
7FA.03 | NAM North America | 298137 | Gas Turbine | 147545 | Major Inspection (MI) | 550906 | 2026-07-04 | 2026-08-01
7FA.03 | NAM North America | 298136 | Gas Turbine | 147547 | Major Inspection (MI) | 550907 | 2026-07-04 | 2026-08-01
7FA.03 | NAM North America | 297842 | Gas Turbine | 147548 | Hot Gas Path Inspection (HGPI) | 550910 | 2027-10-18 | 2027-11-05
7FA.03 | NAM North America | 297843 | Gas Turbine | 147549 | Hot Gas Path Inspection (HGPI) | 554952 | 2028-05-15 | 2028-06-02
7FA.03 | NAM North America | 297603 | Gas Turbine | 147577 | Major Inspection (MI) | 542656 | 2026-04-04 | 2026-05-01
7FA.03 | NAM North America | 297605 | Gas Turbine | 147578 | Hot Gas Path Inspection (HGPI) | 543923 | 2027-03-01 | 2027-05-05
7FA.03 | NAM North America | 297344 | Gas Turbine | 147587 | Hot Gas Path Inspection (HGPI) | 532112 | 2027-04-07 | 2027-05-17
7FA.03 | NAM North America | 297343 | Gas Turbine | 147588 | Hot Gas Path Inspection (HGPI) | 548598 | 2027-04-07 | 2027-05-20
7FA.03 | NAM North America | 297400 | Gas Turbine | 151014 | Borescope Inspection (BI) | 532392 | 2026-11-07 | 2026-11-20
7FA.03 | NAM North America | 297401 | Gas Turbine | 151015 | Borescope Inspection (BI) | 532393 | 2026-11-11 | 2026-11-20
7FA.03 | NAM North America | 297458 | Gas Turbine | 152546 | Borescope Inspection (BI) | 533525 | 2026-04-22 | 2026-05-03
7FA.03 | NAM North America | 297458 | Gas Turbine | 152548 | Borescope Inspection (BI) | 533528 | 2026-10-03 | 2026-10-10
7FA.03 | NAM North America | 297727 | Gas Turbine | 152651 | Major Inspection (MI) | 533619 | 2026-09-21 | 2026-10-30
7FA.03 | NAM North America | 297666 | Gas Turbine | 154036 | Borescope Inspection (BI) | 534663 | 2026-11-02 | 2026-11-06
7FA.03 | NAM North America | 297667 | Gas Turbine | 154037 | Borescope Inspection (BI) | 534664 | 2026-11-09 | 2026-11-13
7FA.03 | NAM North America | 297838 | Gas Turbine | 154555 | Borescope Inspection (BI) | 534916 | 2026-04-15 | 2026-04-24
7FA.03 | NAM North America | 297838 | Gas Turbine | 154556 | Borescope Inspection (BI) | 534917 | 2026-10-14 | 2026-10-16
7FA.03 | NAM North America | 297838 | Gas Turbine | 154557 | Borescope Inspection (BI) | 534918 | 2027-04-15 | 2027-04-24
7FA.03 | NAM North America | 297838 | Gas Turbine | 154558 | Borescope Inspection (BI) | 534919 | 2027-10-13 | 2027-10-15
7FA.03 | NAM North America | 297924 | Gas Turbine | 154662 | Borescope Inspection (BI) | 534992 | 2026-04-06 | 2026-04-09
7FA.03 | Latin America | 298026 | Gas Turbine | 157360 | Borescope Inspection (BI) | 536962 | 2027-01-08 | 2027-01-11
7FA.03 | Latin America | 298025 | Gas Turbine | 157361 | Borescope Inspection (BI) | 536963 | 2027-01-15 | 2027-01-18
7FA.03 | NAM North America | 297612 | Gas Turbine | 158592 | Hot Gas Path Inspection (HGPI) | 537930 | 2027-04-15 | 2027-05-01
7FA.03 | NAM North America | 297614 | Gas Turbine | 158595 | Hot Gas Path Inspection (HGPI) | 537931 | 2028-03-06 | 2028-03-22
7FA.03 | Latin America | 299148 | Gas Turbine | 158602 | Combustion Inspection (CI) |  | 2030-01-13 | 2030-01-20
7FA.03 | Latin America | 299147 | Gas Turbine | 158603 | Combustion Inspection (CI) |  | 2030-06-25 | 2030-07-02
7FA.03 | Latin America | 298025 | Gas Turbine | 158629 | Major Inspection (MI) | 537955 | 2029-09-30 | 2029-10-28
7FA.03 | Latin America | 298026 | Gas Turbine | 158632 | Major Inspection (MI) | 537956 | 2030-03-02 | 2030-03-30
7FA.03 | MENA | 298656 | Gas Turbine | 158647 | Hot Gas Path Inspection (HGPI) | 537964 | 2028-03-31 | 2028-04-14
7FA.03 | MENA | 298657 | Gas Turbine | 158650 | Hot Gas Path Inspection (HGPI) | 537965 | 2028-04-09 | 2028-04-23
7FA.03 | MENA | 298658 | Gas Turbine | 158651 | Hot Gas Path Inspection (HGPI) | 537966 | 2029-01-01 | 2029-01-15
7FA.03 | MENA | 298660 | Gas Turbine | 158653 | Hot Gas Path Inspection (HGPI) | 537967 | 2028-11-22 | 2028-12-06
7FA.03 | MENA | 298667 | Gas Turbine | 158656 | Major Inspection (MI) | 537968 | 2027-12-20 | 2028-01-14
7FA.03 | MENA | 298665 | Gas Turbine | 158657 | Major Inspection (MI) | 537969 | 2028-02-15 | 2028-03-13
7FA.03 | MENA | 298664 | Gas Turbine | 158659 | Hot Gas Path Inspection (HGPI) | 537970 | 2029-01-29 | 2029-02-12
7FA.03 | MENA | 298661 | Gas Turbine | 158661 | Hot Gas Path Inspection (HGPI) | 537971 | 2029-04-27 | 2029-05-11
7FA.03 | MENA | 298662 | Gas Turbine | 158663 | Hot Gas Path Inspection (HGPI) | 537972 | 2029-07-10 | 2029-07-24
7FA.03 | MENA | 298663 | Gas Turbine | 158665 | Hot Gas Path Inspection (HGPI) | 537973 | 2029-08-10 | 2029-08-24
7FA.03 | NAM North America | 297031 | Gas Turbine | 158685 | Major Inspection (MI) | 537989 | 2029-08-20 | 2029-09-17
7FA.03 | NAM North America | 297612 | Gas Turbine | 158691 | Borescope Inspection (BI) | 537995 | 2026-04-20 | 2026-04-24
7FA.03 | MENA | 298494 | Gas Turbine | 158914 | Hot Gas Path Inspection (HGPI) | 538115 | 2026-01-16 | 2026-02-01
7FA.03 | NAM North America | 297403 | Gas Turbine | 158918 | Major Inspection (MI) | 538121 | 2028-04-15 | 2028-05-13
7FA.03 | NAM North America | 297402 | Gas Turbine | 158919 | Major Inspection (MI) | 538122 | 2028-04-16 | 2028-05-14
7FA.03 | NAM North America | 297626 | Gas Turbine | 158924 | Major Inspection (MI) | 538125 | 2028-09-22 | 2028-10-20
7FA.03 | NAM North America | 297625 | Gas Turbine | 158926 | Major Inspection (MI) | 538126 | 2028-04-08 | 2028-05-06
7FA.03 | NAM North America | 298937 | Gas Turbine | 158929 | Major Inspection (MI) | 548237 | 2029-05-22 | 2029-06-19
7FA.03 | NAM North America | 297401 | Gas Turbine | 158934 | Major Inspection (MI) | 538129 | 2029-04-30 | 2029-05-28
7FA.03 | NAM North America | 298354 | Gas Turbine | 159096 | Hot Gas Path Inspection (HGPI) | 538206 | 2028-08-23 | 2028-09-07
7FA.03 | NAM North America | 298356 | Gas Turbine | 159099 | Major Inspection (MI) | 538207 | 2030-12-25 | 2031-02-22
7FA.03 | NAM North America | 297828 | Gas Turbine | 159123 | Hot Gas Path Inspection (HGPI) | 538219 | 2028-12-21 | 2029-01-04
7FA.03 | NAM North America | 297827 | Gas Turbine | 159124 | Hot Gas Path Inspection (HGPI) | 538221 | 2028-06-21 | 2028-07-05
7FA.03 | NAM North America | 297826 | Gas Turbine | 159125 | Hot Gas Path Inspection (HGPI) | 538220 | 2028-12-21 | 2029-01-04
7FA.03 | NAM North America | 298250 | Gas Turbine | 159144 | Major Inspection (MI) | 538233 | 2027-08-01 | 2027-10-01
7FA.03 | NAM North America | 298251 | Gas Turbine | 159146 | Major Inspection (MI) | 538234 | 2028-12-09 | 2029-01-06
7FA.03 | NAM North America | 297919 | Gas Turbine | 159158 | Major Inspection (MI) | 538237 | 2029-03-01 | 2029-04-08
7FA.03 | NAM North America | 297115 | Gas Turbine | 159229 | Hot Gas Path Inspection (HGPI) | 538297 | 2026-10-02 | 2026-10-19
7FA.03 | NAM North America | 297114 | Gas Turbine | 159231 | Hot Gas Path Inspection (HGPI) | 538298 | 2027-03-19 | 2027-04-05
7FA.03 | NAM North America | 297115 | Gas Turbine | 159235 | Major Inspection (MI) | 538299 | 2029-10-02 | 2029-11-30
7FA.03 | NAM North America | 297114 | Gas Turbine | 159238 | Major Inspection (MI) | 538300 | 2030-03-02 | 2030-04-30
7FA.03 | Asia | 297360 | Gas Turbine | 160252 | Borescope Inspection (BI) |  | 2026-10-10 | 2026-10-10
7FA.03 | Asia | 297361 | Gas Turbine | 160360 | Borescope Inspection (BI) |  | 2026-10-11 | 2026-10-11
7FA.03 | NAM North America | 297343 | Gas Turbine | 160546 | Borescope Inspection (BI) | 539210 | 2026-10-05 | 2026-10-06
7FA.03 | NAM North America | 297344 | Gas Turbine | 160549 | Borescope Inspection (BI) | 539212 | 2026-10-03 | 2026-10-04
7FA.03 | NAM North America | 297547 | Gas Turbine | 160551 | Borescope Inspection (BI) | 539214 | 2026-09-30 | 2026-10-02
7FA.03 | NAM North America | 297548 | Gas Turbine | 160559 | Borescope Inspection (BI) | 539221 | 2026-09-27 | 2026-09-29
7FA.03 | Latin America | 298078 | Gas Turbine | 162654 | Hot Gas Path Inspection (HGPI) | 540937 | 2028-02-15 | 2028-03-05
7FA.03 | Latin America | 299059 | Gas Turbine | 162661 | Major Inspection (MI) | 540943 | 2029-10-01 | 2029-10-29
7FA.03 | Latin America | 299058 | Gas Turbine | 162664 | Major Inspection (MI) | 540944 | 2029-10-01 | 2029-10-29
7FA.03 | NAM North America | 297768 | Gas Turbine | 162965 | Hot Gas Path Inspection (HGPI) | 541128 | 2029-01-24 | 2029-02-07
7FA.03 | NAM North America | 297769 | Gas Turbine | 162967 | Hot Gas Path Inspection (HGPI) | 541129 | 2029-11-30 | 2029-12-14
7FA.03 | NAM North America | 298007 | Gas Turbine | 163010 | Hot Gas Path Inspection (HGPI) | 541164 | 2029-05-23 | 2029-06-06
7FA.03 | NAM North America | 298005 | Gas Turbine | 163011 | Hot Gas Path Inspection (HGPI) | 541165 | 2029-05-23 | 2029-06-06
7FA.03 | MENA | 298492 | Gas Turbine | 163394 | Hot Gas Path Inspection (HGPI) | 541496 | 2026-10-02 | 2026-10-17
7FA.03 | NAM North America | 297970 | Gas Turbine | 164590 | Major Inspection (MI) | 542446 | 2028-03-08 | 2028-05-22
7FA.03 | NAM North America | 298209 | Gas Turbine | 165108 | Major Inspection (MI) | 542815 | 2030-04-01 | 2030-04-29
7FA.03 | NAM North America | 298210 | Gas Turbine | 165109 | Major Inspection (MI) | 542816 | 2030-10-01 | 2030-10-29
7FA.03 | NAM North America | 297388 | Gas Turbine | 165122 | Major Inspection (MI) | 542822 | 2029-10-05 | 2029-11-02
7FA.03 | NAM North America | 297587 | Gas Turbine | 165133 | Combustion Inspection (CI) |  | 2028-07-20 | 2028-07-27
7FA.03 | NAM North America | 297608 | Gas Turbine | 165151 | Major Inspection (MI) |  | 2029-10-01 | 2029-10-29
7FA.03 | NAM North America | 298472 | Gas Turbine | 165156 | Major Inspection (MI) | 542837 | 2030-03-04 | 2030-04-01
7FA.03 | NAM North America | 297175 | Gas Turbine | 165170 | Hot Gas Path Inspection (HGPI) | 552525 | 2028-09-11 | 2028-10-11
7FA.03 | NAM North America | 297686 | Gas Turbine | 165174 | Major Inspection (MI) | 542846 | 2028-12-23 | 2029-01-20
7FA.03 | NAM North America | 297687 | Gas Turbine | 165175 | Major Inspection (MI) | 542847 | 2028-02-08 | 2028-04-15
7FA.03 | NAM North America | 297602 | Gas Turbine | 165194 | Hot Gas Path Inspection (HGPI) | 555434 | 2029-04-21 | 2029-05-12
7FA.03 | NAM North America | 297460 | Gas Turbine | 165218 | Hot Gas Path Inspection (HGPI) | 542859 | 2029-12-31 | 2030-01-14
7FA.03 | NAM North America | 297459 | Gas Turbine | 165221 | Hot Gas Path Inspection (HGPI) | 542860 | 2030-04-30 | 2030-05-14
7FA.03 | NAM North America | 297196 | Gas Turbine | 165255 | Major Inspection (MI) | 542878 | 2028-11-14 | 2028-12-19
7FA.03 | NAM North America | 297968 | Gas Turbine | 165285 | Major Inspection (MI) | 542895 | 2027-03-10 | 2027-05-24
7FA.03 | NAM North America | 297967 | Gas Turbine | 165289 | Major Inspection (MI) | 542896 | 2027-03-10 | 2027-05-24
7FA.03 | NAM North America | 297969 | Gas Turbine | 165375 | Major Inspection (MI) | 542931 | 2028-03-08 | 2028-05-22
7FA.03 | NAM North America | 298610 | Gas Turbine | 165755 | Major Inspection (MI) | 543188 | 2026-01-25 | 2026-04-17
7FA.03 | NAM North America | 297180 | Gas Turbine | 167994 | Hot Gas Path Inspection (HGPI) | 544907 | 2028-10-17 | 2028-11-05
7FA.03 | NAM North America | 297178 | Gas Turbine | 168605 | Hot Gas Path Inspection (HGPI) | 545405 | 2028-09-11 | 2028-10-11
7FA.03 | NAM North America | 297550 | Gas Turbine | 168607 | Hot Gas Path Inspection (HGPI) | 545406 | 2029-03-05 | 2029-04-05
7FA.03 | NAM North America | 298396 | Gas Turbine | 169260 | Hot Gas Path Inspection (HGPI) | 550956 | 2027-02-05 | 2027-05-05
7FA.03 | NAM North America | 297649 | Gas Turbine | 169392 | Large Call-Out | 546012 | 2027-03-03 | 2027-03-21
7FA.03 | NAM North America | 297650 | Gas Turbine | 169394 | Large Call-Out | 546013 | 2027-03-03 | 2027-03-21
7FA.03 | NAM North America | 297686 | Gas Turbine | 172377 | Major Inspection (MI) | 547696 | 2027-02-04 | 2027-04-10
7FA.03 | NAM North America | 297780 | Gas Turbine | 172911 | Hot Gas Path Inspection (HGPI) | 547995 | 2027-10-03 | 2027-11-15
7FA.03 | NAM North America | 298041 | Gas Turbine | 172914 | Hot Gas Path Inspection (HGPI) | 547997 | 2027-10-03 | 2027-11-15
7FA.03 | NAM North America | 297778 | Gas Turbine | 172916 | Hot Gas Path Inspection (HGPI) | 547998 | 2028-03-02 | 2028-05-10
7FA.03 | NAM North America | 297779 | Gas Turbine | 172918 | Hot Gas Path Inspection (HGPI) | 547999 | 2028-10-03 | 2028-11-15
7FA.03 | NAM North America | 298938 | Gas Turbine | 173319 | Major Inspection (MI) |  | 2030-01-02 | 2030-01-30
7FA.03 | NAM North America | 297629 | Gas Turbine | 174039 | Hot Gas Path Inspection (HGPI) | 548742 | 2028-04-03 | 2028-05-08
7FA.03 | NAM North America | 297630 | Gas Turbine | 174040 | Hot Gas Path Inspection (HGPI) | 548743 | 2029-03-05 | 2029-04-13
7FA.03 | NAM North America | 296737 | Gas Turbine | 174048 | Stand Alone Small Upgrade | 548717 | 2026-02-28 | 2026-07-01
7FA.03 | NAM North America | 297180 | Gas Turbine | 174666 | Stand Alone Small Upgrade | 549108 | 2026-03-09 | 2026-03-20
7FA.03 | NAM North America | 297620 | Gas Turbine | 175519 | Combustion Inspection (CI) | 550219 | 2026-04-01 | 2026-04-08
7FA.03 | Latin America | 299114 | Gas Turbine | 175859 | Major Inspection (MI) | 556994 | 2030-11-19 | 2030-12-17
7FA.03 | Latin America | 299003 | Gas Turbine | 175860 | Major Inspection (MI) | 549906 | 2030-10-12 | 2030-11-08
7FA.03 | Latin America | 299001 | Gas Turbine | 175861 | Major Inspection (MI) | 557073 | 2030-11-11 | 2030-12-08
7FA.03 | NAM North America | 297730 | Gas Turbine | 176157 | Hot Gas Path Inspection (HGPI) | 550072 | 2030-10-01 | 2030-10-15
7FA.03 | NAM North America | 297729 | Gas Turbine | 176159 | Hot Gas Path Inspection (HGPI) | 550073 | 2030-04-24 | 2030-05-08
7FA.03 | NAM North America | 297728 | Gas Turbine | 176161 | Hot Gas Path Inspection (HGPI) | 550074 | 2029-09-01 | 2029-09-15
7FA.03 | NAM North America | 297405 | Gas Turbine | 176358 | Combustion Inspection (CI) | 550222 | 2026-04-01 | 2026-04-08
7FA.03 | NAM North America | 297322 | Gas Turbine | 177100 | Major Inspection (MI) | 551953 | 2026-10-01 | 2027-01-14
7FA.03 | NAM North America | 297719 | Gas Turbine | 177240 | Major Inspection (MI) | 552834 | 2026-05-19 | 2026-08-06
7FA.03 | NAM North America | 297181 | Gas Turbine | 177273 | Hot Gas Path Inspection (HGPI) | 550865 | 2030-10-01 | 2030-10-15
7FA.03 | NAM North America | 296737 | Gas Turbine | 177288 | Hot Gas Path Inspection (HGPI) | 550872 | 2029-08-24 | 2029-09-07
7FA.03 | NAM North America | 298297 | Gas Turbine | 177362 | Major Inspection (MI) | 550880 | 2029-10-14 | 2029-11-11
7FA.03 | NAM North America | 298471 | Gas Turbine | 177366 | Major Inspection (MI) | 556935 | 2030-03-18 | 2030-04-15
7FA.03 | NAM North America | 297923 | Gas Turbine | 177384 | Major Inspection (MI) | 550890 | 2030-03-01 | 2030-04-09
7FA.03 | NAM North America | 297924 | Gas Turbine | 177385 | Major Inspection (MI) | 550889 | 2029-03-03 | 2029-03-31
7FA.03 | NAM North America | 298136 | Gas Turbine | 177935 | Major Inspection (MI) | 551236 | 2027-04-15 | 2027-05-12
7FA.03 | NAM North America | 298137 | Gas Turbine | 177938 | Major Inspection (MI) | 551238 | 2027-04-15 | 2027-05-12
7FA.03 | NAM North America | 297322 | Gas Turbine | 181471 | Major Inspection (MI) | 553097 | 2026-10-01 | 2026-10-31
7FA.03 | NAM North America | 297718 | Gas Turbine | 181489 | Major Inspection (MI) | 553100 | 2026-09-06 | 2026-11-24
7FA.03 | NAM North America | 297956 | Gas Turbine | 181599 | Major Inspection (MI) | 553169 | 2027-03-28 | 2027-06-15
7FA.03 | Latin America | 298998 | Gas Turbine | 182152 | Major Inspection (MI) | 553594 | 2030-01-21 | 2030-02-17
7FA.03 | Latin America | 298999 | Gas Turbine | 182155 | Major Inspection (MI) | 553596 | 2030-02-20 | 2030-03-19
7FA.03 | Latin America | 299000 | Gas Turbine | 182157 | Major Inspection (MI) | 553597 | 2030-01-21 | 2030-02-17
7FA.03 | NAM North America | 297866 | Gas Turbine | 182410 | Major Inspection (MI) | 553722 | 2028-11-01 | 2028-11-28
7FA.03 | NAM North America | 297868 | Gas Turbine | 182411 | Major Inspection (MI) | 553723 | 2028-02-01 | 2028-03-01
7FA.03 | NAM North America | 297865 | Gas Turbine | 182414 | Major Inspection (MI) | 553724 | 2029-02-01 | 2029-03-01
7FA.03 | NAM North America | 297867 | Gas Turbine | 182416 | Major Inspection (MI) | 553725 | 2027-11-01 | 2027-12-01
7FA.03 | NAM North America | 298833 | Gas Turbine | 182460 | Hot Gas Path Inspection (HGPI) |  | 2026-10-01 | 2026-10-15
7FA.03 | NAM North America | 298833 | Gas Turbine | 182463 | Major Inspection (MI) | 553749 | 2030-02-01 | 2030-03-01
7FA.03 | NAM North America | 298045 | Gas Turbine | 183878 | Major Inspection (MI) | 554647 | 2026-09-01 | 2026-09-30
7FA.03 | NAM North America | 298250 | Gas Turbine | 184783 | Stand Alone Small Upgrade | 555284 | 2026-09-15 | 2026-09-28
7FA.03 | NAM North America | 297677 | Gas Turbine | 185523 | Major Inspection (MI) | 555822 | 2029-12-01 | 2029-12-11
7FA.03 | MENA | 298666 | Gas Turbine | 186149 | Major Inspection (MI) | 556249 | 2027-10-20 | 2027-11-13
7FA.03 | NAM North America | 297484 | Gas Turbine | 186243 | Hot Gas Path Inspection (HGPI) | 556327 | 2028-05-01 | 2028-05-22
7FA.03 | NAM North America | 297487 | Gas Turbine | 186244 | Hot Gas Path Inspection (HGPI) | 556328 | 2028-10-30 | 2028-11-20
7FA.03 | NAM North America | 297485 | Gas Turbine | 186245 | Hot Gas Path Inspection (HGPI) | 556329 | 2029-04-30 | 2029-05-21
7FA.03 | NAM North America | 297489 | Gas Turbine | 186246 | Hot Gas Path Inspection (HGPI) | 556330 | 2029-10-29 | 2029-11-19
7FA.03 | NAM North America | 297486 | Gas Turbine | 186247 | Hot Gas Path Inspection (HGPI) | 556331 | 2030-04-29 | 2030-05-20
7FA.03 | NAM North America | 297488 | Gas Turbine | 186248 | Hot Gas Path Inspection (HGPI) | 556332 | 2030-10-28 | 2030-11-18
7FA.03 | NAM North America | 297402 | Gas Turbine | 186301 | Hot Gas Path Inspection (HGPI) | 556368 | 2028-09-01 | 2028-09-15
7FA.03 | NAM North America | 298631 | Gas Turbine | 186965 | Hot Gas Path Inspection (HGPI) | 556774 | 2028-04-20 | 2028-05-15
7FA.03 | MENA | 298657 | Gas Turbine | 187617 | Hot Gas Path Inspection (HGPI) |  | 2028-12-08 | 2028-12-22
7FA.03 | MENA | 298658 | Gas Turbine | 187618 | Hot Gas Path Inspection (HGPI) |  | 2029-01-01 | 2029-01-15
7FA.03 | MENA | 298664 | Gas Turbine | 187619 | Hot Gas Path Inspection (HGPI) |  | 2029-01-29 | 2029-02-12
7FA.03 | MENA | 298661 | Gas Turbine | 187620 | Hot Gas Path Inspection (HGPI) |  | 2029-04-27 | 2029-05-11
7FA.03 | MENA | 298667 | Gas Turbine | 187621 | Major Inspection (MI) |  | 2030-06-02 | 2030-06-30
7FA.03 | NAM North America | 297400 | Gas Turbine | 187626 | Hot Gas Path Inspection (HGPI) |  | 2030-05-23 | 2030-06-06
7FA.03 | NAM North America | 297414 | Gas Turbine | 187638 | Hot Gas Path Inspection (HGPI) |  | 2026-10-02 | 2026-10-16
7FA.03 | NAM North America | 298914 | Gas Turbine | 187688 | Major Inspection (MI) |  | 2028-03-04 | 2028-04-01
7FA.03 | NAM North America | 297626 | Gas Turbine | 187696 | Major Inspection (MI) |  | 2027-10-10 | 2027-11-07
7FA.03 | NAM North America | 297826 | Gas Turbine | 187710 | Hot Gas Path Inspection (HGPI) |  | 2028-12-21 | 2029-01-04
7FA.03 | NAM North America | 297751 | Gas Turbine | 187722 | Major Inspection (MI) |  | 2028-09-01 | 2028-09-29
7FA.03 | NAM North America | 297752 | Gas Turbine | 187724 | Major Inspection (MI) |  | 2028-09-01 | 2028-09-29
7FA.03 | NAM North America | 298353 | Gas Turbine | 187730 | Hot Gas Path Inspection (HGPI) |  | 2026-11-13 | 2026-11-27
7FA.03 | NAM North America | 298353 | Gas Turbine | 187731 | Major Inspection (MI) |  | 2030-12-06 | 2031-01-03
7FA.03 | Latin America | 299148 | Gas Turbine | 187732 | Combustion Inspection (CI) |  | 2026-04-17 | 2026-04-24
7FA.03 | Latin America | 299147 | Gas Turbine | 187733 | Combustion Inspection (CI) |  | 2026-11-05 | 2026-11-12
7FA.03 | Latin America | 299149 | Gas Turbine | 187734 | Major Inspection (MI) |  | 2027-11-23 | 2027-12-21
7FA.03 | Latin America | 299148 | Gas Turbine | 187735 | Major Inspection (MI) |  | 2028-05-10 | 2028-06-07
7FA.03 | Latin America | 299147 | Gas Turbine | 187736 | Major Inspection (MI) |  | 2028-11-18 | 2028-12-16
7FA.03 | Latin America | 299149 | Gas Turbine | 187737 | Combustion Inspection (CI) |  | 2029-12-09 | 2029-12-16
7FA.03 | Latin America | 299148 | Gas Turbine | 187738 | Combustion Inspection (CI) |  | 2030-06-03 | 2030-06-10
7FA.03 | Latin America | 299147 | Gas Turbine | 187739 | Combustion Inspection (CI) |  | 2030-12-01 | 2030-12-08
7FA.03 | NAM North America | 297465 | Gas Turbine | 187751 | Combustion Inspection (CI) |  | 2026-03-09 | 2026-03-16
7FA.03 | NAM North America | 297466 | Gas Turbine | 187752 | Hot Gas Path Inspection (HGPI) |  | 2027-01-05 | 2027-01-19
7FA.03 | NAM North America | 297467 | Gas Turbine | 187753 | Major Inspection (MI) |  | 2027-01-15 | 2027-02-12
7FA.03 | NAM North America | 297322 | Gas Turbine | 187755 | Hot Gas Path Inspection (HGPI) | 557313 | 2030-09-01 | 2030-09-15
7FA.03 | NAM North America | 297719 | Gas Turbine | 187757 | Hot Gas Path Inspection (HGPI) | 557314 | 2030-09-17 | 2030-10-01
7FA.03 | NAM North America | 297180 | Gas Turbine | 187770 | Hot Gas Path Inspection (HGPI) |  | 2029-05-31 | 2029-06-14
7FA.03 | NAM North America | 297181 | Gas Turbine | 187771 | Hot Gas Path Inspection (HGPI) | 563521 | 2029-03-02 | 2029-03-21
7FA.03 | NAM North America | 297182 | Gas Turbine | 187772 | Hot Gas Path Inspection (HGPI) |  | 2030-10-01 | 2030-10-15
7FA.03 | NAM North America | 297918 | Gas Turbine | 187779 | Major Inspection (MI) |  | 2026-11-30 | 2026-12-28
7FA.03 | NAM North America | 298058 | Gas Turbine | 187787 | Major Inspection (MI) | 557320 | 2028-09-22 | 2028-10-20
7FA.03 | NAM North America | 298057 | Gas Turbine | 187790 | Major Inspection (MI) | 557321 | 2029-04-16 | 2029-05-14
7FA.03 | NAM North America | 298437 | Gas Turbine | 187792 | Hot Gas Path Inspection (HGPI) |  | 2027-09-11 | 2027-09-25
7FA.03 | NAM North America | 298436 | Gas Turbine | 187793 | Hot Gas Path Inspection (HGPI) |  | 2027-09-11 | 2027-09-25
7FA.03 | NAM North America | 297549 | Gas Turbine | 187795 | Hot Gas Path Inspection (HGPI) | 557322 | 2029-04-30 | 2029-05-14
7FA.03 | NAM North America | 297178 | Gas Turbine | 187797 | Hot Gas Path Inspection (HGPI) | 557323 | 2026-04-07 | 2026-04-21
7FA.03 | NAM North America | 297175 | Gas Turbine | 187798 | Hot Gas Path Inspection (HGPI) |  | 2029-04-03 | 2029-04-17
7FA.03 | NAM North America | 297176 | Gas Turbine | 187800 | Hot Gas Path Inspection (HGPI) | 557324 | 2030-03-04 | 2030-04-04
7FA.03 | NAM North America | 297606 | Gas Turbine | 187801 | Major Inspection (MI) |  | 2030-04-22 | 2030-05-20
7FA.03 | NAM North America | 297468 | Gas Turbine | 187819 | Hot Gas Path Inspection (HGPI) |  | 2029-05-30 | 2029-06-13
7FA.03 | NAM North America | 297906 | Gas Turbine | 187820 | Major Inspection (MI) |  | 2026-09-04 | 2026-10-02
7FA.03 | NAM North America | 297905 | Gas Turbine | 187821 | Major Inspection (MI) |  | 2026-10-14 | 2026-11-11
7FA.03 | NAM North America | 297907 | Gas Turbine | 187822 | Major Inspection (MI) |  | 2027-11-05 | 2027-12-03
7FA.03 | NAM North America | 297967 | Gas Turbine | 187826 | Major Inspection (MI) |  | 2027-02-01 | 2027-03-01
7FA.03 | NAM North America | 297968 | Gas Turbine | 187827 | Major Inspection (MI) |  | 2027-02-01 | 2027-03-01
7FA.03 | NAM North America | 297622 | Gas Turbine | 187830 | Major Inspection (MI) | 557327 | 2027-09-01 | 2027-09-29
7FA.03 | NAM North America | 297621 | Gas Turbine | 187831 | Major Inspection (MI) |  | 2027-09-01 | 2027-09-29
7FA.03 | MENA | 298665 | Gas Turbine | 188120 | Large Call-Out | 557989 | 2026-02-14 | 2026-03-02
7FA.03 | MENA | 298666 | Gas Turbine | 188121 | Large Call-Out | 557990 | 2026-03-13 | 2026-04-24
7FA.03 | MENA | 298667 | Gas Turbine | 188122 | Large Call-Out | 557991 | 2026-01-17 | 2026-02-04
7FA.03 | MENA | 298492 | Gas Turbine | 188441 | Hot Gas Path Inspection (HGPI) | 557761 | 2026-08-27 | 2026-09-10
7FA.03 | NAM North America | 297175 | Gas Turbine | 189299 | Stand Alone Small Upgrade | 558348 | 2026-09-15 | 2026-10-01
7FA.03 | NAM North America | 297176 | Gas Turbine | 189300 | Stand Alone Small Upgrade | 558349 | 2026-09-15 | 2026-10-01
7FA.03 | NAM North America | 297177 | Gas Turbine | 189301 | Stand Alone Small Upgrade | 558350 | 2026-09-15 | 2026-10-01
7FA.03 | NAM North America | 297178 | Gas Turbine | 189303 | Stand Alone Small Upgrade | 558351 | 2026-09-15 | 2026-10-01
7FA.03 | NAM North America | 298046 | Gas Turbine | 189659 | Hot Gas Path Inspection (HGPI) | 558553 | 2030-09-20 | 2030-10-10
7FA.03 | NAM North America | 297414 | Gas Turbine | 190120 | Large Call-Out | 558915 | 2026-05-08 | 2026-05-20
7FA.03 | MENA | 298656 | Gas Turbine | 190205 | Large Call-Out | 558988 | 2026-09-06 | 2026-09-21
7FA.03 | MENA | 298658 | Gas Turbine | 190206 | Large Call-Out | 558989 | 2026-12-13 | 2026-12-28
7FA.03 | MENA | 298659 | Gas Turbine | 190207 | Large Call-Out | 559450 | 2027-07-11 | 2027-07-27
7FA.03 | NAM North America | 297465 | Gas Turbine | 190435 | Hot Gas Path Inspection (HGPI) | 559157 | 2028-03-01 | 2028-03-17
7FA.03 | NAM North America | 297839 | Gas Turbine | 190594 | Stand Alone Small Upgrade | 560257 | 2026-10-01 | 2026-11-14
7FA.03 | NAM North America | 297840 | Gas Turbine | 190595 | Stand Alone Small Upgrade | 560258 | 2026-10-27 | 2026-12-10
7FA.03 | MENA | 298660 | Gas Turbine | 190807 | Large Call-Out | 561534 | 2027-01-30 | 2027-02-16
7FA.03 | MENA | 298495 | Gas Turbine | 191340 | Major Inspection (MI) | 559848 | 2028-10-07 | 2028-11-01
7FA.03 | MENA | 298491 | Gas Turbine | 191365 | Hot Gas Path Inspection (HGPI) | 559868 | 2029-11-02 | 2029-11-17
7FA.03 | MENA | 298492 | Gas Turbine | 191367 | Major Inspection (MI) | 559869 | 2030-10-06 | 2030-10-31
7FA.03 | MENA | 298493 | Gas Turbine | 191370 | Major Inspection (MI) | 559871 | 2028-12-02 | 2028-12-27
7FA.03 | MENA | 298494 | Gas Turbine | 191372 | Major Inspection (MI) | 559872 | 2029-12-02 | 2029-12-27
7FA.03 | MENA | 298496 | Gas Turbine | 191374 | Major Inspection (MI) | 559873 | 2029-10-07 | 2029-11-01
7FA.03 | NAM North America | 297603 | Gas Turbine | 191687 | Stand Alone Small Upgrade | 560053 | 2027-05-05 | 2028-01-03
7FA.03 | NAM North America | 297602 | Gas Turbine | 191688 | Stand Alone Small Upgrade | 560054 | 2027-04-01 | 2027-09-01
7FA.03 | NAM North America | 297605 | Gas Turbine | 191689 | Stand Alone Small Upgrade | 560055 | 2027-05-05 | 2028-01-03
7FA.03 | NAM North America | 297031 | Gas Turbine | 191708 | Major Inspection (MI) | 560068 | 2029-10-31 | 2029-11-28
7FA.03 | NAM North America | 297031 | Gas Turbine | 191717 | Major Inspection (MI) | 560070 | 2030-12-25 | 2030-12-31
7FA.03 | NAM North America | 297031 | Gas Turbine | 191718 | Major Inspection (MI) | 560071 | 2030-11-27 | 2030-12-25
7FA.03 | MENA | 298664 | Gas Turbine | 193049 | Large Call-Out | 560895 | 2027-11-23 | 2027-12-16
7FA.03 | MENA | 298662 | Gas Turbine | 193054 | Large Call-Out | 560900 | 2027-11-14 | 2027-11-30
7FA.03 | MENA | 298663 | Gas Turbine | 193057 | Large Call-Out | 560903 | 2027-10-20 | 2027-11-06
7FA.03 | NAM North America | 297621 | Gas Turbine | 193858 | Stand Alone Small Upgrade |  | 2027-04-02 | 2027-05-03
7FA.03 | NAM North America | 297728 | Gas Turbine | 194248 | Stand Alone Small Upgrade | 562149 | 2026-12-01 | 2026-12-15
7FA.03 | NAM North America | 297752 | Gas Turbine | 194503 | Large Call-Out | 562142 | 2027-05-08 | 2027-05-22
7FA.03 | NAM North America | 298200 | Gas Turbine | 194607 | Major Inspection (MI) | 562229 | 2029-02-16 | 2029-03-05
7FA.03 | NAM North America | 298201 | Gas Turbine | 194609 | Major Inspection (MI) | 562230 | 2029-02-16 | 2029-03-05
7FA.03 | NAM North America | 298250 | Gas Turbine | 194673 | Stand Alone Large Upgrade | 562307 | 2027-08-01 | 2027-10-01
7FA.03 | NAM North America | 298250 | Gas Turbine | 194674 | Stand Alone Large Upgrade | 562291 | 2027-08-01 | 2027-10-01
7FA.03 | NAM North America | 298631 | Gas Turbine | 194962 | Hot Gas Path Inspection (HGPI) |  | 2028-01-20 | 2028-02-03
7FA.03 | NAM North America | 298631 | Gas Turbine | 194963 | Major Inspection (MI) |  | 2030-11-01 | 2030-11-29
7FA.03 | NAM North America | 297688 | Gas Turbine | 195201 | Major Inspection (MI) |  | 2027-08-07 | 2027-09-04
7FA.03 | NAM North America | 297719 | Gas Turbine | 195256 | Hot Gas Path Inspection (HGPI) | 562749 | 2028-10-10 | 2028-10-24
7FA.03 | NAM North America | 297751 | Gas Turbine | 195416 | Large Call-Out | 563313 | 2027-04-19 | 2027-04-30
7FA.03 | NAM North America | 297649 | Gas Turbine | 195843 | Large Call-Out | 563178 | 2027-03-03 | 2027-03-19
7FA.03 | NAM North America | 297588 | Gas Turbine | 195856 | Hot Gas Path Inspection (HGPI) | 563191 | 2027-12-01 | 2027-12-14
7FA.03 | NAM North America | 297919 | Gas Turbine | 196363 | Large Call-Out | 563609 | 2026-07-22 | 2026-08-20
7FA.04 | Latin America | 299402 | Gas Turbine | 106438 | Hot Gas Path Inspection (HGPI) | 502811 | 2029-03-16 | 2029-04-04
7FA.04 | Latin America | 299400 | Gas Turbine | 106439 | Hot Gas Path Inspection (HGPI) | 502812 | 2029-02-04 | 2029-02-23
7FA.04 | NAM North America | 297756 | Gas Turbine | 106446 | Hot Gas Path Inspection (HGPI) | 502819 | 2026-02-07 | 2026-05-05
7FA.04 | NAM North America | 297757 | Gas Turbine | 106447 | Hot Gas Path Inspection (HGPI) | 502820 | 2026-02-07 | 2026-03-30
7FA.04 | NAM North America | 297914 | Gas Turbine | 106475 | Hot Gas Path Inspection (HGPI) | 502848 | 2026-03-06 | 2026-05-24
7FA.04 | NAM North America | 297493 | Gas Turbine | 106547 | Hot Gas Path Inspection (HGPI) | 502920 | 2026-04-19 | 2026-05-04
7FA.04 | Latin America | 298528 | Gas Turbine | 106560 | Hot Gas Path Inspection (HGPI) | 502933 | 2026-02-02 | 2026-02-25
7FA.04 | NAM North America | 297915 | Gas Turbine | 106591 | Major Inspection (MI) | 502964 | 2026-03-06 | 2026-05-24
7FA.04 | NAM North America | 297893 | Gas Turbine | 106593 | Major Inspection (MI) | 502966 | 2026-09-21 | 2027-01-17
7FA.04 | NAM North America | 297896 | Gas Turbine | 106594 | Major Inspection (MI) | 502967 | 2026-09-28 | 2027-02-03
7FA.04 | Latin America | 298477 | Gas Turbine | 106627 | Major Inspection (MI) | 503000 | 2026-03-02 | 2026-03-30
7FA.04 | Latin America | 298478 | Gas Turbine | 106628 | Major Inspection (MI) | 503001 | 2026-03-02 | 2026-03-28
7FA.04 | NAM North America | 297583 | Gas Turbine | 107138 | Major Inspection (MI) | 508055 | 2030-03-07 | 2030-04-04
7FA.04 | NAM North America | 297144 | Gas Turbine | 108899 | Major Inspection (MI) | 505724 | 2029-02-01 | 2029-03-02
7FA.04 | NAM North America | 297198 | Gas Turbine | 109131 | Major Inspection (MI) | 503167 | 2026-10-03 | 2026-11-02
7FA.04 | NAM North America | 297144 | Gas Turbine | 110513 | Hot Gas Path Inspection (HGPI) | 505719 | 2027-03-01 | 2027-03-19
7FA.04 | Latin America | 298513 | Gas Turbine | 113514 | Hot Gas Path Inspection (HGPI) | 513545 | 2026-01-05 | 2026-01-28
7FA.04 | NAM North America | 297641 | Gas Turbine | 113668 | Major Inspection (MI) | 508071 | 2029-05-20 | 2029-06-17
7FA.04 | NAM North America | 297615 | Gas Turbine | 115249 | Major Inspection (MI) | 506361 | 2027-03-01 | 2027-04-13
7FA.04 | NAM North America | 297143 | Gas Turbine | 117520 | Hot Gas Path Inspection (HGPI) | 505720 | 2026-04-03 | 2026-04-26
7FA.04 | NAM North America | 297615 | Gas Turbine | 118117 | Hot Gas Path Inspection (HGPI) | 506360 | 2029-10-22 | 2029-11-05
7FA.04 | Latin America | 298512 | Gas Turbine | 118315 | Hot Gas Path Inspection (HGPI) | 513546 | 2026-01-05 | 2026-01-28
7FA.04 | NAM North America | 296073 | Gas Turbine | 118641 | Hot Gas Path Inspection (HGPI) | 515661 | 2026-05-01 | 2026-06-20
7FA.04 | NAM North America | 297143 | Gas Turbine | 120857 | Major Inspection (MI) | 505722 | 2029-03-01 | 2029-03-28
7FA.04 | Latin America | 299391 | Gas Turbine | 122987 | Major Inspection (MI) | 541015 | 2028-01-07 | 2028-01-12
7FA.04 | NAM North America | 297640 | Gas Turbine | 123770 | Major Inspection (MI) | 508067 | 2029-05-20 | 2029-06-17
7FA.04 | NAM North America | 297584 | Gas Turbine | 124421 | Major Inspection (MI) | 508061 | 2030-03-06 | 2030-04-03
7FA.04 | NAM North America | 297714 | Gas Turbine | 125001 | Hot Gas Path Inspection (HGPI) | 510963 | 2026-03-27 | 2026-06-01
7FA.04 | NAM North America | 298392 | Gas Turbine | 136069 | Major Inspection (MI) | 523622 | 2027-03-15 | 2027-05-24
7FA.04 | MENA | 299334 | Gas Turbine | 139831 | Major Inspection (MI) | 525952 | 2026-10-19 | 2026-11-12
7FA.04 | NAM North America | 297929 | Gas Turbine | 144336 | Hot Gas Path Inspection (HGPI) | 542795 | 2026-09-26 | 2026-10-16
7FA.04 | NAM North America | 298569 | Gas Turbine | 144342 | Major Inspection (MI) | 544853 | 2027-10-31 | 2028-01-13
7FA.04 | NAM North America | 298568 | Gas Turbine | 144344 | Major Inspection (MI) | 542824 | 2027-10-17 | 2027-12-30
7FA.04 | NAM North America | 297884 | Gas Turbine | 144347 | Major Inspection (MI) |  | 2027-05-21 | 2027-06-18
7FA.04 | NAM North America | 297665 | Gas Turbine | 144350 | Hot Gas Path Inspection (HGPI) | 542830 | 2026-11-01 | 2026-11-15
7FA.04 | NAM North America | 298178 | Gas Turbine | 144357 | Hot Gas Path Inspection (HGPI) | 551131 | 2027-10-21 | 2027-11-09
7FA.04 | NAM North America | 298177 | Gas Turbine | 144358 | Major Inspection (MI) | 551132 | 2027-10-21 | 2027-11-24
7FA.04 | NAM North America | 297772 | Gas Turbine | 144364 | Hot Gas Path Inspection (HGPI) | 538204 | 2026-02-18 | 2026-03-31
7FA.04 | NAM North America | 297773 | Gas Turbine | 144366 | Hot Gas Path Inspection (HGPI) | 538203 | 2026-02-18 | 2026-03-31
7FA.04 | NAM North America | 297722 | Gas Turbine | 144367 | Major Inspection (MI) | 541896 | 2027-04-26 | 2027-05-24
7FA.04 | NAM North America | 298357 | Gas Turbine | 144368 | Major Inspection (MI) | 542849 | 2026-02-02 | 2026-03-24
7FA.04 | NAM North America | 298358 | Gas Turbine | 144370 | Major Inspection (MI) | 542850 | 2026-02-09 | 2026-03-24
7FA.04 | Latin America | 297476 | Gas Turbine | 144374 | Hot Gas Path Inspection (HGPI) | 537317 | 2027-02-05 | 2027-02-19
7FA.04 | Latin America | 297477 | Gas Turbine | 144375 | Hot Gas Path Inspection (HGPI) | 537957 | 2028-11-18 | 2028-12-02
7FA.04 | NAM North America | 298924 | Gas Turbine | 144382 | Hot Gas Path Inspection (HGPI) | 528813 | 2027-03-15 | 2027-05-24
7FA.04 | NAM North America | 299141 | Gas Turbine | 144383 | Hot Gas Path Inspection (HGPI) | 542787 | 2027-02-17 | 2027-04-07
7FA.04 | NAM North America | 299140 | Gas Turbine | 144384 | Hot Gas Path Inspection (HGPI) | 544908 | 2027-02-17 | 2027-03-31
7FA.04 | NAM North America | 298004 | Gas Turbine | 144385 | Major Inspection (MI) | 531436 | 2027-03-14 | 2027-04-16
7FA.04 | NAM North America | 298974 | Gas Turbine | 144386 | Hot Gas Path Inspection (HGPI) | 534306 | 2026-04-13 | 2026-05-05
7FA.04 | NAM North America | 298975 | Gas Turbine | 144387 | Hot Gas Path Inspection (HGPI) | 534338 | 2026-10-19 | 2026-11-10
7FA.04 | NAM North America | 298973 | Gas Turbine | 144388 | Hot Gas Path Inspection (HGPI) | 534646 | 2027-04-09 | 2027-04-26
7FA.04 | MENA | 299017 | Gas Turbine | 144396 | Major Inspection (MI) | 545694 | 2027-10-29 | 2027-11-23
7FA.04 | MENA | 299016 | Gas Turbine | 144397 | Major Inspection (MI) | 538113 | 2027-12-03 | 2027-12-28
7FA.04 | NAM North America | 297876 | Gas Turbine | 144414 | Major Inspection (MI) | 531596 | 2026-10-02 | 2026-12-01
7FA.04 | NAM North America | 297897 | Gas Turbine | 144415 | Major Inspection (MI) | 531598 | 2026-10-30 | 2026-12-14
7FA.04 | Latin America | 299276 | Gas Turbine | 144416 | Hot Gas Path Inspection (HGPI) | 548488 | 2028-02-04 | 2028-02-18
7FA.04 | NAM North America | 298126 | Gas Turbine | 144431 | Major Inspection (MI) | 542784 | 2027-10-01 | 2027-10-29
7FA.04 | Asia | 298618 | Gas Turbine | 144432 | Major Inspection (MI) | 536498 | 2026-08-02 | 2026-12-25
7FA.04 | Asia | 298617 | Gas Turbine | 144433 | Major Inspection (MI) | 546279 | 2027-10-01 | 2027-12-15
7FA.04 | Latin America | 299399 | Gas Turbine | 144443 | Hot Gas Path Inspection (HGPI) | 559936 | 2029-01-15 | 2029-02-03
7FA.04 | Latin America | 299401 | Gas Turbine | 144444 | Hot Gas Path Inspection (HGPI) | 559937 | 2029-02-24 | 2029-03-15
7FA.04 | NAM North America | 299317 | Gas Turbine | 144449 | Major Inspection (MI) | 538244 | 2027-03-13 | 2027-04-12
7FA.04 | Asia | 297953 | Gas Turbine | 145474 | Major Inspection (MI) | 533750 | 2027-02-05 | 2027-03-10
7FA.04 | NAM North America | 297715 | Gas Turbine | 145475 | Hot Gas Path Inspection (HGPI) | 542848 | 2026-05-17 | 2026-06-02
7FA.04 | NAM North America | 298613 | Gas Turbine | 145478 | Hot Gas Path Inspection (HGPI) | 535677 | 2026-03-27 | 2026-05-19
7FA.04 | NAM North America | 298614 | Gas Turbine | 145479 | Hot Gas Path Inspection (HGPI) | 535678 | 2026-03-27 | 2026-05-19
7FA.04 | NAM North America | 297758 | Gas Turbine | 145481 | Hot Gas Path Inspection (HGPI) | 535682 | 2027-01-21 | 2027-03-13
7FA.04 | NAM North America | 297759 | Gas Turbine | 145482 | Hot Gas Path Inspection (HGPI) | 535683 | 2027-01-21 | 2027-03-13
7FA.04 | NAM North America | 297096 | Gas Turbine | 145486 | Major Inspection (MI) | 529218 | 2026-05-04 | 2026-06-11
7FA.04 | NAM North America | 299480 | Gas Turbine | 145487 | Hot Gas Path Inspection (HGPI) | 529219 | 2027-03-29 | 2027-04-15
7FA.04 | Asia | 298922 | Gas Turbine | 145500 | Major Inspection (MI) | 547159 | 2026-04-04 | 2026-06-25
7FA.04 | Asia | 298923 | Gas Turbine | 145501 | Major Inspection (MI) | 547174 | 2026-04-04 | 2026-08-28
7FA.04 | Asia | 298921 | Gas Turbine | 145502 | Hot Gas Path Inspection (HGPI) | 546282 | 2027-03-20 | 2027-06-12
7FA.04 | Asia | 298997 | Gas Turbine | 145503 | Hot Gas Path Inspection (HGPI) | 546283 | 2027-03-20 | 2027-06-12
7FA.04 | Asia | 298918 | Gas Turbine | 145504 | Hot Gas Path Inspection (HGPI) |  | 2028-03-21 | 2028-07-19
7FA.04 | NAM North America | 297760 | Gas Turbine | 145506 | Major Inspection (MI) |  | 2026-04-01 | 2026-04-29
7FA.04 | Asia | 299200 | Gas Turbine | 145511 | Major Inspection (MI) | 546281 | 2027-09-01 | 2027-12-03
7FA.04 | NAM North America | 297937 | Gas Turbine | 146509 | Major Inspection (MI) | 542916 | 2026-11-04 | 2026-12-15
7FA.04 | Latin America | 299098 | Gas Turbine | 146510 | Major Inspection (MI) | 530181 | 2027-02-19 | 2027-03-22
7FA.04 | Latin America | 299099 | Gas Turbine | 146511 | Major Inspection (MI) | 530213 | 2027-03-24 | 2027-04-24
7FA.04 | Latin America | 299123 | Gas Turbine | 146513 | Major Inspection (MI) | 540792 | 2028-04-09 | 2028-05-10
7FA.04 | Latin America | 299122 | Gas Turbine | 146514 | Major Inspection (MI) | 533954 | 2028-05-15 | 2028-06-15
7FA.04 | Latin America | 299183 | Gas Turbine | 146515 | Major Inspection (MI) | 540980 | 2026-03-26 | 2026-04-29
7FA.04 | Latin America | 299182 | Gas Turbine | 146516 | Major Inspection (MI) | 540789 | 2026-05-03 | 2026-06-03
7FA.04 | Latin America | 298099 | Gas Turbine | 146572 | Major Inspection (MI) | 534881 | 2030-06-25 | 2030-07-24
7FA.04 | Latin America | 299465 | Gas Turbine | 146688 | Major Inspection (MI) | 534894 | 2029-02-17 | 2029-03-13
7FA.04 | Latin America | 299466 | Gas Turbine | 146689 | Major Inspection (MI) | 534893 | 2029-02-17 | 2029-03-13
7FA.04 | Latin America | 299464 | Gas Turbine | 146690 | Major Inspection (MI) | 534892 | 2028-02-18 | 2028-03-13
7FA.04 | Latin America | 299463 | Gas Turbine | 146691 | Major Inspection (MI) | 534891 | 2028-02-18 | 2028-03-13
7FA.04 | Asia | 299024 | Gas Turbine | 146723 | Combustion Inspection (CI) | 552037 | 2026-10-05 | 2026-10-13
7FA.04 | MENA | 299426 | Gas Turbine | 146804 | Hot Gas Path Inspection (HGPI) | 538302 | 2027-06-11 | 2027-06-25
7FA.04 | MENA | 299234 | Gas Turbine | 146807 | Hot Gas Path Inspection (HGPI) | 530623 | 2026-03-29 | 2026-05-12
7FA.04 | MENA | 299235 | Gas Turbine | 146808 | Hot Gas Path Inspection (HGPI) | 540889 | 2027-01-12 | 2027-01-26
7FA.04 | MENA | 299236 | Gas Turbine | 146809 | Hot Gas Path Inspection (HGPI) | 556588 | 2028-01-06 | 2028-01-20
7FA.04 | NAM North America | 297601 | Gas Turbine | 146923 | Hot Gas Path Inspection (HGPI) | 544848 | 2028-03-01 | 2028-05-15
7FA.04 | NAM North America | 298339 | Gas Turbine | 147531 | Major Inspection (MI) | 542842 | 2028-03-06 | 2028-04-09
7FA.04 | NAM North America | 298340 | Gas Turbine | 147532 | Major Inspection (MI) | 545051 | 2028-03-06 | 2028-04-09
7FA.04 | NAM North America | 297544 | Gas Turbine | 147533 | Hot Gas Path Inspection (HGPI) | 542762 | 2027-04-03 | 2027-05-17
7FA.04 | NAM North America | 297546 | Gas Turbine | 147534 | Hot Gas Path Inspection (HGPI) | 542923 | 2027-04-03 | 2027-05-17
7FA.04 | NAM North America | 297545 | Gas Turbine | 147535 | Major Inspection (MI) | 555022 | 2029-04-01 | 2029-04-29
7FA.04 | NAM North America | 298122 | Gas Turbine | 147539 | Hot Gas Path Inspection (HGPI) | 530377 | 2026-09-23 | 2026-10-17
7FA.04 | NAM North America | 298123 | Gas Turbine | 147540 | Hot Gas Path Inspection (HGPI) | 530378 | 2026-09-23 | 2026-10-17
7FA.04 | NAM North America | 297381 | Gas Turbine | 147541 | Hot Gas Path Inspection (HGPI) | 550901 | 2027-11-09 | 2027-11-28
7FA.04 | NAM North America | 297382 | Gas Turbine | 147543 | Hot Gas Path Inspection (HGPI) | 550902 | 2027-11-09 | 2027-11-28
7FA.04 | Latin America | 297963 | Gas Turbine | 147550 | Hot Gas Path Inspection (HGPI) | 530594 | 2026-11-01 | 2026-12-02
7FA.04 | Latin America | 297964 | Gas Turbine | 147552 | Hot Gas Path Inspection (HGPI) | 530595 | 2026-11-01 | 2026-12-02
7FA.04 | Latin America | 297962 | Gas Turbine | 147553 | Major Inspection (MI) | 542798 | 2029-03-01 | 2029-03-30
7FA.04 | Latin America | 297961 | Gas Turbine | 147555 | Major Inspection (MI) | 542799 | 2029-03-01 | 2029-03-30
7FA.04 | Latin America | 298374 | Gas Turbine | 147556 | Hot Gas Path Inspection (HGPI) | 545047 | 2027-01-16 | 2027-01-30
7FA.04 | Latin America | 298375 | Gas Turbine | 147558 | Hot Gas Path Inspection (HGPI) | 545048 | 2027-01-16 | 2027-01-30
7FA.04 | Latin America | 298527 | Gas Turbine | 147561 | Hot Gas Path Inspection (HGPI) | 542802 | 2026-02-02 | 2026-02-25
7FA.04 | Latin America | 298480 | Gas Turbine | 147563 | Hot Gas Path Inspection (HGPI) | 545049 | 2029-01-15 | 2029-02-03
7FA.04 | Latin America | 298479 | Gas Turbine | 147564 | Hot Gas Path Inspection (HGPI) | 545050 | 2029-01-15 | 2029-02-03
7FA.04 | Latin America | 298478 | Gas Turbine | 147565 | Hot Gas Path Inspection (HGPI) | 542808 | 2030-03-01 | 2030-03-21
7FA.04 | Latin America | 298477 | Gas Turbine | 147567 | Hot Gas Path Inspection (HGPI) | 542807 | 2030-03-01 | 2030-03-21
7FA.04 | NAM North America | 298288 | Gas Turbine | 147568 | Major Inspection (MI) | 534890 | 2026-04-11 | 2026-05-05
7FA.04 | NAM North America | 297273 | Gas Turbine | 147569 | Major Inspection (MI) | 542834 | 2027-11-08 | 2027-12-09
7FA.04 | NAM North America | 298341 | Gas Turbine | 147570 | Major Inspection (MI) | 542841 | 2028-10-06 | 2028-11-09
7FA.04 | NAM North America | 298113 | Gas Turbine | 147571 | Hot Gas Path Inspection (HGPI) | 542853 | 2028-04-01 | 2028-04-15
7FA.04 | NAM North America | 298128 | Gas Turbine | 147573 | Hot Gas Path Inspection (HGPI) | 542855 | 2028-09-30 | 2028-10-14
7FA.04 | NAM North America | 298112 | Gas Turbine | 147575 | Hot Gas Path Inspection (HGPI) | 542854 | 2028-04-01 | 2028-04-15
7FA.04 | NAM North America | 298127 | Gas Turbine | 147576 | Hot Gas Path Inspection (HGPI) | 542856 | 2028-09-30 | 2028-10-14
7FA.04 | NAM North America | 297152 | Gas Turbine | 147579 | Hot Gas Path Inspection (HGPI) | 542865 | 2027-09-16 | 2027-11-04
7FA.04 | NAM North America | 297151 | Gas Turbine | 147580 | Hot Gas Path Inspection (HGPI) | 542864 | 2027-09-16 | 2027-11-04
7FA.04 | NAM North America | 297783 | Gas Turbine | 147593 | Major Inspection (MI) | 542888 | 2027-11-18 | 2027-12-16
7FA.04 | NAM North America | 297255 | Gas Turbine | 147594 | Hot Gas Path Inspection (HGPI) | 541291 | 2028-03-07 | 2028-03-21
7FA.04 | NAM North America | 297256 | Gas Turbine | 147595 | Hot Gas Path Inspection (HGPI) | 541292 | 2028-03-07 | 2028-03-21
7FA.04 | NAM North America | 298016 | Gas Turbine | 147597 | Major Inspection (MI) | 541289 | 2028-04-03 | 2028-05-03
7FA.04 | NAM North America | 298017 | Gas Turbine | 147599 | Major Inspection (MI) | 541290 | 2028-04-03 | 2028-05-03
7FA.04 | NAM North America | 298015 | Gas Turbine | 147600 | Major Inspection (MI) | 541288 | 2028-04-03 | 2028-05-03
7FA.04 | NAM North America | 298003 | Gas Turbine | 149470 | Major Inspection (MI) | 531435 | 2028-03-28 | 2028-04-30
7FA.04 | NAM North America | 298002 | Gas Turbine | 149473 | Major Inspection (MI) | 531437 | 2029-03-28 | 2029-04-30
7FA.04 | NAM North America | 297875 | Gas Turbine | 149670 | Major Inspection (MI) | 531595 | 2027-09-28 | 2027-11-12
7FA.04 | NAM North America | 297877 | Gas Turbine | 149673 | Major Inspection (MI) | 531597 | 2028-09-28 | 2028-11-12
7FA.04 | NAM North America | 297898 | Gas Turbine | 149676 | Major Inspection (MI) | 531599 | 2027-04-15 | 2027-05-30
7FA.04 | NAM North America | 297899 | Gas Turbine | 149678 | Major Inspection (MI) | 531600 | 2027-10-02 | 2027-11-16
7FA.04 | NAM North America | 297925 | Gas Turbine | 150953 | Borescope Inspection (BI) | 532379 | 2026-03-21 | 2026-04-01
7FA.04 | NAM North America | 297927 | Gas Turbine | 150955 | Borescope Inspection (BI) | 532381 | 2026-04-02 | 2026-04-10
7FA.04 | NAM North America | 297925 | Gas Turbine | 150956 | Borescope Inspection (BI) | 532382 | 2026-12-04 | 2026-12-07
7FA.04 | NAM North America | 297893 | Gas Turbine | 151335 | Borescope Inspection (BI) | 532561 | 2026-10-05 | 2026-10-13
7FA.04 | NAM North America | 297894 | Gas Turbine | 151336 | Borescope Inspection (BI) | 532562 | 2026-10-13 | 2026-10-16
7FA.04 | NAM North America | 297895 | Gas Turbine | 151337 | Borescope Inspection (BI) | 532563 | 2026-10-17 | 2026-10-20
7FA.04 | NAM North America | 297896 | Gas Turbine | 151338 | Borescope Inspection (BI) | 532564 | 2026-10-05 | 2026-10-13
7FA.04 | NAM North America | 298123 | Gas Turbine | 152547 | Borescope Inspection (BI) | 533527 | 2026-04-10 | 2026-04-21
7FA.04 | NAM North America | 298123 | Gas Turbine | 152549 | Borescope Inspection (BI) | 533529 | 2026-11-08 | 2026-11-19
7FA.04 | NAM North America | 298123 | Gas Turbine | 152550 | Borescope Inspection (BI) | 533530 | 2026-11-09 | 2026-11-20
7FA.04 | NAM North America | 299201 | Gas Turbine | 154060 | Hot Gas Path Inspection (HGPI) | 538278 | 2026-10-03 | 2026-10-19
7FA.04 | NAM North America | 299202 | Gas Turbine | 154061 | Hot Gas Path Inspection (HGPI) | 538279 | 2027-04-16 | 2027-04-30
7FA.04 | NAM North America | 298087 | Gas Turbine | 154288 | Major Inspection (MI) | 534714 | 2026-03-16 | 2026-05-07
7FA.04 | NAM North America | 298120 | Gas Turbine | 154562 | Large Call-Out | 534923 | 2026-03-27 | 2026-04-09
7FA.04 | NAM North America | 298120 | Gas Turbine | 154563 | Borescope Inspection (BI) | 561385 | 2026-11-02 | 2026-11-18
7FA.04 | NAM North America | 298120 | Gas Turbine | 154564 | Borescope Inspection (BI) | 534924 | 2027-03-27 | 2027-04-09
7FA.04 | NAM North America | 298120 | Gas Turbine | 154566 | Borescope Inspection (BI) | 534925 | 2027-11-02 | 2027-11-18
7FA.04 | NAM North America | 298178 | Gas Turbine | 154614 | Borescope Inspection (BI) | 534946 | 2026-04-04 | 2026-04-12
7FA.04 | NAM North America | 298177 | Gas Turbine | 154615 | Borescope Inspection (BI) | 534947 | 2026-04-04 | 2026-04-12
7FA.04 | NAM North America | 298235 | Gas Turbine | 154616 | Borescope Inspection (BI) | 534948 | 2026-04-09 | 2026-04-17
7FA.04 | NAM North America | 298236 | Gas Turbine | 154617 | Borescope Inspection (BI) | 534949 | 2026-04-09 | 2026-04-17
7FA.04 | NAM North America | 298177 | Gas Turbine | 154618 | Borescope Inspection (BI) | 534950 | 2027-04-01 | 2027-04-09
7FA.04 | NAM North America | 298178 | Gas Turbine | 154619 | Borescope Inspection (BI) | 534951 | 2027-04-01 | 2027-04-09
7FA.04 | NAM North America | 298235 | Gas Turbine | 154620 | Borescope Inspection (BI) | 534952 | 2027-04-07 | 2027-04-15
7FA.04 | NAM North America | 298236 | Gas Turbine | 154621 | Borescope Inspection (BI) | 534953 | 2027-04-07 | 2027-04-15
7FA.04 | NAM North America | 297513 | Gas Turbine | 154660 | Borescope Inspection (BI) | 534990 | 2026-03-28 | 2026-03-31
7FA.04 | NAM North America | 297513 | Gas Turbine | 154663 | Borescope Inspection (BI) | 534993 | 2026-11-16 | 2026-11-19
7FA.04 | NAM North America | 298312 | Gas Turbine | 154819 | Major Inspection (MI) | 535061 | 2026-02-23 | 2026-04-27
7FA.04 | NAM North America | 298313 | Gas Turbine | 154821 | Major Inspection (MI) | 535062 | 2026-02-19 | 2026-04-27
7FA.04 | NAM North America | 297897 | Gas Turbine | 155186 | Borescope Inspection (BI) | 535348 | 2026-03-02 | 2026-03-05
7FA.04 | NAM North America | 297897 | Gas Turbine | 155187 | Borescope Inspection (BI) | 535349 | 2026-10-20 | 2026-10-22
7FA.04 | NAM North America | 297898 | Gas Turbine | 155188 | Borescope Inspection (BI) | 535350 | 2026-03-10 | 2026-03-12
7FA.04 | NAM North America | 297898 | Gas Turbine | 155189 | Borescope Inspection (BI) | 535351 | 2026-10-13 | 2026-10-15
7FA.04 | NAM North America | 297899 | Gas Turbine | 155190 | Borescope Inspection (BI) | 535352 | 2026-03-07 | 2026-03-10
7FA.04 | NAM North America | 297899 | Gas Turbine | 155191 | Borescope Inspection (BI) | 535353 | 2026-10-12 | 2026-10-14
7FA.04 | NAM North America | 297875 | Gas Turbine | 155193 | Borescope Inspection (BI) | 535356 | 2026-03-29 | 2026-04-01
7FA.04 | NAM North America | 297875 | Gas Turbine | 155194 | Borescope Inspection (BI) | 535357 | 2026-10-05 | 2026-10-07
7FA.04 | NAM North America | 297876 | Gas Turbine | 155195 | Borescope Inspection (BI) | 535358 | 2026-03-16 | 2026-03-19
7FA.04 | NAM North America | 297876 | Gas Turbine | 155197 | Borescope Inspection (BI) | 535360 | 2026-10-05 | 2026-10-07
7FA.04 | NAM North America | 297877 | Gas Turbine | 155198 | Borescope Inspection (BI) | 535361 | 2026-04-01 | 2026-04-03
7FA.04 | NAM North America | 297877 | Gas Turbine | 155199 | Borescope Inspection (BI) | 535362 | 2026-10-12 | 2026-10-14
7FA.04 | NAM North America | 298973 | Gas Turbine | 155206 | Borescope Inspection (BI) | 535369 | 2026-04-01 | 2026-04-04
7FA.04 | NAM North America | 298973 | Gas Turbine | 155207 | Borescope Inspection (BI) | 535370 | 2026-11-13 | 2026-11-17
7FA.04 | NAM North America | 298974 | Gas Turbine | 155208 | Borescope Inspection (BI) | 535371 | 2026-04-13 | 2026-04-16
7FA.04 | NAM North America | 298974 | Gas Turbine | 155209 | Borescope Inspection (BI) | 535372 | 2026-11-11 | 2026-11-16
7FA.04 | NAM North America | 298975 | Gas Turbine | 155210 | Borescope Inspection (BI) | 535373 | 2026-05-07 | 2026-05-10
7FA.04 | NAM North America | 298975 | Gas Turbine | 155211 | Borescope Inspection (BI) | 535374 | 2026-10-19 | 2026-10-22
7FA.04 | Asia | 298618 | Gas Turbine | 158562 | Major Inspection (MI) |  | 2030-10-01 | 2030-10-29
7FA.04 | NAM North America | 297613 | Gas Turbine | 158596 | Hot Gas Path Inspection (HGPI) | 548284 | 2029-03-12 | 2029-03-28
7FA.04 | Asia | 297954 | Gas Turbine | 158626 | Major Inspection (MI) | 538018 | 2028-01-23 | 2028-02-25
7FA.04 | Latin America | 297476 | Gas Turbine | 158636 | Hot Gas Path Inspection (HGPI) | 537959 | 2030-10-01 | 2030-10-15
7FA.04 | NAM North America | 298015 | Gas Turbine | 158694 | Borescope Inspection (BI) | 537998 | 2026-04-19 | 2026-04-28
7FA.04 | NAM North America | 297258 | Gas Turbine | 158764 | Borescope Inspection (BI) | 538036 | 2026-03-20 | 2026-03-28
7FA.04 | NAM North America | 297490 | Gas Turbine | 158765 | Borescope Inspection (BI) | 538037 | 2026-04-13 | 2026-04-29
7FA.04 | NAM North America | 297492 | Gas Turbine | 158766 | Borescope Inspection (BI) | 538038 | 2026-04-20 | 2026-05-04
7FA.04 | MENA | 299332 | Gas Turbine | 158899 | Hot Gas Path Inspection (HGPI) | 538109 | 2028-09-05 | 2028-09-19
7FA.04 | MENA | 299331 | Gas Turbine | 158901 | Hot Gas Path Inspection (HGPI) | 538110 | 2028-11-02 | 2028-11-16
7FA.04 | MENA | 299333 | Gas Turbine | 158903 | Hot Gas Path Inspection (HGPI) | 538111 | 2029-05-17 | 2029-05-31
7FA.04 | MENA | 299334 | Gas Turbine | 158905 | Hot Gas Path Inspection (HGPI) | 538112 | 2029-08-19 | 2029-09-02
7FA.04 | MENA | 299014 | Gas Turbine | 158907 | Major Inspection (MI) | 545696 | 2028-04-01 | 2028-04-26
7FA.04 | MENA | 299015 | Gas Turbine | 158908 | Major Inspection (MI) | 545695 | 2028-10-01 | 2028-10-29
7FA.04 | MENA | 299019 | Gas Turbine | 158909 | Major Inspection (MI) | 545697 | 2028-10-01 | 2028-10-29
7FA.04 | MENA | 299020 | Gas Turbine | 158910 | Major Inspection (MI) | 545698 | 2028-12-25 | 2029-01-22
7FA.04 | MENA | 299018 | Gas Turbine | 158912 | Major Inspection (MI) | 538114 | 2029-03-30 | 2029-04-27
7FA.04 | NAM North America | 297756 | Gas Turbine | 159053 | Major Inspection (MI) | 550224 | 2030-09-08 | 2030-10-06
7FA.04 | NAM North America | 297757 | Gas Turbine | 159055 | Major Inspection (MI) | 548240 | 2030-09-08 | 2030-10-06
7FA.04 | NAM North America | 297457 | Gas Turbine | 159152 | Major Inspection (MI) |  | 2030-06-24 | 2030-07-22
7FA.04 | NAM North America | 298236 | Gas Turbine | 159171 | Hot Gas Path Inspection (HGPI) | 538255 | 2028-10-09 | 2028-10-23
7FA.04 | NAM North America | 298235 | Gas Turbine | 159174 | Hot Gas Path Inspection (HGPI) | 538256 | 2028-10-15 | 2028-10-29
7FA.04 | NAM North America | 298003 | Gas Turbine | 159190 | Major Inspection (MI) | 538266 | 2028-10-17 | 2028-11-14
7FA.04 | NAM North America | 298002 | Gas Turbine | 159191 | Major Inspection (MI) | 538267 | 2029-04-30 | 2029-05-28
7FA.04 | NAM North America | 297398 | Gas Turbine | 159196 | Hot Gas Path Inspection (HGPI) | 538271 | 2029-11-24 | 2029-12-08
7FA.04 | NAM North America | 297399 | Gas Turbine | 159198 | Hot Gas Path Inspection (HGPI) | 538272 | 2029-11-24 | 2029-12-08
7FA.04 | NAM North America | 298935 | Gas Turbine | 159646 | Borescope Inspection (BI) | 538632 | 2026-03-09 | 2026-03-13
7FA.04 | NAM North America | 298936 | Gas Turbine | 159647 | Borescope Inspection (BI) | 538633 | 2026-09-28 | 2026-10-02
7FA.04 | Asia | 298679 | Gas Turbine | 160106 | Borescope Inspection (BI) | 538818 | 2026-04-07 | 2026-04-08
7FA.04 | Asia | 298680 | Gas Turbine | 160107 | Borescope Inspection (BI) | 538819 | 2026-04-07 | 2026-04-08
7FA.04 | Asia | 297953 | Gas Turbine | 160488 | Borescope Inspection (BI) | 539157 | 2026-02-15 | 2026-02-23
7FA.04 | Asia | 297954 | Gas Turbine | 160489 | Borescope Inspection (BI) | 539158 | 2026-02-15 | 2026-02-23
7FA.04 | Asia | 297955 | Gas Turbine | 160490 | Borescope Inspection (BI) | 539159 | 2026-02-15 | 2026-02-23
7FA.04 | NAM North America | 298158 | Gas Turbine | 160852 | Borescope Inspection (BI) | 539433 | 2026-04-18 | 2026-04-26
7FA.04 | NAM North America | 298159 | Gas Turbine | 161391 | Borescope Inspection (BI) | 539903 | 2026-04-18 | 2026-04-26
7FA.04 | NAM North America | 298112 | Gas Turbine | 161553 | Borescope Inspection (BI) | 540072 | 2026-04-24 | 2026-05-03
7FA.04 | NAM North America | 298113 | Gas Turbine | 161554 | Borescope Inspection (BI) | 540074 | 2026-04-24 | 2026-05-03
7FA.04 | NAM North America | 298127 | Gas Turbine | 161557 | Borescope Inspection (BI) | 540075 | 2026-04-24 | 2026-05-03
7FA.04 | NAM North America | 298128 | Gas Turbine | 161559 | Borescope Inspection (BI) | 540077 | 2026-04-24 | 2026-05-03
7FA.04 | NAM North America | 297938 | Gas Turbine | 162116 | Major Inspection (MI) | 548425 | 2027-05-01 | 2027-06-04
7FA.04 | NAM North America | 297936 | Gas Turbine | 162117 | Major Inspection (MI) | 548428 | 2027-05-01 | 2027-06-04
7FA.04 | Asia | 299022 | Gas Turbine | 162153 | Hot Gas Path Inspection (HGPI) | 540556 | 2027-10-01 | 2027-10-17
7FA.04 | Asia | 299023 | Gas Turbine | 162156 | Hot Gas Path Inspection (HGPI) | 540557 | 2027-10-01 | 2027-10-17
7FA.04 | Asia | 299024 | Gas Turbine | 162158 | Hot Gas Path Inspection (HGPI) | 540558 | 2028-10-01 | 2028-10-17
7FA.04 | Asia | 299022 | Gas Turbine | 162159 | Combustion Inspection (CI) |  | 2030-10-16 | 2030-10-23
7FA.04 | Latin America | 298077 | Gas Turbine | 162653 | Hot Gas Path Inspection (HGPI) | 540936 | 2028-02-15 | 2028-03-05
7FA.04 | Latin America | 299124 | Gas Turbine | 162712 | Major Inspection (MI) | 540981 | 2028-03-04 | 2028-04-04
7FA.04 | NAM North America | 298006 | Gas Turbine | 163012 | Hot Gas Path Inspection (HGPI) | 541163 | 2028-05-23 | 2028-06-17
7FA.04 | NAM North America | 298304 | Gas Turbine | 163030 | Major Inspection (MI) | 541169 | 2026-09-28 | 2026-11-16
7FA.04 | NAM North America | 298305 | Gas Turbine | 163031 | Major Inspection (MI) | 541170 | 2027-03-04 | 2027-04-28
7FA.04 | NAM North America | 298306 | Gas Turbine | 163032 | Major Inspection (MI) | 541171 | 2026-10-02 | 2026-11-20
7FA.04 | NAM North America | 298645 | Gas Turbine | 163059 | Hot Gas Path Inspection (HGPI) | 541182 | 2030-04-12 | 2030-05-02
7FA.04 | NAM North America | 297490 | Gas Turbine | 163147 | Major Inspection (MI) | 541256 | 2028-10-01 | 2028-11-01
7FA.04 | NAM North America | 297491 | Gas Turbine | 163149 | Major Inspection (MI) | 541257 | 2028-10-01 | 2028-11-01
7FA.04 | NAM North America | 297492 | Gas Turbine | 163153 | Major Inspection (MI) | 541258 | 2029-10-01 | 2029-11-01
7FA.04 | NAM North America | 297257 | Gas Turbine | 163186 | Hot Gas Path Inspection (HGPI) | 541293 | 2029-03-17 | 2029-03-31
7FA.04 | NAM North America | 297258 | Gas Turbine | 163190 | Hot Gas Path Inspection (HGPI) | 541294 | 2029-03-17 | 2029-03-31
7FA.04 | NAM North America | 298020 | Gas Turbine | 163192 | Major Inspection (MI) | 541297 | 2030-04-01 | 2030-05-01
7FA.04 | NAM North America | 298019 | Gas Turbine | 163193 | Major Inspection (MI) | 541296 | 2030-04-01 | 2030-05-01
7FA.04 | NAM North America | 298018 | Gas Turbine | 163194 | Major Inspection (MI) | 541295 | 2030-04-01 | 2030-05-01
7FA.04 | NAM North America | 297096 | Gas Turbine | 164657 | Hot Gas Path Inspection (HGPI) | 542489 | 2030-04-01 | 2030-04-22
7FA.04 | NAM North America | 298125 | Gas Turbine | 165046 | Major Inspection (MI) | 542785 | 2028-03-01 | 2028-03-29
7FA.04 | NAM North America | 297627 | Gas Turbine | 165062 | Major Inspection (MI) | 542796 | 2029-03-01 | 2029-03-29
7FA.04 | NAM North America | 297628 | Gas Turbine | 165066 | Major Inspection (MI) | 542797 | 2029-03-01 | 2029-03-29
7FA.04 | Latin America | 297963 | Gas Turbine | 165070 | Major Inspection (MI) | 542800 | 2029-10-01 | 2029-10-31
7FA.04 | Latin America | 297964 | Gas Turbine | 165073 | Major Inspection (MI) | 542801 | 2029-10-01 | 2029-10-31
7FA.04 | Latin America | 298527 | Gas Turbine | 165078 | Combustion Inspection (CI) |  | 2028-08-12 | 2028-08-19
7FA.04 | Latin America | 298528 | Gas Turbine | 165079 | Combustion Inspection (CI) |  | 2028-08-13 | 2028-08-20
7FA.04 | Latin America | 298512 | Gas Turbine | 165082 | Major Inspection (MI) | 542803 | 2029-08-12 | 2029-09-09
7FA.04 | Latin America | 298527 | Gas Turbine | 165084 | Major Inspection (MI) | 542804 | 2029-09-17 | 2029-10-15
7FA.04 | Latin America | 298528 | Gas Turbine | 165088 | Major Inspection (MI) | 542805 | 2029-09-17 | 2029-10-15
7FA.04 | Latin America | 298513 | Gas Turbine | 165091 | Major Inspection (MI) | 542806 | 2029-08-12 | 2029-09-09
7FA.04 | Latin America | 298479 | Gas Turbine | 165096 | Major Inspection (MI) | 542810 | 2030-11-03 | 2030-12-01
7FA.04 | Latin America | 298480 | Gas Turbine | 165097 | Major Inspection (MI) | 542809 | 2030-11-03 | 2030-12-01
7FA.04 | NAM North America | 298289 | Gas Turbine | 165129 | Hot Gas Path Inspection (HGPI) | 542825 | 2029-02-01 | 2029-02-15
7FA.04 | NAM North America | 298288 | Gas Turbine | 165130 | Hot Gas Path Inspection (HGPI) | 542826 | 2029-10-09 | 2029-10-23
7FA.04 | NAM North America | 298111 | Gas Turbine | 165140 | Major Inspection (MI) | 542829 | 2028-04-23 | 2028-05-21
7FA.04 | NAM North America | 298110 | Gas Turbine | 165141 | Major Inspection (MI) | 542828 | 2028-04-23 | 2028-05-21
7FA.04 | NAM North America | 297664 | Gas Turbine | 165146 | Hot Gas Path Inspection (HGPI) | 542831 | 2030-03-15 | 2030-03-29
7FA.04 | NAM North America | 299021 | Gas Turbine | 165158 | Major Inspection (MI) | 542838 | 2029-04-20 | 2029-06-04
7FA.04 | NAM North America | 298357 | Gas Turbine | 165182 | Hot Gas Path Inspection (HGPI) | 542851 | 2030-09-01 | 2030-09-15
7FA.04 | NAM North America | 298358 | Gas Turbine | 165184 | Hot Gas Path Inspection (HGPI) | 542852 | 2030-10-01 | 2030-10-15
7FA.04 | NAM North America | 297543 | Gas Turbine | 165195 | Hot Gas Path Inspection (HGPI) |  | 2030-10-01 | 2030-10-15
7FA.04 | NAM North America | 298122 | Gas Turbine | 165222 | Major Inspection (MI) | 542862 | 2030-10-01 | 2030-10-29
7FA.04 | NAM North America | 298123 | Gas Turbine | 165225 | Major Inspection (MI) | 542861 | 2030-10-01 | 2030-10-29
7FA.04 | NAM North America | 297482 | Gas Turbine | 165256 | Hot Gas Path Inspection (HGPI) | 542879 | 2029-05-01 | 2029-05-15
7FA.04 | NAM North America | 297483 | Gas Turbine | 165259 | Hot Gas Path Inspection (HGPI) | 542880 | 2029-09-06 | 2029-09-20
7FA.04 | NAM North America | 298392 | Gas Turbine | 165263 | Hot Gas Path Inspection (HGPI) | 542882 | 2030-12-29 | 2031-01-12
7FA.04 | NAM North America | 297782 | Gas Turbine | 165275 | Major Inspection (MI) | 542889 | 2028-05-10 | 2028-06-08
7FA.04 | NAM North America | 297781 | Gas Turbine | 165277 | Major Inspection (MI) | 542890 | 2028-11-05 | 2028-12-03
7FA.04 | NAM North America | 297546 | Gas Turbine | 165352 | Large Call-Out | 542921 | 2026-04-21 | 2026-05-10
7FA.04 | NAM North America | 298120 | Gas Turbine | 168031 | Hot Gas Path Inspection (HGPI) | 544940 | 2028-10-02 | 2028-10-15
7FA.04 | NAM North America | 298121 | Gas Turbine | 168033 | Hot Gas Path Inspection (HGPI) | 544941 | 2028-10-02 | 2028-10-15
7FA.04 | NAM North America | 297543 | Gas Turbine | 169150 | Stand Alone Large Upgrade | 545869 | 2026-04-11 | 2026-05-10
7FA.04 | MENA | 299426 | Gas Turbine | 169807 | Major Inspection (MI) | 546214 | 2027-01-05 | 2027-02-03
7FA.04 | NAM North America | 297894 | Gas Turbine | 170898 | Stand Alone Large Upgrade | 546832 | 2027-03-15 | 2027-05-23
7FA.04 | NAM North America | 297895 | Gas Turbine | 170900 | Stand Alone Large Upgrade | 546833 | 2027-03-22 | 2027-05-30
7FA.04 | NAM North America | 297894 | Gas Turbine | 171266 | Major Inspection (MI) | 547091 | 2030-01-01 | 2030-03-01
7FA.04 | NAM North America | 297714 | Gas Turbine | 173082 | Major Inspection (MI) | 548097 | 2030-07-22 | 2030-08-19
7FA.04 | NAM North America | 298159 | Gas Turbine | 173276 | Stand Alone Small Upgrade | 548213 | 2026-09-01 | 2027-02-16
7FA.04 | NAM North America | 298127 | Gas Turbine | 173279 | Stand Alone Small Upgrade | 548214 | 2027-02-01 | 2027-07-19
7FA.04 | NAM North America | 297623 | Gas Turbine | 173280 | Stand Alone Small Upgrade | 548215 | 2027-02-01 | 2027-07-19
7FA.04 | NAM North America | 297624 | Gas Turbine | 173281 | Stand Alone Small Upgrade | 548217 | 2026-02-01 | 2026-07-20
7FA.04 | NAM North America | 297908 | Gas Turbine | 173353 | Hot Gas Path Inspection (HGPI) | 559744 | 2028-09-01 | 2028-09-15
7FA.04 | NAM North America | 297909 | Gas Turbine | 173354 | Hot Gas Path Inspection (HGPI) | 559901 | 2028-09-01 | 2028-09-15
7FA.04 | NAM North America | 297785 | Gas Turbine | 173561 | Major Inspection (MI) | 548353 | 2030-03-02 | 2030-03-20
7FA.04 | Asia | 298679 | Gas Turbine | 173783 | Major Inspection (MI) | 548514 | 2027-04-30 | 2027-06-01
7FA.04 | NAM North America | 298342 | Gas Turbine | 175430 | Major Inspection (MI) | 549599 | 2028-10-06 | 2028-11-09
7FA.04 | NAM North America | 297518 | Gas Turbine | 175868 | Major Inspection (MI) | 549912 | 2030-02-16 | 2030-05-16
7FA.04 | NAM North America | 297517 | Gas Turbine | 175869 | Major Inspection (MI) | 549911 | 2030-02-16 | 2030-05-16
7FA.04 | NAM North America | 297493 | Gas Turbine | 176106 | Major Inspection (MI) | 550050 | 2029-10-01 | 2029-11-01
7FA.04 | NAM North America | 298613 | Gas Turbine | 176382 | Major Inspection (MI) |  | 2030-07-09 | 2030-08-06
7FA.04 | NAM North America | 298614 | Gas Turbine | 176385 | Major Inspection (MI) | 550223 | 2030-07-09 | 2030-08-06
7FA.04 | NAM North America | 297651 | Gas Turbine | 177260 | Major Inspection (MI) | 550861 | 2028-03-26 | 2028-04-23
7FA.04 | NAM North America | 297652 | Gas Turbine | 177261 | Major Inspection (MI) | 550860 | 2028-03-26 | 2028-04-23
7FA.04 | NAM North America | 297929 | Gas Turbine | 177278 | Major Inspection (MI) | 550867 | 2030-10-26 | 2030-11-23
7FA.04 | NAM North America | 298936 | Gas Turbine | 177350 | Hot Gas Path Inspection (HGPI) | 550875 | 2028-03-11 | 2028-04-01
7FA.04 | NAM North America | 298935 | Gas Turbine | 177352 | Hot Gas Path Inspection (HGPI) | 550876 | 2028-09-16 | 2028-10-07
7FA.04 | NAM North America | 298298 | Gas Turbine | 177360 | Major Inspection (MI) | 550879 | 2029-03-28 | 2029-04-25
7FA.04 | NAM North America | 297519 | Gas Turbine | 177371 | Major Inspection (MI) | 550883 | 2028-09-16 | 2028-10-14
7FA.04 | NAM North America | 297520 | Gas Turbine | 177374 | Major Inspection (MI) | 550884 | 2028-09-16 | 2028-10-14
7FA.04 | NAM North America | 297927 | Gas Turbine | 177380 | Major Inspection (MI) | 550888 | 2027-09-01 | 2027-09-28
7FA.04 | NAM North America | 297928 | Gas Turbine | 177381 | Major Inspection (MI) | 550887 | 2027-09-01 | 2027-09-28
7FA.04 | NAM North America | 296301 | Gas Turbine | 177392 | Hot Gas Path Inspection (HGPI) | 554989 | 2029-10-13 | 2029-10-31
7FA.04 | NAM North America | 296302 | Gas Turbine | 177393 | Major Inspection (MI) | 555007 | 2029-10-13 | 2030-05-25
7FA.04 | NAM North America | 296300 | Gas Turbine | 177394 | Hot Gas Path Inspection (HGPI) | 554985 | 2030-10-05 | 2030-10-26
7FA.04 | NAM North America | 296303 | Gas Turbine | 177395 | Major Inspection (MI) | 554988 | 2030-10-05 | 2030-11-02
7FA.04 | NAM North America | 298159 | Gas Turbine | 177396 | Hot Gas Path Inspection (HGPI) | 550894 | 2029-04-07 | 2029-04-25
7FA.04 | NAM North America | 298158 | Gas Turbine | 177399 | Hot Gas Path Inspection (HGPI) | 550893 | 2029-04-07 | 2029-04-25
7FA.04 | NAM North America | 297623 | Gas Turbine | 177401 | Hot Gas Path Inspection (HGPI) | 550895 | 2030-04-13 | 2030-05-01
7FA.04 | NAM North America | 297624 | Gas Turbine | 177402 | Hot Gas Path Inspection (HGPI) | 550896 | 2030-04-13 | 2030-05-01
7FA.04 | NAM North America | 297345 | Gas Turbine | 177413 | Hot Gas Path Inspection (HGPI) | 550897 | 2028-10-01 | 2028-10-15
7FA.04 | NAM North America | 297346 | Gas Turbine | 177414 | Hot Gas Path Inspection (HGPI) | 550898 | 2028-10-01 | 2028-10-15
7FA.04 | NAM North America | 297153 | Gas Turbine | 177416 | Hot Gas Path Inspection (HGPI) | 550899 | 2028-11-23 | 2028-12-07
7FA.04 | NAM North America | 297154 | Gas Turbine | 177419 | Hot Gas Path Inspection (HGPI) | 550900 | 2028-11-23 | 2028-12-07
7FA.04 | Latin America | 299124 | Gas Turbine | 178583 | Stand Alone Small Upgrade | 551972 | 2026-10-01 | 2026-10-05
7FA.04 | NAM North America | 297939 | Gas Turbine | 178885 | Major Inspection (MI) | 551709 | 2029-11-01 | 2029-11-29
7FA.04 | NAM North America | 297940 | Gas Turbine | 178886 | Major Inspection (MI) | 551710 | 2030-02-01 | 2030-03-01
7FA.04 | Asia | 298920 | Gas Turbine | 179256 | Major Inspection (MI) | 551875 | 2029-04-15 | 2029-06-30
7FA.04 | Asia | 298996 | Gas Turbine | 179257 | Major Inspection (MI) | 551876 | 2029-04-15 | 2029-06-30
7FA.04 | Asia | 298922 | Gas Turbine | 179258 | Major Inspection (MI) | 551877 | 2030-04-15 | 2030-06-30
7FA.04 | Asia | 298923 | Gas Turbine | 179260 | Major Inspection (MI) | 551878 | 2030-04-15 | 2030-06-30
7FA.04 | Asia | 298918 | Gas Turbine | 179661 | Hot Gas Path Inspection (HGPI) | 552133 | 2028-04-29 | 2028-07-19
7FA.04 | Asia | 298919 | Gas Turbine | 179662 | Hot Gas Path Inspection (HGPI) | 552134 | 2028-04-29 | 2028-07-19
7FA.04 | NAM North America | 298110 | Gas Turbine | 181372 | Major Inspection (MI) | 553023 | 2028-03-16 | 2028-05-31
7FA.04 | NAM North America | 298111 | Gas Turbine | 181373 | Major Inspection (MI) | 553024 | 2028-03-16 | 2028-05-31
7FA.04 | NAM North America | 297583 | Gas Turbine | 182312 | Hot Gas Path Inspection (HGPI) |  | 2030-05-31 | 2030-06-14
7FA.04 | NAM North America | 297836 | Gas Turbine | 182470 | Major Inspection (MI) | 553754 | 2029-04-30 | 2029-05-28
7FA.04 | NAM North America | 297837 | Gas Turbine | 182471 | Major Inspection (MI) | 553753 | 2029-04-30 | 2029-05-28
7FA.04 | NAM North America | 298276 | Gas Turbine | 182479 | Major Inspection (MI) | 553757 | 2028-09-05 | 2028-10-02
7FA.04 | NAM North America | 297720 | Gas Turbine | 183674 | Hot Gas Path Inspection (HGPI) | 554520 | 2026-10-03 | 2026-11-03
7FA.04 | NAM North America | 297721 | Gas Turbine | 183676 | Hot Gas Path Inspection (HGPI) | 554521 | 2026-10-03 | 2026-11-03
7FA.04 | NAM North America | 298289 | Gas Turbine | 183770 | Stand Alone Large Upgrade | 554576 | 2030-04-01 | 2030-05-31
7FA.04 | NAM North America | 298288 | Gas Turbine | 183771 | Stand Alone Large Upgrade | 554577 | 2030-09-01 | 2030-10-31
7FA.04 | Latin America | 299391 | Gas Turbine | 184054 | Hot Gas Path Inspection (HGPI) | 559806 | 2028-10-02 | 2028-10-16
7FA.04 | NAM North America | 297665 | Gas Turbine | 184101 | Large Call-Out | 554834 | 2028-05-01 | 2028-05-24
7FA.04 | NAM North America | 298314 | Gas Turbine | 184778 | Major Inspection (MI) | 555278 | 2029-09-18 | 2029-10-17
7FA.04 | NAM North America | 298313 | Gas Turbine | 184781 | Major Inspection (MI) | 555279 | 2030-02-19 | 2030-03-20
7FA.04 | NAM North America | 298312 | Gas Turbine | 184852 | Major Inspection (MI) | 555322 | 2030-02-19 | 2030-03-20
7FA.04 | NAM North America | 297660 | Gas Turbine | 185346 | Hot Gas Path Inspection (HGPI) | 555655 | 2028-10-16 | 2028-11-01
7FA.04 | NAM North America | 297661 | Gas Turbine | 185349 | Hot Gas Path Inspection (HGPI) | 555658 | 2027-10-07 | 2027-11-07
7FA.04 | NAM North America | 297628 | Gas Turbine | 185793 | Large Call-Out | 556008 | 2026-03-10 | 2026-04-13
7FA.04 | NAM North America | 297784 | Gas Turbine | 185878 | Major Inspection (MI) | 556048 | 2029-03-03 | 2029-03-21
7FA.04 | Asia | 298679 | Gas Turbine | 186468 | Major Inspection (MI) |  | 2028-12-02 | 2028-12-30
7FA.04 | Asia | 298680 | Gas Turbine | 186469 | Hot Gas Path Inspection (HGPI) | 556739 | 2030-04-01 | 2030-04-25
7FA.04 | NAM North America | 298568 | Gas Turbine | 186998 | Stand Alone Large Upgrade | 556798 | 2027-10-17 | 2027-12-30
7FA.04 | NAM North America | 298569 | Gas Turbine | 187063 | Stand Alone Large Upgrade | 556829 | 2027-10-31 | 2028-01-13
7FA.04 | NAM North America | 298357 | Gas Turbine | 187068 | Stand Alone Large Upgrade | 556835 | 2028-02-05 | 2028-04-17
7FA.04 | NAM North America | 298358 | Gas Turbine | 187069 | Stand Alone Large Upgrade | 556837 | 2028-03-18 | 2028-05-29
7FA.04 | Latin America | 299276 | Gas Turbine | 187634 | Hot Gas Path Inspection (HGPI) |  | 2027-04-29 | 2027-05-13
7FA.04 | NAM North America | 298788 | Gas Turbine | 187650 | Hot Gas Path Inspection (HGPI) | 557284 | 2030-12-20 | 2031-01-03
7FA.04 | NAM North America | 297757 | Gas Turbine | 187681 | Hot Gas Path Inspection (HGPI) | 557296 | 2026-03-28 | 2026-04-11
7FA.04 | NAM North America | 297756 | Gas Turbine | 187682 | Hot Gas Path Inspection (HGPI) | 557295 | 2026-03-28 | 2026-04-11
7FA.04 | NAM North America | 297759 | Gas Turbine | 187685 | Hot Gas Path Inspection (HGPI) | 557297 | 2026-10-23 | 2026-11-06
7FA.04 | NAM North America | 297758 | Gas Turbine | 187686 | Hot Gas Path Inspection (HGPI) | 557298 | 2026-10-23 | 2026-11-06
7FA.04 | NAM North America | 297898 | Gas Turbine | 187699 | Major Inspection (MI) | 557299 | 2027-04-01 | 2027-05-15
7FA.04 | NAM North America | 297899 | Gas Turbine | 187700 | Major Inspection (MI) | 557300 | 2027-10-01 | 2027-10-29
7FA.04 | NAM North America | 297877 | Gas Turbine | 187704 | Major Inspection (MI) | 557301 | 2028-10-01 | 2028-10-29
7FA.04 | NAM North America | 297722 | Gas Turbine | 187713 | Major Inspection (MI) |  | 2026-10-01 | 2026-10-29
7FA.04 | NAM North America | 297760 | Gas Turbine | 187717 | Hot Gas Path Inspection (HGPI) | 557306 | 2030-08-01 | 2030-08-15
7FA.04 | NAM North America | 298392 | Gas Turbine | 187718 | Major Inspection (MI) | 557307 | 2026-07-30 | 2026-08-27
7FA.04 | NAM North America | 297483 | Gas Turbine | 187721 | Hot Gas Path Inspection (HGPI) |  | 2029-07-07 | 2029-07-21
7FA.04 | NAM North America | 297628 | Gas Turbine | 187744 | Major Inspection (MI) |  | 2029-03-15 | 2029-04-12
7FA.04 | NAM North America | 297627 | Gas Turbine | 187745 | Major Inspection (MI) |  | 2029-03-15 | 2029-04-12
7FA.04 | NAM North America | 297096 | Gas Turbine | 187773 | Major Inspection (MI) |  | 2026-05-07 | 2026-06-04
7FA.04 | NAM North America | 299480 | Gas Turbine | 187774 | Hot Gas Path Inspection (HGPI) |  | 2026-10-21 | 2026-11-04
7FA.04 | NAM North America | 297457 | Gas Turbine | 187775 | Major Inspection (MI) |  | 2029-12-10 | 2030-01-07
7FA.04 | NAM North America | 297096 | Gas Turbine | 187776 | Hot Gas Path Inspection (HGPI) |  | 2030-09-01 | 2030-09-15
7FA.04 | NAM North America | 298569 | Gas Turbine | 187781 | Major Inspection (MI) |  | 2027-02-24 | 2027-03-24
7FA.04 | NAM North America | 297665 | Gas Turbine | 187785 | Hot Gas Path Inspection (HGPI) |  | 2026-10-01 | 2026-10-15
7FA.04 | NAM North America | 297664 | Gas Turbine | 187786 | Hot Gas Path Inspection (HGPI) |  | 2030-03-01 | 2030-03-15
7FA.04 | NAM North America | 299201 | Gas Turbine | 187823 | Hot Gas Path Inspection (HGPI) |  | 2027-03-19 | 2027-04-02
7FA.04 | NAM North America | 297893 | Gas Turbine | 187837 | Major Inspection (MI) | 557329 | 2026-09-26 | 2026-10-24
7FA.04 | NAM North America | 297896 | Gas Turbine | 187838 | Major Inspection (MI) | 557330 | 2026-09-26 | 2026-10-24
7FA.04 | NAM North America | 297894 | Gas Turbine | 187841 | Major Inspection (MI) | 557331 | 2027-04-01 | 2027-04-29
7FA.04 | NAM North America | 297895 | Gas Turbine | 187842 | Major Inspection (MI) | 557332 | 2027-04-01 | 2027-04-29
7FA.04 | NAM North America | 298110 | Gas Turbine | 187856 | Major Inspection (MI) |  | 2028-04-26 | 2028-05-24
7FA.04 | Latin America | 299099 | Gas Turbine | 188659 | Stand Alone Small Upgrade | 558638 | 2026-02-02 | 2026-02-10
7FA.04 | NAM North America | 297720 | Gas Turbine | 188758 | Major Inspection (MI) | 558245 | 2030-03-01 | 2030-05-31
7FA.04 | NAM North America | 297721 | Gas Turbine | 188760 | Major Inspection (MI) | 558247 | 2030-03-01 | 2030-05-31
7FA.04 | NAM North America | 297183 | Gas Turbine | 189760 | Hot Gas Path Inspection (HGPI) | 558637 | 2028-03-06 | 2028-04-22
7FA.04 | Latin America | 299182 | Gas Turbine | 189993 | Stand Alone Small Upgrade | 558825 | 2027-02-05 | 2027-02-24
7FA.04 | Latin America | 299098 | Gas Turbine | 190257 | Stand Alone Small Upgrade | 559661 | 2026-02-02 | 2026-02-10
7FA.04 | NAM North America | 297184 | Gas Turbine | 190954 | Hot Gas Path Inspection (HGPI) | 559544 | 2029-03-05 | 2029-04-23
7FA.04 | NAM North America | 297545 | Gas Turbine | 191262 | Stand Alone Small Upgrade | 559800 | 2026-04-27 | 2026-04-27
7FA.04 | NAM North America | 297543 | Gas Turbine | 191690 | Stand Alone Small Upgrade | 560056 | 2027-05-03 | 2028-01-03
7FA.04 | NAM North America | 297543 | Gas Turbine | 192616 | Large Call-Out | 560736 | 2027-03-06 | 2027-04-30
7FA.04 | NAM North America | 297544 | Gas Turbine | 192931 | Hot Gas Path Inspection (HGPI) | 560840 | 2029-07-01 | 2029-07-14
7FA.04 | NAM North America | 298298 | Gas Turbine | 193588 | Large Call-Out | 561336 | 2026-04-27 | 2026-05-13
7FA.04 | NAM North America | 297715 | Gas Turbine | 193949 | Major Inspection (MI) | 561663 | 2030-05-16 | 2030-06-21
7FA.04 | NAM North America | 297875 | Gas Turbine | 194508 | Borescope Inspection (BI) | 562147 | 2027-03-21 | 2027-03-23
7FA.04 | NAM North America | 297513 | Gas Turbine | 194631 | Major Inspection (MI) | 562253 | 2029-10-01 | 2029-11-09
7FA.04 | NAM North America | 297514 | Gas Turbine | 194633 | Major Inspection (MI) | 562254 | 2029-10-01 | 2029-11-09
7FA.04 | NAM North America | 297627 | Gas Turbine | 194738 | Stand Alone Small Upgrade |  | 2027-04-08 | 2027-04-26
7FA.04 | Asia | 299712 | Gas Turbine | 195235 | Hot Gas Path Inspection (HGPI) | 562736 | 2029-01-01 | 2029-01-17
7FA.04 | MENA | 299234 | Gas Turbine | 195311 | Major Inspection (MI) | 562780 | 2030-03-06 | 2030-03-31
7FA.04 | MENA | 299235 | Gas Turbine | 195313 | Major Inspection (MI) | 562781 | 2030-12-02 | 2030-12-27
7FA.04-200 | NAM North America | 297515 | Gas Turbine | 147590 | Major Inspection (MI) | 542884 | 2028-04-01 | 2028-06-14
7FA.04-200 | NAM North America | 297516 | Gas Turbine | 147592 | Major Inspection (MI) | 542885 | 2028-04-01 | 2028-06-14
7FA.04-200 | NAM North America | 297515 | Gas Turbine | 162142 | Large Call-Out | 540544 | 2026-03-07 | 2026-03-30
7FA.04-200 | NAM North America | 297516 | Gas Turbine | 188388 | Large Call-Out | 558065 | 2026-03-07 | 2026-03-30
7FA.05 | NAM North America | 299374 | Gas Turbine | 106434 | Hot Gas Path Inspection (HGPI) | 502807 | 2027-03-12 | 2027-03-28
7FA.05 | NAM North America | 299233 | Gas Turbine | 106530 | Hot Gas Path Inspection (HGPI) | 502903 | 2026-01-19 | 2026-02-04
7FA.05 | NAM North America | 299375 | Gas Turbine | 106546 | Hot Gas Path Inspection (HGPI) | 502919 | 2030-03-26 | 2030-04-09
7FA.05 | Latin America | 299382 | Gas Turbine | 106646 | Major Inspection (MI) | 503019 | 2026-01-28 | 2026-03-01
7FA.05 | NAM North America | 299410 | Gas Turbine | 120996 | Major Inspection (MI) | 541705 | 2026-03-08 | 2026-04-24
7FA.05 | MENA | 299361 | Gas Turbine | 130964 | Hot Gas Path Inspection (HGPI) |  | 2026-03-01 | 2026-03-15
7FA.05 | MENA | 299362 | Gas Turbine | 130979 | Hot Gas Path Inspection (HGPI) |  | 2026-03-01 | 2026-03-15
7FA.05 | MENA | 299355 | Gas Turbine | 131000 | Hot Gas Path Inspection (HGPI) |  | 2026-03-31 | 2026-04-14
7FA.05 | MENA | 299356 | Gas Turbine | 131001 | Hot Gas Path Inspection (HGPI) |  | 2026-03-31 | 2026-04-14
7FA.05 | NAM North America | 299213 | Gas Turbine | 131577 | Hot Gas Path Inspection (HGPI) | 521536 | 2026-03-23 | 2026-05-13
7FA.05 | Latin America | 299367 | Gas Turbine | 139348 | Hot Gas Path Inspection (HGPI) | 525680 | 2026-10-03 | 2026-10-17
7FA.05 | NAM North America | 299212 | Gas Turbine | 144439 | Hot Gas Path Inspection (HGPI) | 529220 | 2027-03-08 | 2027-03-21
7FA.05 | NAM North America | 299525 | Gas Turbine | 144442 | Hot Gas Path Inspection (HGPI) | 528945 | 2026-10-14 | 2026-10-31
7FA.05 | NAM North America | 299404 | Gas Turbine | 144450 | Hot Gas Path Inspection (HGPI) | 538013 | 2028-03-11 | 2028-04-04
7FA.05 | NAM North America | 299545 | Gas Turbine | 145252 | Major Inspection (MI) | 556724 | 2027-09-11 | 2027-10-14
7FA.05 | NAM North America | 299544 | Gas Turbine | 145254 | Major Inspection (MI) |  | 2028-04-25 | 2028-05-23
7FA.05 | NAM North America | 299212 | Gas Turbine | 146164 | Stand Alone Small Upgrade | 529488 | 2026-04-06 | 2026-04-12
7FA.05 | NAM North America | 299213 | Gas Turbine | 146170 | Stand Alone Small Upgrade | 529494 | 2026-04-10 | 2026-04-15
7FA.05 | NAM North America | 299557 | Gas Turbine | 146476 | Major Inspection (MI) | 546844 | 2029-03-06 | 2029-04-06
7FA.05 | NAM North America | 299558 | Gas Turbine | 146477 | Major Inspection (MI) | 549449 | 2029-03-06 | 2029-04-06
7FA.05 | NAM North America | 299559 | Gas Turbine | 146479 | Major Inspection (MI) | 541046 | 2029-04-17 | 2029-05-18
7FA.05 | NAM North America | 299560 | Gas Turbine | 146480 | Major Inspection (MI) | 541047 | 2029-04-17 | 2029-05-18
7FA.05 | Latin America | 299365 | Gas Turbine | 146639 | Major Inspection (MI) | 540873 | 2028-03-18 | 2028-04-18
7FA.05 | Latin America | 299366 | Gas Turbine | 146640 | Major Inspection (MI) | 540874 | 2028-10-21 | 2028-11-21
7FA.05 | Latin America | 299367 | Gas Turbine | 146641 | Major Inspection (MI) | 540875 | 2029-10-20 | 2029-11-18
7FA.05 | NAM North America | 299409 | Gas Turbine | 146679 | Hot Gas Path Inspection (HGPI) |  | 2028-06-08 | 2028-06-22
7FA.05 | NAM North America | 299327 | Gas Turbine | 146740 | Hot Gas Path Inspection (HGPI) | 534414 | 2027-05-03 | 2027-05-17
7FA.05 | NAM North America | 299328 | Gas Turbine | 146741 | Hot Gas Path Inspection (HGPI) | 541139 | 2026-09-21 | 2026-10-05
7FA.05 | NAM North America | 299438 | Gas Turbine | 146743 | Hot Gas Path Inspection (HGPI) | 553529 | 2027-03-15 | 2027-03-31
7FA.05 | NAM North America | 299439 | Gas Turbine | 146744 | Hot Gas Path Inspection (HGPI) | 553530 | 2027-10-31 | 2027-11-14
7FA.05 | MENA | 299425 | Gas Turbine | 146803 | Major Inspection (MI) | 538301 | 2026-01-08 | 2026-02-19
7FA.05 | MENA | 299425 | Gas Turbine | 146805 | Hot Gas Path Inspection (HGPI) | 538303 | 2028-04-30 | 2028-05-14
7FA.05 | MENA | 299489 | Gas Turbine | 146819 | Major Inspection (MI) | 540965 | 2027-02-01 | 2027-02-28
7FA.05 | NAM North America | 299232 | Gas Turbine | 146837 | Hot Gas Path Inspection (HGPI) | 541000 | 2027-01-26 | 2027-02-09
7FA.05 | NAM North America | 299427 | Gas Turbine | 146937 | Combustion Inspection (CI) | 531829 | 2026-04-13 | 2026-04-22
7FA.05 | NAM North America | 299428 | Gas Turbine | 146938 | Combustion Inspection (CI) | 534878 | 2026-11-02 | 2026-11-11
7FA.05 | NAM North America | 299427 | Gas Turbine | 146939 | Major Inspection (MI) | 541161 | 2027-03-08 | 2027-05-05
7FA.05 | NAM North America | 299428 | Gas Turbine | 146940 | Major Inspection (MI) | 541162 | 2027-10-20 | 2027-11-17
7FA.05 | NAM North America | 299486 | Gas Turbine | 149553 | Hot Gas Path Inspection (HGPI) | 531487 | 2026-12-03 | 2026-12-20
7FA.05 | MENA | 299359 | Gas Turbine | 154191 | Hot Gas Path Inspection (HGPI) | 534697 | 2027-02-05 | 2027-03-01
7FA.05 | MENA | 299362 | Gas Turbine | 154229 | Hot Gas Path Inspection (HGPI) | 534702 | 2026-12-13 | 2026-12-29
7FA.05 | MENA | 299363 | Gas Turbine | 154247 | Hot Gas Path Inspection (HGPI) | 534703 | 2026-11-08 | 2026-11-24
7FA.05 | MENA | 299364 | Gas Turbine | 154262 | Hot Gas Path Inspection (HGPI) | 534704 | 2026-10-25 | 2026-11-10
7FA.05 | MENA | 299356 | Gas Turbine | 154326 | Hot Gas Path Inspection (HGPI) | 534744 | 2026-11-12 | 2026-12-08
7FA.05 | MENA | 299357 | Gas Turbine | 154328 | Hot Gas Path Inspection (HGPI) | 534745 | 2026-10-19 | 2026-11-14
7FA.05 | MENA | 299358 | Gas Turbine | 154330 | Hot Gas Path Inspection (HGPI) | 534746 | 2026-10-01 | 2026-10-27
7FA.05 | NAM North America | 299404 | Gas Turbine | 155200 | Borescope Inspection (BI) | 535363 | 2026-03-01 | 2026-03-03
7FA.05 | NAM North America | 299405 | Gas Turbine | 155202 | Borescope Inspection (BI) | 535365 | 2026-03-03 | 2026-03-06
7FA.05 | NAM North America | 299405 | Gas Turbine | 155203 | Borescope Inspection (BI) | 535366 | 2026-11-08 | 2026-11-11
7FA.05 | NAM North America | 299406 | Gas Turbine | 155204 | Borescope Inspection (BI) | 535367 | 2026-03-06 | 2026-03-09
7FA.05 | NAM North America | 299406 | Gas Turbine | 155205 | Borescope Inspection (BI) | 535368 | 2026-11-23 | 2026-11-26
7FA.05 | NAM North America | 299405 | Gas Turbine | 158728 | Hot Gas Path Inspection (HGPI) | 538014 | 2028-10-07 | 2028-10-31
7FA.05 | NAM North America | 299406 | Gas Turbine | 158733 | Hot Gas Path Inspection (HGPI) | 538015 | 2029-03-31 | 2029-04-24
7FA.05 | NAM North America | 299667 | Gas Turbine | 159183 | Hot Gas Path Inspection (HGPI) | 538263 | 2028-10-28 | 2028-11-15
7FA.05 | NAM North America | 299666 | Gas Turbine | 159185 | Hot Gas Path Inspection (HGPI) | 552007 | 2029-04-05 | 2029-04-25
7FA.05 | NAM North America | 299665 | Gas Turbine | 159187 | Hot Gas Path Inspection (HGPI) | 538264 | 2029-11-03 | 2029-11-23
7FA.05 | Latin America | 299365 | Gas Turbine | 162531 | Hot Gas Path Inspection (HGPI) | 540876 | 2030-07-01 | 2030-07-15
7FA.05 | Latin America | 299366 | Gas Turbine | 162532 | Hot Gas Path Inspection (HGPI) | 540877 | 2030-10-27 | 2030-11-10
7FA.05 | NAM North America | 299438 | Gas Turbine | 162564 | Major Inspection (MI) |  | 2030-03-07 | 2030-04-04
7FA.05 | NAM North America | 299439 | Gas Turbine | 162565 | Major Inspection (MI) |  | 2030-10-22 | 2030-11-19
7FA.05 | MENA | 299490 | Gas Turbine | 162689 | Major Inspection (MI) | 540966 | 2027-01-03 | 2027-01-30
7FA.05 | MENA | 299491 | Gas Turbine | 162691 | Major Inspection (MI) | 540967 | 2028-01-01 | 2028-01-26
7FA.05 | MENA | 299492 | Gas Turbine | 162692 | Major Inspection (MI) | 540968 | 2028-03-01 | 2028-03-26
7FA.05 | NAM North America | 299233 | Gas Turbine | 162738 | Major Inspection (MI) | 541001 | 2029-01-08 | 2029-02-05
7FA.05 | NAM North America | 299419 | Gas Turbine | 162770 | Major Inspection (MI) | 542041 | 2027-05-10 | 2027-06-09
7FA.05 | NAM North America | 299418 | Gas Turbine | 162771 | Major Inspection (MI) | 541031 | 2027-05-03 | 2027-06-02
7FA.05 | MENA | 299356 | Gas Turbine | 162922 | Major Inspection (MI) | 545052 | 2029-12-25 | 2030-01-22
7FA.05 | MENA | 299355 | Gas Turbine | 162923 | Major Inspection (MI) | 541098 | 2029-10-26 | 2029-11-23
7FA.05 | MENA | 299357 | Gas Turbine | 162925 | Major Inspection (MI) | 559486 | 2030-10-01 | 2030-10-29
7FA.05 | MENA | 299358 | Gas Turbine | 162927 | Major Inspection (MI) | 541099 | 2030-11-09 | 2030-12-07
7FA.05 | MENA | 299359 | Gas Turbine | 162928 | Major Inspection (MI) | 541100 | 2028-12-10 | 2029-01-07
7FA.05 | MENA | 299360 | Gas Turbine | 162929 | Major Inspection (MI) | 541101 | 2028-12-22 | 2029-01-19
7FA.05 | MENA | 299361 | Gas Turbine | 162932 | Major Inspection (MI) | 541102 | 2029-10-01 | 2029-10-29
7FA.05 | MENA | 299362 | Gas Turbine | 162934 | Major Inspection (MI) | 541103 | 2029-10-26 | 2029-11-23
7FA.05 | MENA | 299363 | Gas Turbine | 162936 | Major Inspection (MI) | 541104 | 2030-10-23 | 2030-11-20
7FA.05 | MENA | 299364 | Gas Turbine | 162938 | Major Inspection (MI) | 541105 | 2030-10-01 | 2030-10-29
7FA.05 | NAM North America | 299410 | Gas Turbine | 162974 | Hot Gas Path Inspection (HGPI) | 558425 | 2030-04-21 | 2030-05-05
7FA.05 | NAM North America | 299375 | Gas Turbine | 162998 | Hot Gas Path Inspection (HGPI) | 541151 | 2028-10-01 | 2028-10-15
7FA.05 | MENA | 299649 | Gas Turbine | 163140 | Hot Gas Path Inspection (HGPI) |  | 2029-10-01 | 2029-10-15
7FA.05 | MENA | 299650 | Gas Turbine | 163141 | Hot Gas Path Inspection (HGPI) |  | 2029-10-01 | 2029-10-15
7FA.05 | NAM North America | 299409 | Gas Turbine | 168910 | Major Inspection (MI) | 545656 | 2026-10-04 | 2026-11-02
7FA.05 | NAM North America | 299525 | Gas Turbine | 173090 | Major Inspection (MI) | 548103 | 2029-09-28 | 2029-10-26
7FA.05 | NAM North America | 299524 | Gas Turbine | 173092 | Major Inspection (MI) | 548104 | 2030-10-05 | 2030-11-02
7FA.05 | NAM North America | 299328 | Gas Turbine | 175582 | Major Inspection (MI) | 549954 | 2030-05-01 | 2030-05-29
7FA.05 | NAM North America | 299327 | Gas Turbine | 175583 | Major Inspection (MI) | 549702 | 2030-10-07 | 2030-11-04
7FA.05 | NAM North America | 299232 | Gas Turbine | 175808 | Major Inspection (MI) | 549872 | 2029-06-12 | 2029-07-10
7FA.05 | NAM North America | 299448 | Gas Turbine | 176001 | Combustion Inspection (CI) | 553896 | 2028-11-01 | 2028-11-08
7FA.05 | NAM North America | 299449 | Gas Turbine | 176003 | Combustion Inspection (CI) |  | 2029-06-16 | 2029-06-23
7FA.05 | Latin America | 299382 | Gas Turbine | 176086 | Hot Gas Path Inspection (HGPI) | 550043 | 2029-01-29 | 2029-02-25
7FA.05 | Latin America | 299689 | Gas Turbine | 176096 | Hot Gas Path Inspection (HGPI) | 550044 | 2029-10-01 | 2029-10-20
7FA.05 | Latin America | 299690 | Gas Turbine | 176098 | Hot Gas Path Inspection (HGPI) | 550045 | 2028-10-02 | 2028-10-21
7FA.05 | MENA | 299651 | Gas Turbine | 179413 | Hot Gas Path Inspection (HGPI) | 551983 | 2030-03-14 | 2030-04-04
7FA.05 | NAM North America | 299524 | Gas Turbine | 179706 | Stand Alone Small Upgrade | 552156 | 2026-10-14 | 2026-10-31
7FA.05 | MENA | 299649 | Gas Turbine | 182180 | Hot Gas Path Inspection (HGPI) | 553612 | 2029-03-14 | 2029-03-28
7FA.05 | MENA | 299650 | Gas Turbine | 182182 | Hot Gas Path Inspection (HGPI) | 553613 | 2030-02-17 | 2030-03-10
7FA.05 | NAM North America | 299669 | Gas Turbine | 184505 | Hot Gas Path Inspection (HGPI) | 555072 | 2030-11-04 | 2030-11-29
7FA.05 | NAM North America | 299668 | Gas Turbine | 184506 | Hot Gas Path Inspection (HGPI) | 555074 | 2030-03-04 | 2030-03-29
7FA.05 | NAM North America | 299525 | Gas Turbine | 187767 | Hot Gas Path Inspection (HGPI) |  | 2026-05-01 | 2026-05-15
7FA.05 | NAM North America | 299524 | Gas Turbine | 187768 | Major Inspection (MI) |  | 2029-11-13 | 2029-12-11
7FA.05 | NAM North America | 299525 | Gas Turbine | 187769 | Major Inspection (MI) | 557717 | 2030-05-09 | 2030-06-06
7FA.05 | NAM North America | 299418 | Gas Turbine | 189463 | Hot Gas Path Inspection (HGPI) |  | 2030-12-11 | 2030-12-25
7FA.05 | NAM North America | 299419 | Gas Turbine | 189464 | Hot Gas Path Inspection (HGPI) |  | 2030-12-11 | 2030-12-25
7FA.05 | MENA | 299353 | Gas Turbine | 190816 | Major Inspection (MI) | 559457 | 2028-10-01 | 2028-10-29
7FA.05 | MENA | 299354 | Gas Turbine | 190817 | Major Inspection (MI) | 559456 | 2028-10-01 | 2028-10-29
7FA.05 | NAM North America | 299666 | Gas Turbine | 193179 | Large Call-Out | 560974 | 2026-04-06 | 2026-04-30
7FA.05 | MENA | 299649 | Gas Turbine | 193264 | Hot Gas Path Inspection (HGPI) | 561045 | 2028-12-08 | 2028-12-30
7FA.05 | MENA | 299650 | Gas Turbine | 193268 | Hot Gas Path Inspection (HGPI) | 561049 | 2030-02-17 | 2030-03-10
7FA.05 | MENA | 299651 | Gas Turbine | 193269 | Hot Gas Path Inspection (HGPI) | 561050 | 2030-03-14 | 2030-04-04
7FA.05 | NAM North America | 299404 | Gas Turbine | 194443 | Borescope Inspection (BI) | 562087 | 2027-11-16 | 2027-11-19
7FA.05 | NAM North America | 299405 | Gas Turbine | 194466 | Borescope Inspection (BI) | 562106 | 2027-03-20 | 2027-03-23
7FA.05 | NAM North America | 299405 | Gas Turbine | 194740 | Borescope Inspection (BI) | 562353 | 2027-11-18 | 2027-11-21
7FA.05 | NAM North America | 299405 | Gas Turbine | 194745 | Borescope Inspection (BI) | 562356 | 2027-03-20 | 2027-03-23
7FA.05 | NAM North America | 299405 | Gas Turbine | 194747 | Borescope Inspection (BI) | 562357 | 2028-03-20 | 2028-03-23
7FA.05 | NAM North America | 299405 | Gas Turbine | 194748 | Borescope Inspection (BI) | 562359 | 2028-11-22 | 2028-11-24
7FA.05 | NAM North America | 299711 | Gas Turbine | 194942 | Hot Gas Path Inspection (HGPI) | 562528 | 2028-04-08 | 2028-05-14
7FA.05 | NAM North America | 299406 | Gas Turbine | 195508 | Borescope Inspection (BI) | 562946 | 2027-03-24 | 2027-03-27
7FA.05 | NAM North America | 299406 | Gas Turbine | 195509 | Borescope Inspection (BI) | 562947 | 2027-11-22 | 2027-11-25
7FA.05 | NAM North America | 299406 | Gas Turbine | 195510 | Borescope Inspection (BI) | 562950 | 2028-03-24 | 2028-03-27
7FA.05 | NAM North America | 299406 | Gas Turbine | 195511 | Borescope Inspection (BI) | 562951 | 2028-11-25 | 2028-11-28
7FA.05 | NAM North America | 299406 | Gas Turbine | 195513 | Borescope Inspection (BI) | 562952 | 2029-03-25 | 2029-03-28
7FA.05 | NAM North America | 299665 | Gas Turbine | 195515 | Borescope Inspection (BI) | 562953 | 2027-03-28 | 2027-03-31
7FA.05 | NAM North America | 299666 | Gas Turbine | 195516 | Borescope Inspection (BI) | 562954 | 2027-04-01 | 2027-04-04
7FA.05 | NAM North America | 299667 | Gas Turbine | 195517 | Borescope Inspection (BI) | 562955 | 2027-04-05 | 2027-04-08
7FA.05 | NAM North America | 299665 | Gas Turbine | 195550 | Borescope Inspection (BI) | 562975 | 2027-11-26 | 2027-11-29
7FA.05 | NAM North America | 299666 | Gas Turbine | 195552 | Borescope Inspection (BI) | 562976 | 2027-11-30 | 2027-12-03
7FA.05 | NAM North America | 299667 | Gas Turbine | 195553 | Borescope Inspection (BI) | 562977 | 2027-12-03 | 2027-12-06
7FA.05 | NAM North America | 299665 | Gas Turbine | 195554 | Borescope Inspection (BI) | 562978 | 2028-03-28 | 2028-03-31
7FA.05 | NAM North America | 299666 | Gas Turbine | 195559 | Borescope Inspection (BI) | 562979 | 2028-04-01 | 2028-04-04
7FA.05 | NAM North America | 299667 | Gas Turbine | 195560 | Borescope Inspection (BI) | 562980 | 2028-04-05 | 2028-04-08
7FA.05 | NAM North America | 299665 | Gas Turbine | 195563 | Borescope Inspection (BI) | 562981 | 2028-11-25 | 2028-11-28
7FA.05 | NAM North America | 299666 | Gas Turbine | 195564 | Borescope Inspection (BI) | 562982 | 2028-11-30 | 2028-12-03
7FA.05 | NAM North America | 299667 | Gas Turbine | 195565 | Borescope Inspection (BI) | 562983 | 2028-12-04 | 2028-12-07
7FB.04 | NAM North America | 297599 | Gas Turbine | 146922 | Hot Gas Path Inspection (HGPI) | 544846 | 2028-03-01 | 2028-05-15
7FB.04 | NAM North America | 297600 | Gas Turbine | 146924 | Hot Gas Path Inspection (HGPI) | 544847 | 2028-03-01 | 2028-05-15
7FB.04 | NAM North America | 298598 | Gas Turbine | 163049 | Major Inspection (MI) | 541178 | 2028-11-30 | 2028-12-28
7FB.04 | NAM North America | 298596 | Gas Turbine | 176133 | Major Inspection (MI) | 550066 | 2029-11-30 | 2029-12-28
7FB.04 | NAM North America | 298597 | Gas Turbine | 176135 | Major Inspection (MI) | 550067 | 2030-11-30 | 2030-12-28
7FH2 | MENA | 338X374 | Generator | 103898 | Minor Inspection | 501589 | 2028-12-21 | 2029-01-04
7FH2 | NAM North America | 337X770 | Generator | 109071 | Major Inspection (Robotic) | 505365 | 2027-08-28 | 2027-11-12
7FH2 | NAM North America | 337X811 | Generator | 111531 | Major Inspection (Robotic) | 512081 | 2027-10-01 | 2027-11-07
7FH2 | NAM North America | 338X434 | Generator | 112162 | Major Inspection (Rotor Out) | 505671 | 2030-02-25 | 2030-03-25
7FH2 | NAM North America | 290T597 | Generator | 114814 | Major Inspection (Rotor Out) | 505680 | 2030-02-25 | 2030-03-25
7FH2 | Latin America | 338X398 | Generator | 115146 | Minor Inspection | 513531 | 2026-01-27 | 2026-02-12
7FH2 | NAM North America | 337X170 | Generator | 115250 | Major Inspection (Rotor Out) | 506361 | 2027-03-01 | 2027-04-13
7FH2 | Latin America | 338X396 | Generator | 117067 | Minor Inspection | 513310 | 2026-01-22 | 2026-02-07
7FH2 | NAM North America | 337X170 | Generator | 118118 | Minor Inspection | 506360 | 2029-10-22 | 2029-11-05
7FH2 | Latin America | 338X397 | Generator | 118355 | Minor Inspection | 513524 | 2026-02-07 | 2026-02-21
7FH2 | NAM North America | 337X171 | Generator | 122486 | Major Inspection (Rotor Out) | 505727 | 2026-11-03 | 2026-12-17
7FH2 | NAM North America | 337X769 | Generator | 122638 | Major Inspection (Robotic) | 505350 | 2027-08-28 | 2027-11-12
7FH2 | NAM North America | 337X714 | Generator | 123056 | Minor Inspection | 503596 | 2028-03-20 | 2028-04-09
7FH2 | NAM North America | 338X433 | Generator | 124143 | Major Inspection (Rotor Out) | 505670 | 2030-10-14 | 2030-11-11
7FH2 | NAM North America | 337X746 | Generator | 124420 | Major Inspection (Robotic) | 508061 | 2030-03-06 | 2030-04-03
7FH2 | NAM North America | 337X171 | Generator | 124835 | Minor Inspection | 505732 | 2028-04-11 | 2028-05-01
7FH2 | Latin America | 337X451 | Generator | 125847 | Minor Inspection | 516738 | 2026-11-23 | 2026-12-07
7FH2 | Latin America | 337X369 | Generator | 126058 | Major Inspection (Rotor Out) | 503000 | 2026-03-02 | 2026-03-30
7FH2 | Latin America | 337X370 | Generator | 126060 | Major Inspection (Rotor Out) | 503001 | 2026-03-02 | 2026-03-28
7FH2 | Latin America | 337X450 | Generator | 126074 | Minor Inspection | 516945 | 2026-11-06 | 2026-11-20
7FH2 | Latin America | 338X399 | Generator | 126758 | Minor Inspection | 517572 | 2026-11-06 | 2026-11-20
7FH2 | NAM North America | 338X765 | Generator | 136070 | Major Inspection (Robotic) | 523622 | 2027-03-15 | 2027-04-15
7FH2 | NAM North America | 337X794 | Generator | 137216 | Major Inspection (Rotor Out) | 502966 | 2026-09-21 | 2027-01-17
7FH2 | NAM North America | 338X722 | Generator | 137217 | Major Inspection (Rotor Out) | 502967 | 2026-09-28 | 2027-02-03
7FH2 | MENA | 337X490 | Generator | 139832 | Major Inspection (Rotor Out) | 525952 | 2026-10-19 | 2026-11-12
7FH2 | MENA | 338X379 | Generator | 140004 | Major Inspection (Robotic) | 525947 | 2026-01-15 | 2026-02-07
7FH2 | NAM North America | 337X029 | Generator | 141290 | Minor Inspection | 505711 | 2026-01-20 | 2026-02-13
7FH2 | NAM North America | 337X155 | Generator | 142410 | Minor Inspection | 502920 | 2026-04-19 | 2026-05-04
7FH2 | NAM North America | 338X435 | Generator | 144523 | Major Inspection (Robotic) | 528496 | 2026-04-27 | 2026-06-08
7FH2 | NAM North America | 338X338 | Generator | 144970 | Major Inspection (Robotic) | 502964 | 2026-03-06 | 2026-05-07
7FH2 | NAM North America | 338X337 | Generator | 144971 | Major Inspection (Robotic) | 502848 | 2026-03-06 | 2026-05-24
7FH2 | NAM North America | 338X766 | Generator | 145030 | Minor Inspection | 528795 | 2029-09-10 | 2029-10-10
7FH2 | NAM North America | 338X767 | Generator | 145032 | Minor Inspection | 528796 | 2028-03-06 | 2028-04-06
7FH2 | NAM North America | 338X768 | Generator | 145034 | Minor Inspection | 528797 | 2027-09-13 | 2027-10-13
7FH2 | NAM North America | 338X775 | Generator | 145067 | Major Inspection (Robotic) | 528813 | 2027-03-15 | 2027-04-01
7FH2 | NAM North America | 338X751 | Generator | 145405 | Major Inspection (Robotic) | 529082 | 2026-03-29 | 2026-05-07
7FH2 | NAM North America | 338X750 | Generator | 145407 | Major Inspection (Robotic) | 529084 | 2026-11-16 | 2026-12-20
7FH2 | NAM North America | 337X063 | Generator | 147074 | Major Inspection (Robotic) | 548188 | 2026-04-12 | 2026-05-11
7FH2 | Latin America | 337X465 | Generator | 147396 | Major Inspection (Robotic) | 530181 | 2027-02-19 | 2027-03-22
7FH2 | Latin America | 337X466 | Generator | 147440 | Major Inspection (Robotic) | 530213 | 2027-03-24 | 2027-04-24
7FH2 | NAM North America | 338X404 | Generator | 147934 | Major Inspection (Rotor Out) | 524381 | 2026-03-02 | 2026-03-23
7FH2 | Latin America | 337X837 | Generator | 148179 | Minor Inspection | 530594 | 2026-11-01 | 2026-12-02
7FH2 | Latin America | 337X838 | Generator | 148181 | Minor Inspection | 530595 | 2026-11-01 | 2026-12-02
7FH2 | MENA | 338X786 | Generator | 148214 | Minor Inspection | 530623 | 2026-03-29 | 2026-05-12
7FH2 | NAM North America | 338X321 | Generator | 149444 | Minor Inspection | 531419 | 2029-03-05 | 2029-03-22
7FH2 | NAM North America | 338X322 | Generator | 149445 | Minor Inspection | 531420 | 2029-03-05 | 2029-04-03
7FH2 | NAM North America | 338X340 | Generator | 149471 | Major Inspection (Rotor Out) | 531435 | 2028-03-28 | 2028-04-30
7FH2 | NAM North America | 338X341 | Generator | 149472 | Major Inspection (Rotor Out) | 531436 | 2027-03-14 | 2027-04-16
7FH2 | NAM North America | 338X339 | Generator | 149474 | Major Inspection (Rotor Out) | 531437 | 2029-03-28 | 2029-04-30
7FH2 | NAM North America | 337X288 | Generator | 149544 | Minor Inspection | 530377 | 2026-09-23 | 2026-10-17
7FH2 | NAM North America | 337X289 | Generator | 149545 | Minor Inspection | 530378 | 2026-09-23 | 2026-10-17
7FH2 | NAM North America | 337X233 | Generator | 149555 | Major Inspection (Rotor Out) | 531488 | 2026-09-14 | 2026-10-11
7FH2 | NAM North America | 337X235 | Generator | 149557 | Major Inspection (Rotor Out) | 531490 | 2026-10-16 | 2026-11-01
7FH2 | NAM North America | 337X216 | Generator | 149671 | Major Inspection (Rotor Out) | 531595 | 2027-09-28 | 2027-11-12
7FH2 | NAM North America | 337X217 | Generator | 149672 | Major Inspection (Rotor Out) | 531596 | 2026-10-02 | 2026-12-04
7FH2 | NAM North America | 337X218 | Generator | 149674 | Major Inspection (Rotor Out) | 531597 | 2028-09-28 | 2028-11-12
7FH2 | NAM North America | 338X713 | Generator | 149675 | Major Inspection (Rotor Out) | 531598 | 2026-10-30 | 2026-12-14
7FH2 | NAM North America | 338X714 | Generator | 149677 | Major Inspection (Rotor Out) | 531599 | 2027-04-15 | 2027-05-30
7FH2 | NAM North America | 338X715 | Generator | 149679 | Major Inspection (Rotor Out) | 531600 | 2027-10-02 | 2027-11-16
7FH2 | NAM North America | 337X813 | Generator | 150074 | Major Inspection (Robotic) | 510963 | 2026-03-27 | 2026-06-01
7FH2 | NAM North America | 337X132 | Generator | 150415 | Major Inspection (Robotic) | 532112 | 2027-04-07 | 2027-05-30
7FH2 | Latin America | 338X785 | Generator | 152156 | Major Inspection (Rotor Out) | 533199 | 2026-11-24 | 2026-12-22
7FH2 | NAM North America | 337X779 | Generator | 152652 | Major Inspection (Rotor Out) | 533619 | 2026-09-21 | 2026-11-04
7FH2 | NAM North America | 338X782 | Generator | 153577 | Minor Inspection | 534306 | 2026-04-13 | 2026-05-05
7FH2 | NAM North America | 338X783 | Generator | 153612 | Minor Inspection | 534338 | 2026-10-19 | 2026-11-10
7FH2 | NAM North America | 338X425 | Generator | 153930 | Major Inspection (Stator Rewind) | 531099 | 2026-04-11 | 2026-05-25
7FH2 | NAM North America | 338X781 | Generator | 154019 | Minor Inspection | 534646 | 2027-04-09 | 2027-04-26
7FH2 | NAM North America | 338X719 | Generator | 154289 | Major Inspection (Robotic) | 534714 | 2026-03-16 | 2026-05-07
7FH2 | NAM North America | 337X336 | Generator | 154820 | Major Inspection (Rotor Out) | 535061 | 2026-02-23 | 2026-04-27
7FH2 | NAM North America | 337X337 | Generator | 154822 | Major Inspection (Robotic) | 535062 | 2026-02-19 | 2026-04-27
7FH2 | NAM North America | 338X438 | Generator | 155020 | Major Inspection (Robotic) | 535216 | 2026-10-21 | 2026-11-05
7FH2 | Latin America | 337X464 | Generator | 155654 | Borescope Inspection (BI) | 535661 | 2027-09-27 | 2027-10-16
7FH2 | Latin America | 337X462 | Generator | 155661 | Borescope Inspection (BI) | 535698 | 2027-11-17 | 2027-12-09
7FH2 | Latin America | 337X463 | Generator | 155662 | Borescope Inspection (BI) | 535699 | 2027-10-25 | 2027-11-16
7FH2 | Asia | 337X804 | Generator | 156155 | Major Inspection (Rotor Out) | 529688 | 2026-01-01 | 2026-01-30
7FH2 | Asia | 337X805 | Generator | 156156 | Major Inspection (Rotor Out) | 535939 | 2026-04-01 | 2026-06-10
7FH2 | Latin America | 337X478 | Generator | 156318 | Major Inspection (Robotic) | 536083 | 2027-09-01 | 2027-09-26
7FH2 | Latin America | 337X477 | Generator | 156319 | Major Inspection (Robotic) | 536084 | 2028-01-10 | 2028-02-01
7FH2 | Latin America | 338X784 | Generator | 156320 | Major Inspection (Robotic) | 536085 | 2028-03-02 | 2028-03-25
7FH2 | NAM North America | 338X709 | Generator | 157550 | Major Inspection (Rotor Out) | 502819 | 2026-02-14 | 2026-04-03
7FH2 | NAM North America | 338X710 | Generator | 157552 | Major Inspection (Rotor Out) | 502820 | 2026-02-07 | 2026-03-30
7FH2 | NAM North America | 338X711 | Generator | 157554 | Major Inspection (Rotor Out) | 535682 | 2027-01-21 | 2027-03-13
7FH2 | NAM North America | 338X712 | Generator | 157555 | Major Inspection (Rotor Out) | 535683 | 2027-01-21 | 2027-03-13
7FH2 | Latin America | 338X700 | Generator | 157754 | Minor Inspection | 507744 | 2026-01-12 | 2026-01-30
7FH2 | Latin America | 338X701 | Generator | 157755 | Minor Inspection | 507836 | 2026-01-13 | 2026-01-31
7FH2 | Latin America | 337X133 | Generator | 157756 | Major Inspection (Robotic) | 537317 | 2027-02-05 | 2027-02-19
7FH2 | Latin America | 337X846 | Generator | 158140 | Major Inspection (Robotic) |  | 2027-02-01 | 2027-03-02
7FH2 | Latin America | 337X847 | Generator | 158141 | Major Inspection (Robotic) |  | 2027-02-01 | 2027-03-02
7FH2 | Latin America | 337X847 | Generator | 158142 | Major Inspection (Robotic) | 537612 | 2027-03-01 | 2027-03-30
7FH2 | Latin America | 337X846 | Generator | 158143 | Major Inspection (Robotic) | 537613 | 2027-03-01 | 2027-03-30
7FH2 | NAM North America | 338X406 | Generator | 158593 | Minor Inspection | 537930 | 2027-04-15 | 2027-05-01
7FH2 | NAM North America | 338X408 | Generator | 158594 | Major Inspection (Stator Rewind) | 537931 | 2028-03-06 | 2028-03-22
7FH2 | Latin America | 338X700 | Generator | 158630 | Major Inspection (Robotic) | 537955 | 2029-09-30 | 2029-10-28
7FH2 | Latin America | 338X701 | Generator | 158631 | Major Inspection (Robotic) | 537956 | 2030-03-02 | 2030-03-30
7FH2 | Latin America | 337X134 | Generator | 158633 | Minor Inspection | 537957 | 2028-11-18 | 2028-12-02
7FH2 | Latin America | 337X135 | Generator | 158634 | Major Inspection (Robotic) | 537958 | 2028-11-18 | 2028-12-16
7FH2 | Latin America | 337X133 | Generator | 158635 | Minor Inspection | 537959 | 2030-10-01 | 2030-10-15
7FH2 | MENA | 338X377 | Generator | 158644 | Major Inspection (Robotic) | 537961 | 2026-02-12 | 2026-03-07
7FH2 | MENA | 338X378 | Generator | 158645 | Major Inspection (Robotic) | 537962 | 2026-03-12 | 2026-04-06
7FH2 | MENA | 338X381 | Generator | 158646 | Major Inspection (Robotic) | 537963 | 2028-12-06 | 2029-01-03
7FH2 | MENA | 338X371 | Generator | 158648 | Minor Inspection | 537964 | 2028-03-31 | 2028-04-28
7FH2 | MENA | 338X372 | Generator | 158649 | Minor Inspection | 537965 | 2028-12-08 | 2029-01-05
7FH2 | MENA | 338X373 | Generator | 158652 | Minor Inspection | 537966 | 2029-01-01 | 2029-01-29
7FH2 | MENA | 338X375 | Generator | 158654 | Minor Inspection | 537967 | 2028-11-22 | 2028-12-20
7FH2 | MENA | 338X382 | Generator | 158655 | Major Inspection (Robotic) | 537968 | 2027-12-20 | 2028-01-11
7FH2 | MENA | 338X380 | Generator | 158658 | Major Inspection (Robotic) | 537969 | 2028-02-15 | 2028-03-13
7FH2 | MENA | 338X379 | Generator | 158660 | Minor Inspection | 537970 | 2029-01-29 | 2029-02-26
7FH2 | MENA | 338X376 | Generator | 158662 | Minor Inspection | 537971 | 2029-04-27 | 2029-05-25
7FH2 | MENA | 338X377 | Generator | 158664 | Minor Inspection | 537972 | 2029-07-10 | 2029-08-07
7FH2 | MENA | 338X378 | Generator | 158666 | Minor Inspection | 537973 | 2029-08-10 | 2029-09-07
7FH2 | NAM North America | 337X029 | Generator | 158684 | Major Inspection (Robotic) | 537989 | 2029-08-20 | 2029-09-17
7FH2 | Asia | 337X829 | Generator | 158737 | Major Inspection (Rotor Out) | 538018 | 2028-01-23 | 2028-02-25
7FH2 | MENA | 337X488 | Generator | 158898 | Minor Inspection | 538109 | 2028-09-05 | 2028-10-03
7FH2 | MENA | 337X487 | Generator | 158900 | Minor Inspection | 538110 | 2028-11-02 | 2028-11-30
7FH2 | MENA | 337X489 | Generator | 158902 | Minor Inspection | 538111 | 2029-05-17 | 2029-06-14
7FH2 | MENA | 337X490 | Generator | 158904 | Minor Inspection | 538112 | 2029-08-19 | 2029-09-16
7FH2 | MENA | 338X602 | Generator | 158906 | Major Inspection (Robotic) | 538113 | 2027-12-03 | 2027-12-28
7FH2 | MENA | 338X604 | Generator | 158911 | Major Inspection (Robotic) | 538114 | 2029-03-30 | 2029-04-27
7FH2 | MENA | 337X376 | Generator | 158913 | Minor Inspection | 538115 | 2026-01-16 | 2026-02-01
7FH2 | NAM North America | 337X119 | Generator | 158917 | Major Inspection (Robotic) | 538121 | 2028-04-15 | 2028-05-13
7FH2 | NAM North America | 337X118 | Generator | 158920 | Major Inspection (Robotic) | 538122 | 2028-04-16 | 2028-05-14
7FH2 | NAM North America | 337X776 | Generator | 158923 | Major Inspection (Robotic) | 538125 | 2027-10-10 | 2027-11-07
7FH2 | NAM North America | 337X775 | Generator | 158925 | Major Inspection (Robotic) | 538126 | 2028-04-08 | 2028-05-06
7FH2 | NAM North America | 337X117 | Generator | 158933 | Major Inspection (Robotic) | 538129 | 2029-04-30 | 2029-05-28
7FH2 | NAM North America | 337X394 | Generator | 159049 | Minor Inspection | 535678 | 2026-03-27 | 2026-05-10
7FH2 | NAM North America | 337X393 | Generator | 159050 | Minor Inspection | 535677 | 2026-03-27 | 2026-05-10
7FH2 | NAM North America | 338X387 | Generator | 159051 | Major Inspection (Robotic) | 535679 | 2028-02-05 | 2028-03-19
7FH2 | NAM North America | 338X388 | Generator | 159052 | Major Inspection (Robotic) | 535680 | 2028-02-05 | 2028-03-19
7FH2 | NAM North America | 337X208 | Generator | 159093 | Minor Inspection | 538203 | 2026-02-18 | 2026-03-31
7FH2 | NAM North America | 337X207 | Generator | 159094 | Minor Inspection | 538204 | 2026-02-18 | 2026-03-31
7FH2 | NAM North America | 338X437 | Generator | 159095 | Major Inspection (Robotic) | 538205 | 2027-05-19 | 2027-06-02
7FH2 | NAM North America | 338X436 | Generator | 159097 | Major Inspection (Robotic) | 538206 | 2028-08-23 | 2028-09-07
7FH2 | NAM North America | 338X438 | Generator | 159098 | Major Inspection (Stator Rewind) | 538207 | 2030-12-25 | 2031-02-22
7FH2 | NAM North America | 337X228 | Generator | 159122 | Minor Inspection | 538219 | 2028-12-21 | 2029-01-04
7FH2 | NAM North America | 337X226 | Generator | 159126 | Minor Inspection | 538220 | 2028-12-21 | 2029-01-04
7FH2 | NAM North America | 337X227 | Generator | 159127 | Minor Inspection | 538221 | 2028-06-21 | 2028-07-05
7FH2 | NAM North America | 337X210 | Generator | 159140 | Major Inspection (Robotic) | 538231 | 2028-02-21 | 2028-03-22
7FH2 | NAM North America | 337X209 | Generator | 159141 | Major Inspection (Robotic) | 538232 | 2028-02-21 | 2028-03-22
7FH2 | NAM North America | 338X447 | Generator | 159145 | Major Inspection (Rotor Out) | 538233 | 2027-08-01 | 2027-10-01
7FH2 | NAM North America | 338X448 | Generator | 159147 | Major Inspection (Robotic) | 538234 | 2028-12-09 | 2029-01-06
7FH2 | NAM North America | 337X196 | Generator | 159154 | Major Inspection (Rotor Out) | 513739 | 2026-10-01 | 2026-11-09
7FH2 | NAM North America | 337X188 | Generator | 159155 | Major Inspection (Robotic) | 513740 | 2026-03-01 | 2026-04-21
7FH2 | NAM North America | 337X239 | Generator | 159156 | Major Inspection (Rotor Out) | 503022 | 2027-03-01 | 2027-04-08
7FH2 | NAM North America | 337X240 | Generator | 159157 | Major Inspection (Rotor Out) | 538237 | 2029-03-01 | 2029-04-08
7FH2 | NAM North America | 338X501 | Generator | 159170 | Major Inspection (Field Rewind) | 538254 | 2027-03-08 | 2027-04-06
7FH2 | NAM North America | 338X743 | Generator | 159172 | Major Inspection (Robotic) | 538255 | 2028-10-09 | 2028-10-23
7FH2 | NAM North America | 338X742 | Generator | 159173 | Minor Inspection | 538256 | 2028-10-15 | 2028-11-12
7FH2 | NAM North America | 338X500 | Generator | 159176 | Major Inspection (Field Rewind) | 538258 | 2027-10-01 | 2027-10-29
7FH2 | NAM North America | 338X340 | Generator | 159189 | Major Inspection (Robotic) | 538266 | 2028-04-30 | 2028-05-28
7FH2 | NAM North America | 338X339 | Generator | 159192 | Major Inspection (Robotic) | 538267 | 2030-04-08 | 2030-05-06
7FH2 | NAM North America | 338X718 | Generator | 159193 | Minor Inspection | 538269 | 2027-09-21 | 2027-10-19
7FH2 | NAM North America | 338X720 | Generator | 159194 | Minor Inspection | 538270 | 2027-10-01 | 2027-10-29
7FH2 | NAM North America | 337X113 | Generator | 159197 | Minor Inspection | 538271 | 2029-11-24 | 2029-12-08
7FH2 | NAM North America | 337X114 | Generator | 159200 | Minor Inspection | 538272 | 2029-11-24 | 2029-12-08
7FH2 | NAM North America | 338X435 | Generator | 159202 | Major Inspection (Robotic) | 538274 | 2030-12-06 | 2031-01-03
7FH2 | NAM North America | 337X482 | Generator | 159205 | Minor Inspection | 538278 | 2026-10-03 | 2026-10-19
7FH2 | NAM North America | 337X483 | Generator | 159206 | Minor Inspection | 538279 | 2027-04-16 | 2027-04-30
7FH2 | NAM North America | 337X045 | Generator | 159230 | Minor Inspection | 538297 | 2026-10-02 | 2026-10-19
7FH2 | NAM North America | 337X044 | Generator | 159233 | Minor Inspection | 538298 | 2027-03-19 | 2027-04-05
7FH2 | NAM North America | 337X045 | Generator | 159234 | Major Inspection (Stator Rewind) | 538299 | 2029-10-02 | 2029-11-30
7FH2 | NAM North America | 337X044 | Generator | 159236 | Major Inspection (Stator Rewind) | 538300 | 2030-03-02 | 2030-04-30
7FH2 | Latin America | GG10530 | Generator | 159254 | Major Inspection (Robotic) | 534894 | 2029-02-17 | 2029-03-13
7FH2 | Latin America | GG10531 | Generator | 159255 | Major Inspection (Robotic) | 534893 | 2029-02-17 | 2029-03-13
7FH2 | Latin America | GG10529 | Generator | 159256 | Major Inspection (Robotic) | 534892 | 2028-02-18 | 2028-03-13
7FH2 | Latin America | GG10528 | Generator | 159257 | Major Inspection (Robotic) | 534891 | 2028-02-18 | 2028-03-13
7FH2 | NAM North America | 338X502 | Generator | 159272 | Major Inspection (Field Rewind) | 538323 | 2027-10-01 | 2027-10-27
7FH2 | NAM North America | 337X752 | Generator | 159815 | Minor Inspection | 502887 | 2027-03-01 | 2027-05-05
7FH2 | NAM North America | 337X778 | Generator | 161395 | Major Inspection (Robotic) | 514523 | 2026-01-29 | 2026-04-20
7FH2 | NAM North America | 337X812 | Generator | 161959 | Major Inspection (Robotic) | 502973 | 2028-04-01 | 2028-05-09
7FH2 | Asia | 337X454 | Generator | 162154 | Minor Inspection | 540556 | 2027-10-01 | 2027-10-17
7FH2 | Asia | 337X455 | Generator | 162155 | Minor Inspection | 540557 | 2027-10-01 | 2027-10-17
7FH2 | Asia | 337X456 | Generator | 162157 | Minor Inspection | 540558 | 2028-10-01 | 2028-10-17
7FH2 | Latin America | 337X469 | Generator | 162416 | Major Inspection (Robotic) | 540792 | 2028-04-09 | 2028-05-10
7FH2 | Latin America | 337X480 | Generator | 162417 | Major Inspection (Robotic) | 540789 | 2026-05-03 | 2026-06-03
7FH2 | MENA | 338X788 | Generator | 162560 | Minor Inspection | 540889 | 2027-01-12 | 2027-01-26
7FH2 | Latin America | 338X395 | Generator | 162576 | Minor Inspection | 540910 | 2028-06-02 | 2028-06-30
7FH2 | Latin America | 338X785 | Generator | 162577 | Minor Inspection | 540911 | 2028-12-02 | 2028-12-30
7FH2 | Latin America | 338X704 | Generator | 162652 | Minor Inspection | 540936 | 2028-02-15 | 2028-03-05
7FH2 | Latin America | 338X705 | Generator | 162655 | Minor Inspection | 540937 | 2028-02-15 | 2028-03-05
7FH2 | Latin America | 337X461 | Generator | 162662 | Major Inspection (Robotic) | 540943 | 2029-10-01 | 2029-10-29
7FH2 | Latin America | 337X460 | Generator | 162663 | Major Inspection (Robotic) | 540944 | 2029-10-01 | 2029-10-29
7FH2 | Latin America | 337X485 | Generator | 162710 | Major Inspection (Robotic) | 540980 | 2026-03-26 | 2026-04-29
7FH2 | Latin America | 337X479 | Generator | 162711 | Major Inspection (Robotic) | 540981 | 2028-03-04 | 2028-04-04
7FH2 | Latin America | 337X468 | Generator | 162720 | Major Inspection (Robotic) | 533954 | 2028-05-15 | 2028-06-15
7FH2 | Latin America | GG10425 | Generator | 162761 | Minor Inspection | 541015 | 2028-03-31 | 2028-04-05
7FH2 | NAM North America | 337X773 | Generator | 162964 | Minor Inspection | 541128 | 2029-01-24 | 2029-02-07
7FH2 | NAM North America | 337X774 | Generator | 162966 | Minor Inspection | 541129 | 2029-11-30 | 2029-12-28
7FH2 | NAM North America | 337X278 | Generator | 163013 | Minor Inspection | 541163 | 2028-05-23 | 2028-06-06
7FH2 | NAM North America | 337X279 | Generator | 163014 | Minor Inspection | 541164 | 2029-05-23 | 2029-06-20
7FH2 | NAM North America | 338X524 | Generator | 163015 | Minor Inspection | 541165 | 2029-05-23 | 2029-06-20
7FH2 | NAM North America | 337X330 | Generator | 163033 | Major Inspection (Rotor Out) | 541169 | 2026-09-28 | 2026-11-16
7FH2 | NAM North America | 337X331 | Generator | 163034 | Minor Inspection | 541170 | 2027-03-04 | 2027-04-28
7FH2 | NAM North America | 337X332 | Generator | 163035 | Major Inspection (Rotor Out) | 541171 | 2026-10-02 | 2026-11-20
7FH2 | NAM North America | 337X399 | Generator | 163060 | Minor Inspection | 541182 | 2030-04-12 | 2030-05-02
7FH2 | NAM North America | 337X152 | Generator | 163148 | Major Inspection (Robotic) | 541256 | 2028-10-01 | 2028-11-01
7FH2 | NAM North America | 337X153 | Generator | 163150 | Major Inspection (Robotic) | 541257 | 2028-10-01 | 2028-11-01
7FH2 | NAM North America | 337X154 | Generator | 163152 | Major Inspection (Robotic) | 541258 | 2029-10-01 | 2029-11-01
7FH2 | NAM North America | 337X236 | Generator | 163181 | Major Inspection (Robotic) | 541288 | 2028-04-03 | 2028-05-03
7FH2 | NAM North America | 337X259 | Generator | 163182 | Major Inspection (Robotic) | 541289 | 2028-04-03 | 2028-05-03
7FH2 | NAM North America | 337X260 | Generator | 163183 | Major Inspection (Robotic) | 541290 | 2028-04-03 | 2028-05-03
7FH2 | NAM North America | 337X709 | Generator | 163184 | Minor Inspection | 541291 | 2028-03-07 | 2028-03-21
7FH2 | NAM North America | 337X708 | Generator | 163185 | Minor Inspection | 541292 | 2028-03-07 | 2028-03-21
7FH2 | NAM North America | 337X710 | Generator | 163187 | Minor Inspection | 541293 | 2029-03-17 | 2029-03-31
7FH2 | NAM North America | 337X711 | Generator | 163188 | Minor Inspection | 541294 | 2029-03-17 | 2029-03-31
7FH2 | NAM North America | 337X261 | Generator | 163191 | Major Inspection (Robotic) | 541295 | 2030-04-01 | 2030-05-01
7FH2 | NAM North America | 337X262 | Generator | 163196 | Major Inspection (Robotic) | 541296 | 2030-04-01 | 2030-05-01
7FH2 | NAM North America | 337X263 | Generator | 163197 | Major Inspection (Robotic) | 541297 | 2030-04-01 | 2030-05-01
7FH2 | Latin America | 290T870 | Generator | 163419 | Major Inspection (Robotic) | 523664 | 2026-04-22 | 2026-05-30
7FH2 | MENA | 338X370 | Generator | 163427 | Major Inspection (Robotic) | 541496 | 2026-10-02 | 2026-10-17
7FH2 | NAM North America | 290T519 | Generator | 163812 | Minor Inspection | 541800 | 2026-02-18 | 2026-03-31
7FH2 | NAM North America | 337X189 | Generator | 163927 | Major Inspection (Robotic) | 541896 | 2027-04-26 | 2027-05-24
7FH2 | NAM North America | 337X093 | Generator | 164527 | Minor Inspection | 542395 | 2028-03-25 | 2028-04-08
7FH2 | NAM North America | 337X211 | Generator | 164575 | Major Inspection (Robotic) | 542428 | 2027-01-09 | 2027-04-03
7FH2 | NAM North America | 338X521 | Generator | 164591 | Major Inspection (Robotic) | 542446 | 2028-03-08 | 2028-05-22
7FH2 | NAM North America | 337X751 | Generator | 164852 | Minor Inspection | 542656 | 2026-04-04 | 2026-05-01
7FH2 | NAM North America | 337X758 | Generator | 165013 | Minor Inspection | 542762 | 2027-04-03 | 2027-05-17
7FH2 | NAM North America | 337X212 | Generator | 165043 | Major Inspection (Robotic) | 542429 | 2027-01-09 | 2027-04-03
7FH2 | NAM North America | 337X305 | Generator | 165044 | Major Inspection (Robotic) | 542784 | 2027-10-01 | 2027-10-29
7FH2 | NAM North America | 337X304 | Generator | 165045 | Major Inspection (Robotic) | 542785 | 2028-03-01 | 2028-03-29
7FH2 | NAM North America | 337X112 | Generator | 165048 | Minor Inspection | 542786 | 2027-03-21 | 2027-04-10
7FH2 | NAM North America | 337X475 | Generator | 165049 | Minor Inspection | 542787 | 2027-02-17 | 2027-04-07
7FH2 | NAM North America | 337X244 | Generator | 165061 | Minor Inspection | 542795 | 2026-09-26 | 2026-10-16
7FH2 | NAM North America | 337X755 | Generator | 165064 | Major Inspection (Robotic) | 542796 | 2029-03-15 | 2029-04-12
7FH2 | NAM North America | 337X756 | Generator | 165065 | Major Inspection (Robotic) | 542797 | 2029-03-15 | 2029-04-12
7FH2 | Latin America | 337X836 | Generator | 165067 | Major Inspection (Robotic) | 542798 | 2029-03-01 | 2029-03-30
7FH2 | Latin America | 337X831 | Generator | 165068 | Major Inspection (Rotor Out) | 542799 | 2029-03-01 | 2029-03-30
7FH2 | Latin America | 337X837 | Generator | 165071 | Major Inspection (Robotic) | 542800 | 2029-10-01 | 2029-10-31
7FH2 | Latin America | 337X838 | Generator | 165072 | Major Inspection (Robotic) | 542801 | 2029-10-01 | 2029-10-31
7FH2 | Latin America | 337X380 | Generator | 165074 | Minor Inspection | 513546 | 2026-01-05 | 2026-01-28
7FH2 | Latin America | 337X383 | Generator | 165075 | Minor Inspection | 502933 | 2026-02-02 | 2026-02-25
7FH2 | Latin America | 337X382 | Generator | 165076 | Minor Inspection | 542802 | 2026-02-02 | 2026-02-25
7FH2 | Latin America | 337X381 | Generator | 165077 | Minor Inspection | 513545 | 2026-01-05 | 2026-01-28
7FH2 | Latin America | 337X380 | Generator | 165083 | Major Inspection (Robotic) | 542803 | 2029-08-12 | 2029-09-09
7FH2 | Latin America | 337X382 | Generator | 165086 | Major Inspection (Rotor Out) | 542804 | 2029-09-17 | 2029-10-15
7FH2 | Latin America | 337X383 | Generator | 165087 | Major Inspection (Robotic) | 542805 | 2029-09-17 | 2029-10-15
7FH2 | Latin America | 337X381 | Generator | 165090 | Major Inspection (Robotic) | 542806 | 2029-08-12 | 2029-09-09
7FH2 | Latin America | 337X369 | Generator | 165092 | Minor Inspection | 542807 | 2030-03-01 | 2030-03-21
7FH2 | Latin America | 337X370 | Generator | 165093 | Minor Inspection | 542808 | 2030-03-01 | 2030-03-21
7FH2 | Latin America | 337X372 | Generator | 165094 | Major Inspection (Robotic) | 542809 | 2030-11-03 | 2030-12-01
7FH2 | Latin America | 337X371 | Generator | 165095 | Major Inspection (Robotic) | 542810 | 2030-11-03 | 2030-12-01
7FH2 | NAM North America | 337X854 | Generator | 165104 | Major Inspection (Robotic) | 542813 | 2026-09-28 | 2026-10-12
7FH2 | NAM North America | 337X855 | Generator | 165105 | Minor Inspection | 505683 | 2027-01-25 | 2027-02-08
7FH2 | NAM North America | 337X856 | Generator | 165106 | Major Inspection (Robotic) | 542814 | 2027-09-14 | 2027-10-14
7FH2 | NAM North America | 337X854 | Generator | 165107 | Major Inspection (Robotic) | 542815 | 2030-04-01 | 2030-04-29
7FH2 | NAM North America | 337X855 | Generator | 165110 | Major Inspection (Robotic) | 542816 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 337X740 | Generator | 165121 | Minor Inspection | 542821 | 2026-10-01 | 2026-10-30
7FH2 | NAM North America | 337X741 | Generator | 165123 | Major Inspection (Robotic) | 542822 | 2029-10-05 | 2029-11-02
7FH2 | NAM North America | 337X389 | Generator | 165126 | Major Inspection (Robotic) | 542824 | 2027-10-17 | 2027-12-30
7FH2 | NAM North America | 337X850 | Generator | 165127 | Major Inspection (Robotic) | 534890 | 2026-04-10 | 2026-05-07
7FH2 | NAM North America | 337X850 | Generator | 165131 | Minor Inspection | 542826 | 2029-10-09 | 2029-11-06
7FH2 | NAM North America | 337X158 | Generator | 165132 | Minor Inspection | 509983 | 2029-03-01 | 2029-03-31
7FH2 | NAM North America | 338X723 | Generator | 165139 | Major Inspection (Robotic) | 542828 | 2028-01-30 | 2028-02-27
7FH2 | NAM North America | 338X724 | Generator | 165142 | Major Inspection (Robotic) | 542829 | 2028-01-30 | 2028-02-27
7FH2 | NAM North America | 337X178 | Generator | 165143 | Major Inspection (Rotor Out) | 542830 | 2026-11-01 | 2026-11-22
7FH2 | NAM North America | 337X177 | Generator | 165145 | Minor Inspection | 542831 | 2030-03-15 | 2030-03-29
7FH2 | NAM North America | 338X404 | Generator | 165148 | Minor Inspection | 542833 | 2026-03-26 | 2026-04-09
7FH2 | NAM North America | 337X705 | Generator | 165152 | Minor Inspection | 542834 | 2027-11-08 | 2027-12-09
7FH2 | NAM North America | 337X366 | Generator | 165153 | Minor Inspection | 542835 | 2026-04-11 | 2026-05-14
7FH2 | NAM North America | 337X365 | Generator | 165154 | Minor Inspection | 542836 | 2026-04-11 | 2026-05-14
7FH2 | NAM North America | 337X366 | Generator | 165155 | Major Inspection (Robotic) | 542837 | 2030-03-04 | 2030-04-01
7FH2 | NAM North America | 337X453 | Generator | 165157 | Major Inspection (Robotic) | 542838 | 2029-04-20 | 2029-06-04
7FH2 | NAM North America | 337X296 | Generator | 165160 | Minor Inspection | 542839 | 2028-12-08 | 2029-01-05
7FH2 | NAM North America | 337X295 | Generator | 165161 | Minor Inspection | 542840 | 2028-12-08 | 2029-01-05
7FH2 | NAM North America | 337X352 | Generator | 165164 | Major Inspection (Robotic) | 542841 | 2028-10-06 | 2028-11-09
7FH2 | NAM North America | 337X350 | Generator | 165165 | Major Inspection (Robotic) | 542842 | 2028-03-06 | 2028-04-09
7FH2 | NAM North America | 337X181 | Generator | 165171 | Major Inspection (Robotic) | 542845 | 2027-08-04 | 2027-10-09
7FH2 | NAM North America | 337X179 | Generator | 165172 | Major Inspection (Robotic) | 542846 | 2028-12-23 | 2029-01-20
7FH2 | NAM North America | 337X180 | Generator | 165176 | Major Inspection (Robotic) | 542847 | 2028-02-08 | 2028-04-15
7FH2 | NAM North America | 337X187 | Generator | 165178 | Major Inspection (Robotic) | 542848 | 2026-05-17 | 2026-06-02
7FH2 | NAM North America | 338X758 | Generator | 165179 | Major Inspection (Robotic) | 542849 | 2026-01-30 | 2026-03-15
7FH2 | NAM North America | 338X759 | Generator | 165180 | Major Inspection (Robotic) | 542850 | 2026-01-30 | 2026-03-15
7FH2 | NAM North America | 338X758 | Generator | 165181 | Minor Inspection | 542851 | 2030-09-01 | 2030-09-29
7FH2 | NAM North America | 338X759 | Generator | 165183 | Minor Inspection | 542852 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 338X726 | Generator | 165190 | Minor Inspection | 542853 | 2028-04-01 | 2028-04-15
7FH2 | NAM North America | 338X725 | Generator | 165191 | Minor Inspection | 542854 | 2028-04-01 | 2028-04-15
7FH2 | NAM North America | 338X728 | Generator | 165192 | Minor Inspection | 542855 | 2028-09-30 | 2028-10-14
7FH2 | NAM North America | 338X727 | Generator | 165193 | Minor Inspection | 542856 | 2028-09-30 | 2028-10-14
7FH2 | NAM North America | 338X522 | Generator | 165201 | Major Inspection (Robotic) | 536414 | 2028-03-01 | 2028-04-14
7FH2 | NAM North America | 337X139 | Generator | 165219 | Minor Inspection | 542859 | 2029-12-31 | 2030-01-14
7FH2 | NAM North America | 337X138 | Generator | 165220 | Minor Inspection | 542860 | 2030-04-30 | 2030-05-14
7FH2 | NAM North America | 337X289 | Generator | 165223 | Major Inspection (Robotic) | 542861 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 337X288 | Generator | 165224 | Major Inspection (Robotic) | 542862 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 337X054 | Generator | 165228 | Major Inspection (Stator Rewind) | 542864 | 2027-09-16 | 2027-11-04
7FH2 | NAM North America | 337X055 | Generator | 165229 | Minor Inspection | 542865 | 2027-09-16 | 2027-11-04
7FH2 | NAM North America | 338X383 | Generator | 165250 | Minor Inspection | 514783 | 2027-04-05 | 2027-04-20
7FH2 | NAM North America | 338X384 | Generator | 165251 | Minor Inspection | 514782 | 2027-04-05 | 2027-04-20
7FH2 | NAM North America | 337X397 | Generator | 165252 | Major Inspection (Rotor Out) | 542877 | 2027-03-06 | 2027-05-04
7FH2 | NAM North America | 337X073 | Generator | 165254 | Major Inspection (Robotic) | 542878 | 2028-11-14 | 2028-12-19
7FH2 | NAM North America | 337X806 | Generator | 165257 | Minor Inspection | 542879 | 2029-05-01 | 2029-05-29
7FH2 | NAM North America | 337X807 | Generator | 165258 | Minor Inspection | 542880 | 2029-07-07 | 2029-08-04
7FH2 | NAM North America | 337X163 | Generator | 165266 | Major Inspection (Robotic) | 542884 | 2028-04-01 | 2028-06-14
7FH2 | NAM North America | 337X164 | Generator | 165267 | Major Inspection (Robotic) | 542885 | 2028-04-01 | 2028-06-14
7FH2 | NAM North America | 337X204 | Generator | 165273 | Major Inspection (Robotic) | 542888 | 2027-11-18 | 2027-12-16
7FH2 | NAM North America | 337X203 | Generator | 165276 | Major Inspection (Robotic) | 542889 | 2028-05-10 | 2028-06-08
7FH2 | NAM North America | 337X202 | Generator | 165278 | Major Inspection (Robotic) | 542890 | 2028-11-05 | 2028-12-03
7FH2 | NAM North America | 337X233 | Generator | 165279 | Major Inspection (Robotic) | 542891 | 2026-09-14 | 2026-12-06
7FH2 | NAM North America | 337X235 | Generator | 165280 | Major Inspection (Robotic) | 542892 | 2027-10-18 | 2027-11-14
7FH2 | NAM North America | 338X519 | Generator | 165286 | Major Inspection (Robotic) | 542895 | 2027-03-10 | 2027-05-24
7FH2 | NAM North America | 338X518 | Generator | 165288 | Major Inspection (Robotic) | 542896 | 2027-03-10 | 2027-05-24
7FH2 | NAM North America | 337X270 | Generator | 165346 | Major Inspection (Robotic) | 542916 | 2026-11-04 | 2026-12-08
7FH2 | NAM North America | 337X760 | Generator | 165355 | Major Inspection (Robotic) | 542923 | 2027-04-03 | 2027-05-17
7FH2 | NAM North America | 338X520 | Generator | 165376 | Major Inspection (Robotic) | 542931 | 2028-03-08 | 2028-05-22
7FH2 | NAM North America | 337X392 | Generator | 165756 | Major Inspection (Rotor Out) | 543188 | 2026-01-25 | 2026-02-27
7FH2 | NAM North America | 290T737 | Generator | 165758 | Major Inspection (Rotor Out) | 543189 | 2026-01-28 | 2026-04-13
7FH2 | NAM North America | 290T524 | Generator | 166410 | Major Inspection (Robotic) | 542430 | 2027-01-09 | 2027-04-03
7FH2 | NAM North America | 337X753 | Generator | 166821 | Minor Inspection | 543923 | 2027-03-01 | 2027-05-05
7FH2 | NAM North America | 337X006 | Generator | 167337 | Minor Inspection |  | 2026-03-02 | 2026-03-23
7FH2 | NAM North America | 337X006 | Generator | 167338 | Major Inspection (Robotic) | 515661 | 2026-05-01 | 2026-06-20
7FH2 | NAM North America | 337X474 | Generator | 167995 | Minor Inspection | 544908 | 2027-02-17 | 2027-04-07
7FH2 | NAM North America | 337X290 | Generator | 168032 | Major Inspection (Robotic) | 544940 | 2028-10-02 | 2028-10-15
7FH2 | NAM North America | 337X291 | Generator | 168034 | Major Inspection (Robotic) | 544941 | 2028-10-02 | 2028-10-15
7FH2 | NAM North America | 290T468 | Generator | 168132 | Major Inspection (Rotor Out) | 545028 | 2028-04-01 | 2028-06-14
7FH2 | Latin America | 337X372 | Generator | 168156 | Minor Inspection | 545049 | 2029-01-15 | 2029-02-03
7FH2 | Latin America | 337X371 | Generator | 168157 | Minor Inspection | 545050 | 2029-01-15 | 2029-02-03
7FH2 | NAM North America | 337X390 | Generator | 168158 | Major Inspection (Robotic) | 544853 | 2027-10-31 | 2028-01-13
7FH2 | NAM North America | 337X351 | Generator | 168159 | Major Inspection (Robotic) | 545051 | 2028-03-06 | 2028-04-09
7FH2 | Asia | 337X828 | Generator | 168447 | Major Inspection (Rotor Out) | 533750 | 2027-02-05 | 2027-03-10
7FH2 | NAM North America | 337X105 | Generator | 168606 | Minor Inspection | 545405 | 2028-09-11 | 2028-10-11
7FH2 | NAM North America | 337X128 | Generator | 168608 | Minor Inspection | 545406 | 2029-03-05 | 2029-04-05
7FH2 | NAM North America | 338X416 | Generator | 168900 | Major Inspection (Stator Rewind) | 545647 | 2028-10-03 | 2028-11-15
7FH2 | NAM North America | 338X415 | Generator | 168901 | Major Inspection (Stator Rewind) | 545648 | 2028-03-02 | 2028-05-12
7FH2 | MENA | 338X603 | Generator | 168949 | Major Inspection (Robotic) | 545694 | 2027-10-29 | 2027-11-23
7FH2 | MENA | 338X601 | Generator | 168950 | Major Inspection (Robotic) | 545695 | 2028-10-01 | 2028-10-29
7FH2 | MENA | 338X600 | Generator | 168951 | Major Inspection (Robotic) | 545696 | 2028-04-01 | 2028-04-26
7FH2 | MENA | 338X605 | Generator | 168952 | Major Inspection (Robotic) | 545697 | 2028-10-01 | 2028-10-29
7FH2 | MENA | 338X606 | Generator | 168953 | Major Inspection (Robotic) | 545698 | 2029-04-10 | 2029-05-08
7FH2 | Latin America | 290T530 | Generator | 168982 | Minor Inspection | 545748 | 2028-02-15 | 2028-03-05
7FH2 | NAM North America | 338X708 | Generator | 171267 | Major Inspection (Rotor Out) | 547091 | 2030-01-01 | 2030-03-01
7FH2 | NAM North America | 338X772 | Generator | 171887 | Minor Inspection | 547286 | 2026-11-01 | 2026-11-24
7FH2 | NAM North America | 290T773 | Generator | 171888 | Minor Inspection | 547287 | 2026-11-01 | 2026-11-24
7FH2 | NAM North America | 337X772 | Generator | 172354 | Major Inspection (Rotor Out) | 504915 | 2026-02-02 | 2026-02-28
7FH2 | NAM North America | 337X179 | Generator | 172378 | Major Inspection (Robotic) | 547696 | 2027-02-04 | 2027-04-10
7FH2 | NAM North America | 338X417 | Generator | 172913 | Minor Inspection | 547995 | 2027-10-03 | 2027-11-15
7FH2 | NAM North America | 338X523 | Generator | 172915 | Minor Inspection | 547997 | 2027-10-03 | 2027-11-15
7FH2 | NAM North America | 338X415 | Generator | 172917 | Major Inspection (Stator Rewind) | 547998 | 2028-10-03 | 2028-11-15
7FH2 | NAM North America | 338X416 | Generator | 172919 | Minor Inspection | 547999 | 2028-03-01 | 2028-03-31
7FH2 | NAM North America | 337X813 | Generator | 173083 | Major Inspection (Robotic) | 548097 | 2030-07-22 | 2030-08-19
7FH2 | NAM North America | 338X391 | Generator | 173318 | Major Inspection (Robotic) | 548237 | 2029-05-22 | 2029-06-19
7FH2 | NAM North America | 338X407 | Generator | 173442 | Major Inspection (Stator Rewind) | 548284 | 2029-03-12 | 2029-03-28
7FH2 | NAM North America | 337X186 | Generator | 173560 | Major Inspection (Robotic) | 548353 | 2030-03-02 | 2030-03-20
7FH2 | Latin America | 337X486 | Generator | 173742 | Minor Inspection | 548488 | 2028-02-04 | 2028-02-18
7FH2 | NAM North America | 337X271 | Generator | 174609 | Major Inspection (Robotic) | 549061 | 2027-05-01 | 2027-06-04
7FH2 | NAM North America | 337X271 | Generator | 174617 | Major Inspection (Robotic) | 548425 | 2027-05-01 | 2027-06-04
7FH2 | NAM North America | 337X353 | Generator | 175431 | Major Inspection (Robotic) | 549599 | 2028-10-06 | 2028-11-09
7FH2 | Latin America | 337X451 | Generator | 175858 | Major Inspection (Robotic) | 549906 | 2030-10-12 | 2030-11-08
7FH2 | NAM North America | 337X159 | Generator | 175870 | Major Inspection (Robotic) | 549911 | 2028-12-31 | 2029-01-28
7FH2 | NAM North America | 337X160 | Generator | 175871 | Major Inspection (Robotic) | 549912 | 2028-12-31 | 2029-01-28
7FH2 | NAM North America | 337X155 | Generator | 176104 | Major Inspection (Robotic) | 550050 | 2029-10-01 | 2029-11-01
7FH2 | NAM North America | 338X409 | Generator | 176155 | Minor Inspection | 548742 | 2028-04-03 | 2028-05-08
7FH2 | NAM North America | 338X410 | Generator | 176156 | Minor Inspection | 548743 | 2029-03-05 | 2029-04-13
7FH2 | NAM North America | 337X763 | Generator | 176158 | Minor Inspection | 550072 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 337X762 | Generator | 176160 | Minor Inspection | 550073 | 2030-04-24 | 2030-05-22
7FH2 | NAM North America | 337X761 | Generator | 176162 | Minor Inspection | 550074 | 2029-09-01 | 2029-09-29
7FH2 | NAM North America | 337X394 | Generator | 176384 | Major Inspection (Robotic) | 550223 | 2030-05-09 | 2030-06-06
7FH2 | NAM North America | 338X709 | Generator | 176386 | Major Inspection (Robotic) | 550224 | 2030-09-08 | 2030-10-06
7FH2 | NAM North America | 337X131 | Generator | 176448 | Major Inspection (Robotic) | 548598 | 2027-04-07 | 2027-05-19
7FH2 | NAM North America | 337X766 | Generator | 177262 | Major Inspection (Robotic) | 550860 | 2028-03-26 | 2028-04-23
7FH2 | NAM North America | 337X765 | Generator | 177263 | Major Inspection (Robotic) | 550861 | 2028-03-26 | 2028-04-23
7FH2 | NAM North America | 337X703 | Generator | 177272 | Minor Inspection | 550865 | 2029-10-01 | 2029-10-29
7FH2 | NAM North America | 337X244 | Generator | 177279 | Major Inspection (Robotic) | 550867 | 2030-10-26 | 2030-11-23
7FH2 | NAM North America | 338X390 | Generator | 177351 | Minor Inspection | 550875 | 2028-03-13 | 2028-04-01
7FH2 | NAM North America | 338X389 | Generator | 177353 | Minor Inspection | 550876 | 2028-09-18 | 2028-10-07
7FH2 | NAM North America | 338X752 | Generator | 177361 | Major Inspection (Robotic) | 550879 | 2029-03-28 | 2029-04-25
7FH2 | NAM North America | 338X751 | Generator | 177363 | Major Inspection (Robotic) | 550880 | 2029-10-14 | 2029-11-11
7FH2 | NAM North America | 337X161 | Generator | 177372 | Major Inspection (Robotic) | 550883 | 2028-09-16 | 2028-10-14
7FH2 | NAM North America | 337X162 | Generator | 177373 | Major Inspection (Robotic) | 550884 | 2028-09-16 | 2028-10-14
7FH2 | NAM North America | 337X249 | Generator | 177379 | Major Inspection (Robotic) | 550887 | 2027-09-01 | 2027-09-28
7FH2 | NAM North America | 337X248 | Generator | 177382 | Major Inspection (Robotic) | 550888 | 2027-09-01 | 2027-09-28
7FH2 | NAM North America | 337X251 | Generator | 177383 | Major Inspection (Robotic) | 550889 | 2029-03-03 | 2029-03-31
7FH2 | NAM North America | 337X250 | Generator | 177386 | Major Inspection (Rotor Out) | 550890 | 2029-03-03 | 2029-03-31
7FH2 | NAM North America | 338X731 | Generator | 177397 | Minor Inspection | 550893 | 2029-04-07 | 2029-04-25
7FH2 | NAM North America | 338X732 | Generator | 177398 | Minor Inspection | 550894 | 2029-04-07 | 2029-04-25
7FH2 | NAM North America | 337X768 | Generator | 177403 | Minor Inspection | 550895 | 2030-04-13 | 2030-05-01
7FH2 | NAM North America | 337X767 | Generator | 177405 | Minor Inspection | 550896 | 2030-04-13 | 2030-05-01
7FH2 | NAM North America | 337X102 | Generator | 177411 | Minor Inspection | 550897 | 2028-10-01 | 2028-10-15
7FH2 | NAM North America | 337X103 | Generator | 177412 | Minor Inspection | 550898 | 2028-10-01 | 2028-10-15
7FH2 | NAM North America | 337X056 | Generator | 177415 | Minor Inspection | 550899 | 2028-11-23 | 2028-12-07
7FH2 | NAM North America | 337X057 | Generator | 177418 | Minor Inspection | 550900 | 2028-11-23 | 2028-12-07
7FH2 | NAM North America | 337X110 | Generator | 177420 | Minor Inspection | 550901 | 2027-11-09 | 2027-11-28
7FH2 | NAM North America | 337X111 | Generator | 177421 | Minor Inspection | 550902 | 2027-11-09 | 2027-11-28
7FH2 | NAM North America | 337X050 | Generator | 177423 | Minor Inspection | 505719 | 2027-03-05 | 2027-03-19
7FH2 | NAM North America | 337X049 | Generator | 177424 | Major Inspection (Robotic) | 505722 | 2030-05-11 | 2030-06-07
7FH2 | NAM North America | 338X440 | Generator | 177432 | Major Inspection (Robotic) | 550906 | 2026-07-04 | 2026-08-01
7FH2 | NAM North America | 338X439 | Generator | 177433 | Major Inspection (Robotic) | 550907 | 2026-07-04 | 2026-08-01
7FH2 | NAM North America | 338X424 | Generator | 177439 | Major Inspection (Robotic) | 550910 | 2027-10-18 | 2027-11-05
7FH2 | NAM North America | 337X182 | Generator | 178809 | Major Inspection (Robotic) | 551652 | 2028-05-08 | 2028-06-25
7FH2 | NAM North America | 337X183 | Generator | 178811 | Major Inspection (Robotic) | 551653 | 2028-05-08 | 2028-06-27
7FH2 | NAM North America | 337X842 | Generator | 178881 | Major Inspection (Robotic) | 551709 | 2029-11-01 | 2029-11-29
7FH2 | NAM North America | 337X843 | Generator | 178882 | Major Inspection (Robotic) | 551710 | 2030-02-01 | 2030-03-01
7FH2 | NAM North America | 337X067 | Generator | 180431 | Minor Inspection | 552525 | 2028-09-11 | 2028-10-11
7FH2 | NAM North America | 337X056 | Generator | 180821 | Large Call-Out | 552814 | 2026-08-01 | 2026-09-09
7FH2 | NAM North America | 337X819 | Generator | 180858 | Major Inspection (Rotor Out) | 552834 | 2026-05-19 | 2026-06-15
7FH2 | NAM North America | 337X199 | Generator | 181305 | Major Inspection (Stator Rewind) | 544848 | 2028-03-01 | 2028-05-15
7FH2 | NAM North America | 337X197 | Generator | 181349 | Major Inspection (Stator Rewind) | 544846 | 2028-03-01 | 2028-05-15
7FH2 | NAM North America | 337X198 | Generator | 181350 | Major Inspection (Stator Rewind) | 544847 | 2028-03-01 | 2028-05-15
7FH2 | NAM North America | 337X115 | Generator | 181470 | Major Inspection (Rotor Out) | 553097 | 2026-10-01 | 2026-10-31
7FH2 | NAM North America | 337X818 | Generator | 181490 | Major Inspection (Rotor Out) | 553100 | 2026-09-06 | 2026-11-24
7FH2 | NAM North America | 337X115 | Generator | 181529 | Major Inspection (Rotor Out) | 551953 | 2026-10-01 | 2026-12-14
7FH2 | NAM North America | 337X252 | Generator | 181600 | Major Inspection (Rotor Out) | 553169 | 2027-03-28 | 2027-06-15
7FH2 | NAM North America | 290T498 | Generator | 182066 | Minor Inspection | 553532 | 2029-03-05 | 2029-03-22
7FH2 | Latin America | 338X396 | Generator | 182153 | Major Inspection (Rotor Out) | 553594 | 2030-01-21 | 2030-02-17
7FH2 | Latin America | 338X397 | Generator | 182156 | Major Inspection (Rotor Out) | 553596 | 2030-02-20 | 2030-03-19
7FH2 | Latin America | 338X398 | Generator | 182158 | Major Inspection (Rotor Out) | 553597 | 2030-01-21 | 2030-02-17
7FH2 | NAM North America | 337X783 | Generator | 182311 | Minor Inspection | 553679 | 2029-10-01 | 2029-10-15
7FH2 | NAM North America | 337X784 | Generator | 182313 | Major Inspection (Robotic) | 508071 | 2030-10-01 | 2030-10-29
7FH2 | NAM North America | 337X788 | Generator | 182409 | Major Inspection (Robotic) | 553722 | 2028-11-01 | 2028-11-28
7FH2 | NAM North America | 337X790 | Generator | 182412 | Major Inspection (Robotic) | 553723 | 2028-02-01 | 2028-03-01
7FH2 | NAM North America | 337X787 | Generator | 182413 | Major Inspection (Robotic) | 553724 | 2029-02-01 | 2029-03-01
7FH2 | NAM North America | 337X789 | Generator | 182415 | Major Inspection (Robotic) | 553725 | 2027-11-01 | 2027-11-30
7FH2 | NAM North America | 337X234 | Generator | 182433 | Major Inspection (Robotic) | 548484 | 2027-05-08 | 2027-06-04
7FH2 | NAM North America | 290T512 | Generator | 182442 | Major Inspection (Rotor Out) | 553739 | 2028-05-08 | 2028-06-27
7FH2 | NAM North America | 338X772 | Generator | 182462 | Major Inspection (Rotor Out) | 553749 | 2030-02-01 | 2030-03-01
7FH2 | NAM North America | 337X214 | Generator | 182469 | Major Inspection (Robotic) | 553753 | 2029-04-30 | 2029-05-28
7FH2 | NAM North America | 337X213 | Generator | 182473 | Major Inspection (Robotic) | 553754 | 2029-04-30 | 2029-05-28
7FH2 | NAM North America | 337X867 | Generator | 182480 | Major Inspection (Robotic) | 553757 | 2028-09-05 | 2028-10-02
7FH2 | NAM North America | 337X771 | Generator | 183224 | Major Inspection (Robotic) | 504914 | 2026-02-02 | 2026-02-28
7FH2 | NAM North America | 337X816 | Generator | 183675 | Minor Inspection | 554520 | 2026-10-03 | 2026-11-03
7FH2 | NAM North America | 337X817 | Generator | 183677 | Minor Inspection | 554521 | 2026-10-03 | 2026-11-03
7FH2 | NAM North America | 337X757 | Generator | 183690 | Major Inspection (Rotor Out) | 554528 | 2027-10-02 | 2027-10-23
7FH2 | NAM North America | 338X427 | Generator | 184324 | Major Inspection (Robotic) | 554952 | 2028-05-15 | 2028-06-02
7FH2 | NAM North America | 337X009 | Generator | 184354 | Major Inspection (Robotic) | 554985 | 2030-10-05 | 2030-10-26
7FH2 | NAM North America | 337X008 | Generator | 184357 | Major Inspection (Robotic) | 554988 | 2030-10-05 | 2030-11-02
7FH2 | NAM North America | 337X003 | Generator | 184358 | Minor Inspection | 554989 | 2029-10-13 | 2029-10-31
7FH2 | NAM North America | 337X007 | Generator | 184381 | Major Inspection (Robotic) | 555007 | 2029-10-13 | 2030-05-25
7FH2 | NAM North America | 290T260 | Generator | 184384 | Major Inspection (Robotic) | 555009 | 2030-10-05 | 2030-11-03
7FH2 | NAM North America | 290T259 | Generator | 184388 | Major Inspection (Robotic) | 555011 | 2029-10-13 | 2029-10-31
7FH2 | NAM North America | 290T424 | Generator | 184397 | Major Inspection (Stator Rewind) | 555019 | 2027-09-16 | 2027-11-04
7FH2 | NAM North America | 337X759 | Generator | 184400 | Major Inspection (Robotic) | 555022 | 2029-04-01 | 2029-04-29
7FH2 | NAM North America | 290T451 | Generator | 184424 | Minor Inspection | 555047 | 2027-11-09 | 2027-11-28
7FH2 | NAM North America | 290T430 | Generator | 184595 | Major Inspection (Stator Rewind) | 555135 | 2027-03-08 | 2027-03-29
7FH2 | Latin America | 338X716 | Generator | 184629 | Major Inspection (Robotic) | 534881 | 2030-06-25 | 2030-07-24
7FH2 | NAM North America | 337X338 | Generator | 184779 | Major Inspection (Rotor Out) | 555278 | 2029-09-18 | 2029-10-17
7FH2 | NAM North America | 337X337 | Generator | 184780 | Major Inspection (Stator Rewind) | 555279 | 2030-02-19 | 2030-03-20
7FH2 | NAM North America | 337X336 | Generator | 184855 | Major Inspection (Rotor Out) | 555322 | 2030-02-19 | 2030-03-20
7FH2 | NAM North America | 337X750 | Generator | 185029 | Minor Inspection | 555434 | 2029-04-21 | 2029-05-12
7FH2 | NAM North America | 338X439 | Generator | 185214 | Major Inspection (Rotor Out) | 551236 | 2027-04-15 | 2027-05-12
7FH2 | NAM North America | 338X440 | Generator | 185215 | Major Inspection (Rotor Out) | 551238 | 2027-04-15 | 2027-05-12
7FH2 | NAM North America | 337X785 | Generator | 185524 | Major Inspection (Rotor Out) | 555822 | 2029-12-01 | 2029-12-11
7FH2 | NAM North America | 338X723 | Generator | 185579 | Major Inspection (Rotor Out) | 553023 | 2028-03-16 | 2028-05-31
7FH2 | NAM North America | 338X724 | Generator | 185580 | Major Inspection (Rotor Out) | 553024 | 2028-03-16 | 2028-05-31
7FH2 | NAM North America | 338X358 | Generator | 185657 | Major Inspection (Robotic) | 556064 | 2027-02-11 | 2027-02-16
7FH2 | NAM North America | 290T483 | Generator | 185868 | Major Inspection (Robotic) | 556045 | 2028-04-11 | 2028-05-11
7FH2 | NAM North America | 337X185 | Generator | 185879 | Major Inspection (Robotic) | 556048 | 2029-03-03 | 2029-03-21
7FH2 | NAM North America | 338X737 | Generator | 185985 | Minor Inspection | 551131 | 2027-10-21 | 2027-11-09
7FH2 | NAM North America | 290T658 | Generator | 186055 | Major Inspection (Robotic) | 556184 | 2027-02-05 | 2027-05-05
7FH2 | NAM North America | 338X738 | Generator | 186092 | Minor Inspection | 551132 | 2027-10-21 | 2027-11-24
7FH2 | MENA | 338X381 | Generator | 186151 | Major Inspection (Robotic) | 556249 | 2027-10-20 | 2027-11-11
7FH2 | NAM North America | 337X175 | Generator | 186216 | Minor Inspection | 556306 | 2027-03-01 | 2027-03-31
7FH2 | NAM North America | 337X176 | Generator | 186218 | Minor Inspection | 556308 | 2027-03-01 | 2027-03-31
7FH2 | NAM North America | 337X175 | Generator | 186267 | Minor Inspection | 555655 | 2028-10-16 | 2028-11-01
7FH2 | NAM North America | 337X176 | Generator | 186268 | Minor Inspection | 555658 | 2027-10-07 | 2027-11-07
7FH2 | NAM North America | 290T658 | Generator | 186278 | Major Inspection (Rotor Out) | 556353 | 2029-02-01 | 2029-02-28
7FH2 | NAM North America | 337X118 | Generator | 186302 | Minor Inspection | 556368 | 2028-09-01 | 2028-09-15
7FH2 | MENA | 338X787 | Generator | 186690 | Minor Inspection | 556588 | 2028-01-06 | 2028-01-20
7FH2 | NAM North America | 337X405 | Generator | 186964 | Minor Inspection | 556774 | 2028-04-20 | 2028-05-15
7FH2 | NAM North America | 337X405 | Generator | 186968 | Major Inspection (Robotic) |  | 2030-11-01 | 2030-11-15
7FH2 | NAM North America | 337X365 | Generator | 187189 | Major Inspection (Robotic) | 556935 | 2030-03-18 | 2030-04-15
7FH2 | NAM North America | 290T493 | Generator | 187451 | Minor Inspection | 557146 | 2026-11-01 | 2026-11-16
7FH2 | NAM North America | 290T493 | Generator | 187605 | Minor Inspection | 549952 | 2026-11-01 | 2026-11-18
7FH2 | NAM North America | 338X771 | Generator | 187651 | Minor Inspection | 557284 | 2030-12-20 | 2031-01-03
7FH2 | NAM North America | 338X709 | Generator | 187680 | Minor Inspection | 557295 | 2026-03-28 | 2026-04-11
7FH2 | NAM North America | 338X710 | Generator | 187683 | Minor Inspection | 557296 | 2026-03-28 | 2026-04-11
7FH2 | NAM North America | 338X712 | Generator | 187684 | Minor Inspection | 557297 | 2026-10-23 | 2026-11-06
7FH2 | NAM North America | 338X711 | Generator | 187687 | Minor Inspection | 557298 | 2026-10-23 | 2026-11-06
7FH2 | NAM North America | 338X713 | Generator | 187697 | Major Inspection (Robotic) | 535349 | 2026-10-01 | 2026-10-03
7FH2 | NAM North America | 338X714 | Generator | 187698 | Major Inspection (Robotic) | 557299 | 2027-04-01 | 2027-05-15
7FH2 | NAM North America | 338X715 | Generator | 187701 | Major Inspection (Robotic) | 557300 | 2027-10-01 | 2027-10-29
7FH2 | NAM North America | 337X218 | Generator | 187705 | Major Inspection (Robotic) | 557301 | 2028-10-01 | 2028-10-29
7FH2 | NAM North America | 337X815 | Generator | 187716 | Minor Inspection | 557306 | 2030-08-01 | 2030-08-15
7FH2 | NAM North America | 338X765 | Generator | 187719 | Minor Inspection | 557307 | 2026-07-30 | 2026-08-27
7FH2 | NAM North America | 337X115 | Generator | 187754 | Minor Inspection | 557313 | 2030-09-01 | 2030-09-15
7FH2 | NAM North America | 337X819 | Generator | 187756 | Minor Inspection | 557314 | 2030-09-17 | 2030-10-01
7FH2 | NAM North America | 338X434 | Generator | 187788 | Major Inspection (Robotic) | 557320 | 2028-09-22 | 2028-10-20
7FH2 | NAM North America | 338X433 | Generator | 187791 | Major Inspection (Robotic) | 557321 | 2029-04-16 | 2029-05-14
7FH2 | NAM North America | 337X127 | Generator | 187794 | Minor Inspection | 557322 | 2029-04-30 | 2029-05-14
7FH2 | NAM North America | 337X105 | Generator | 187796 | Minor Inspection | 557323 | 2026-04-07 | 2026-04-21
7FH2 | NAM North America | 337X068 | Generator | 187799 | Minor Inspection | 557324 | 2030-03-04 | 2030-04-04
7FH2 | NAM North America | 338X310 | Generator | 187807 | Minor Inspection | 556327 | 2027-11-26 | 2027-12-17
7FH2 | NAM North America | 338X313 | Generator | 187808 | Minor Inspection | 556328 | 2028-05-10 | 2028-05-31
7FH2 | NAM North America | 338X311 | Generator | 187809 | Minor Inspection | 556329 | 2028-10-01 | 2028-10-22
7FH2 | NAM North America | 338X315 | Generator | 187810 | Minor Inspection | 556330 | 2029-03-01 | 2029-03-22
7FH2 | NAM North America | 338X312 | Generator | 187811 | Minor Inspection | 556331 | 2029-11-01 | 2029-11-22
7FH2 | NAM North America | 338X314 | Generator | 187812 | Minor Inspection | 556332 | 2030-10-01 | 2030-10-22
7FH2 | NAM North America | 337X770 | Generator | 187833 | Major Inspection (Robotic) | 557327 | 2027-09-01 | 2027-09-29
7FH2 | NAM North America | 337X794 | Generator | 187836 | Major Inspection (Robotic) | 557329 | 2026-09-26 | 2026-10-24
7FH2 | NAM North America | 338X722 | Generator | 187839 | Major Inspection (Robotic) | 557330 | 2026-09-26 | 2026-10-24
7FH2 | NAM North America | 338X708 | Generator | 187840 | Major Inspection (Robotic) | 557331 | 2027-04-01 | 2027-04-29
7FH2 | NAM North America | 338X721 | Generator | 187843 | Major Inspection (Robotic) | 557332 | 2027-04-01 | 2027-04-29
7FH2 | NAM North America | 338X358 | Generator | 188322 | Major Inspection (Robotic) | 550956 | 2027-02-05 | 2027-05-05
7FH2 | MENA | 338X370 | Generator | 188442 | Minor Inspection | 557761 | 2026-08-27 | 2026-09-10
7FH2 | NAM North America | 337X816 | Generator | 188759 | Major Inspection (Robotic) | 558246 | 2030-03-01 | 2030-05-31
7FH2 | NAM North America | 337X817 | Generator | 188761 | Major Inspection (Robotic) | 558248 | 2030-03-01 | 2030-05-31
7FH2 | NAM North America | 337X049 | Generator | 188940 | Major Inspection (Stator Rewind) |  | 2027-03-01 | 2027-03-20
7FH2 | NAM North America | 337X269 | Generator | 189393 | Major Inspection (Robotic) | 558408 | 2027-05-01 | 2027-05-31
7FH2 | NAM North America | 290T443 | Generator | 189415 | Minor Inspection | 558424 | 2027-04-07 | 2027-04-30
7FH2 | NAM North America | 337X273 | Generator | 189658 | Minor Inspection | 558553 | 2030-09-20 | 2030-10-10
7FH2 | NAM North America | 337X061 | Generator | 189761 | Major Inspection (Stator Rewind) | 558637 | 2028-03-06 | 2028-04-22
7FH2 | NAM North America | 337X062 | Generator | 190955 | Major Inspection (Stator Rewind) | 559544 | 2029-03-05 | 2029-04-23
7FH2 | NAM North America | 290T762 | Generator | 190956 | Minor Inspection | 559547 | 2028-04-20 | 2028-05-15
7FH2 | NAM North America | 337X104 | Generator | 190967 | Minor Inspection |  | 2026-02-15 | 2026-02-27
7FH2 | NAM North America | 337X104 | Generator | 190970 | Minor Inspection | 559283 | 2026-01-30 | 2026-03-01
7FH2 | MENA | 338X367 | Generator | 191341 | Major Inspection (Robotic) | 559848 | 2028-10-07 | 2028-11-01
7FH2 | MENA | 338X369 | Generator | 191366 | Minor Inspection | 559868 | 2029-11-02 | 2029-11-17
7FH2 | MENA | 338X370 | Generator | 191368 | Major Inspection (Robotic) | 559869 | 2030-10-06 | 2030-10-31
7FH2 | MENA | 337X375 | Generator | 191371 | Major Inspection (Robotic) | 559871 | 2028-12-02 | 2028-12-27
7FH2 | MENA | 337X376 | Generator | 191373 | Major Inspection (Robotic) | 559872 | 2029-12-02 | 2029-12-27
7FH2 | MENA | 338X368 | Generator | 191375 | Major Inspection (Robotic) | 559873 | 2029-10-07 | 2029-11-01
7FH2 | NAM North America | 290T434 | Generator | 191957 | Minor Inspection | 555124 | 2028-03-07 | 2028-03-21
7FH2 | NAM North America | 337X758 | Generator | 192935 | Major Inspection (Robotic) | 560840 | 2029-07-01 | 2029-07-14
7FH2 | NAM North America | 290T452 | Generator | 193250 | Minor Inspection | 544766 | 2029-11-24 | 2029-12-08
7FH2 | NAM North America | 290T435 | Generator | 193514 | Minor Inspection | 558123 | 2029-03-17 | 2029-03-31
7FH2 | NAM North America | 337X269 | Generator | 193744 | Major Inspection (Robotic) | 548428 | 2027-05-01 | 2027-06-04
7FH2 | NAM North America | 337X187 | Generator | 193950 | Major Inspection (Robotic) | 561663 | 2030-05-16 | 2030-06-21
7FH2 | NAM North America | 337X129 | Generator | 194632 | Major Inspection (Rotor Out) | 562253 | 2029-10-01 | 2029-11-09
7FH2 | NAM North America | 337X130 | Generator | 194634 | Major Inspection (Rotor Out) | 562254 | 2029-10-01 | 2029-11-09
7FH2 | NAM North America | 337X819 | Generator | 195257 | Major Inspection (Robotic) | 562749 | 2028-10-10 | 2028-10-24
7FH2 | MENA | 338X786 | Generator | 195312 | Major Inspection (Robotic) | 562780 | 2030-03-06 | 2030-03-31
7FH2 | MENA | 338X788 | Generator | 195314 | Major Inspection (Robotic) | 562781 | 2030-12-02 | 2030-12-27
7FH2 | NAM North America | 337X703 | Generator | 196260 | Minor Inspection | 563521 | 2029-03-02 | 2029-03-21
7FH2 | NAM North America | 290T658 | Generator | 196263 | Major Inspection (Robotic) | 562689 | 2027-02-01 | 2027-05-01
7FH2 | NAM North America | 290T520 | Generator | 196428 | Major Inspection (Robotic) | 563672 | 2028-02-14 | 2028-03-29
7FH2B | Latin America | 761X102 | Generator | 151964 | Minor Inspection | 525680 | 2026-10-03 | 2026-10-17
7FH2B | NAM North America | 761X037 | Generator | 153724 | Minor Inspection | 534414 | 2027-05-03 | 2027-05-17
7FH2B | MENA | 761X204 | Generator | 154192 | Major Inspection (Rotor Out) | 534697 | 2027-02-05 | 2027-03-01
7FH2B | MENA | 761X207 | Generator | 154240 | Minor Inspection | 534702 | 2026-12-13 | 2026-12-29
7FH2B | MENA | 761X208 | Generator | 154261 | Minor Inspection | 534703 | 2026-11-08 | 2026-11-24
7FH2B | MENA | 761X209 | Generator | 154263 | Minor Inspection | 534704 | 2026-10-25 | 2026-11-10
7FH2B | NAM North America | 761X203 | Generator | 154268 | Minor Inspection | 502903 | 2026-01-19 | 2026-02-07
7FH2B | MENA | 761X043 | Generator | 154327 | Minor Inspection | 534744 | 2026-11-12 | 2026-12-08
7FH2B | MENA | 761X042 | Generator | 154329 | Minor Inspection | 534745 | 2026-10-19 | 2026-11-14
7FH2B | MENA | 761X044 | Generator | 154331 | Minor Inspection | 534746 | 2026-10-01 | 2026-10-27
7FH2B | NAM North America | 761X045 | Generator | 158727 | Minor Inspection | 538013 | 2028-03-11 | 2028-04-04
7FH2B | NAM North America | 761X046 | Generator | 158729 | Minor Inspection | 538014 | 2028-10-07 | 2028-10-31
7FH2B | NAM North America | 761X047 | Generator | 158731 | Minor Inspection | 538015 | 2029-03-31 | 2029-04-24
7FH2B | NAM North America | 761X034 | Generator | 159161 | Major Inspection (Robotic) | 538244 | 2027-03-13 | 2027-04-12
7FH2B | MENA | GG10475 | Generator | 159239 | Major Inspection (Robotic) | 538301 | 2026-01-08 | 2026-02-19
7FH2B | MENA | GG10474 | Generator | 159240 | Minor Inspection | 538302 | 2027-03-14 | 2027-03-28
7FH2B | MENA | GG10475 | Generator | 159241 | Minor Inspection | 538303 | 2028-04-30 | 2028-05-14
7FH2B | Latin America | 761X100 | Generator | 162527 | Major Inspection (Robotic) | 540873 | 2028-03-18 | 2028-04-18
7FH2B | Latin America | 761X101 | Generator | 162528 | Major Inspection (Robotic) | 540874 | 2028-10-21 | 2028-11-21
7FH2B | Latin America | 761X102 | Generator | 162529 | Major Inspection (Robotic) | 540875 | 2029-11-18 | 2029-11-18
7FH2B | Latin America | 761X100 | Generator | 162530 | Minor Inspection | 540876 | 2030-07-01 | 2030-07-29
7FH2B | Latin America | 761X101 | Generator | 162533 | Minor Inspection | 540877 | 2030-10-27 | 2030-11-24
7FH2B | NAM North America | 761X202 | Generator | 162737 | Minor Inspection | 541000 | 2027-01-26 | 2027-02-09
7FH2B | NAM North America | 761X203 | Generator | 162739 | Major Inspection (Robotic) | 541001 | 2029-01-08 | 2029-02-05
7FH2B | MENA | 761X041 | Generator | 162924 | Major Inspection (Robotic) | 541098 | 2029-10-26 | 2029-11-23
7FH2B | MENA | 761X044 | Generator | 162926 | Major Inspection (Robotic) | 541099 | 2030-11-09 | 2030-12-07
7FH2B | MENA | 761X204 | Generator | 162930 | Major Inspection (Robotic) | 541100 | 2028-12-10 | 2029-01-07
7FH2B | MENA | 761X205 | Generator | 162931 | Major Inspection (Robotic) | 541101 | 2028-12-22 | 2029-01-19
7FH2B | MENA | 761X206 | Generator | 162933 | Major Inspection (Robotic) | 541102 | 2029-10-01 | 2029-10-29
7FH2B | MENA | 761X207 | Generator | 162935 | Major Inspection (Robotic) | 541103 | 2029-10-26 | 2029-11-23
7FH2B | MENA | 761X208 | Generator | 162937 | Major Inspection (Robotic) | 541104 | 2030-10-23 | 2030-11-20
7FH2B | MENA | 761X209 | Generator | 162939 | Major Inspection (Robotic) | 541105 | 2030-10-01 | 2030-10-29
7FH2B | NAM North America | 761X038 | Generator | 162982 | Minor Inspection | 541139 | 2026-09-21 | 2026-10-05
7FH2B | NAM North America | 761X011 | Generator | 163050 | Major Inspection (Robotic) | 541178 | 2028-11-30 | 2028-12-28
7FH2B | NAM North America | GG10451 | Generator | 164474 | Major Inspection (Robotic) | 541705 | 2026-03-08 | 2026-04-24
7FH2B | NAM North America | 761X002 | Generator | 165128 | Minor Inspection | 542825 | 2029-02-01 | 2029-03-01
7FH2B | Latin America | 761X004 | Generator | 168154 | Minor Inspection | 545047 | 2027-01-16 | 2027-01-30
7FH2B | Latin America | 761X005 | Generator | 168155 | Minor Inspection | 545048 | 2027-01-16 | 2027-01-30
7FH2B | MENA | 761X043 | Generator | 168168 | Major Inspection (Robotic) | 545052 | 2029-12-25 | 2030-01-22
7FH2B | NAM North America | GG10450 | Generator | 168911 | Major Inspection (Robotic) | 545656 | 2026-10-04 | 2026-11-02
7FH2B | MENA | GG10474 | Generator | 169809 | Major Inspection (Robotic) | 546214 | 2027-01-05 | 2027-02-08
7FH2B | NAM North America | GG10458 | Generator | 172648 | Major Inspection (Robotic) | 542041 | 2027-05-10 | 2027-06-09
7FH2B | NAM North America | GG10457 | Generator | 172650 | Major Inspection (Robotic) | 541031 | 2027-05-03 | 2027-06-02
7FH2B | Asia | 761X012 | Generator | 173784 | Major Inspection (Rotor Out) | 548514 | 2027-04-30 | 2027-06-01
7FH2B | NAM North America | 761X037 | Generator | 175584 | Major Inspection (Robotic) | 549702 | 2030-10-07 | 2030-11-04
7FH2B | NAM North America | 761X202 | Generator | 175810 | Major Inspection (Robotic) | 549872 | 2029-06-12 | 2029-07-10
7FH2B | NAM North America | 761X038 | Generator | 175979 | Major Inspection (Robotic) | 549954 | 2030-05-01 | 2030-05-29
7FH2B | NAM North America | 761X009 | Generator | 176134 | Major Inspection (Robotic) | 550066 | 2029-11-30 | 2029-12-28
7FH2B | NAM North America | 761X010 | Generator | 176136 | Major Inspection (Robotic) | 550067 | 2030-11-30 | 2030-12-28
7FH2B | NAM North America | GG10492 | Generator | 184580 | Minor Inspection | 553529 | 2027-03-15 | 2027-03-31
7FH2B | Asia | 761X013 | Generator | 186913 | Minor Inspection | 556739 | 2030-04-01 | 2030-04-25
7FH2B | NAM North America | GG10493 | Generator | 187242 | Minor Inspection | 553530 | 2027-10-31 | 2027-11-14
7FH2B | MENA | 761X040 | Generator | 190814 | Major Inspection (Robotic) | 559456 | 2028-10-01 | 2028-10-29
7FH2B | MENA | 761X039 | Generator | 190815 | Major Inspection (Robotic) | 559457 | 2028-10-01 | 2028-10-29
7FH2B | MENA | 761X042 | Generator | 190883 | Major Inspection (Robotic) | 559486 | 2030-10-01 | 2030-10-29
7H2-DV | NAM North America | 336X222 | Generator | 165963 | Major Inspection (Robotic) | 543318 | 2028-02-22 | 2028-03-21
7H2-DV | NAM North America | 335X276 | Generator | 166363 | Minor Inspection | 543563 | 2027-03-01 | 2027-03-29
7H2-DV | NAM North America | 335X281 | Generator | 166365 | Minor Inspection | 543564 | 2027-03-01 | 2027-03-16
7H2-DV | NAM North America | 335X287 | Generator | 166367 | Minor Inspection | 543565 | 2027-09-18 | 2027-10-02
7H2-DV | NAM North America | 335X277 | Generator | 166368 | Minor Inspection | 543566 | 2028-01-24 | 2028-02-07
7H2-DV | NAM North America | 335X271 | Generator | 166438 | Minor Inspection | 543612 | 2027-08-31 | 2027-09-28
7H2-DV | NAM North America | 335X271 | Generator | 166441 | Major Inspection (Robotic) | 543614 | 2030-12-23 | 2031-01-20
7H2-DV | NAM North America | 335X272 | Generator | 179940 | Minor Inspection | 552297 | 2028-07-05 | 2028-08-02
7H2-DV | NAM North America | 335X275 | Generator | 182832 | Major Inspection (Rotor Out) | 553980 | 2027-01-13 | 2027-04-19
7H2-DV | NAM North America | 335X273 | Generator | 184646 | Minor Inspection | 508367 | 2028-05-15 | 2028-06-28
7H2-IV | NAM North America | 335X293 | Generator | 166437 | Major Inspection (Robotic) | 541668 | 2026-02-05 | 2026-06-25
7H2-IV | NAM North America | 335X293 | Generator | 166439 | Minor Inspection | 543613 | 2030-06-01 | 2030-06-29
7HA.01 | Latin America | 299570 | Gas Turbine | 162612 | Hot Gas Path Inspection (HGPI) | 554362 | 2028-01-28 | 2028-02-11
7HA.01 | Latin America | 299571 | Gas Turbine | 162614 | Hot Gas Path Inspection (HGPI) | 551501 | 2028-01-02 | 2028-01-16
7HA.01 | NAM North America | 299487 | Gas Turbine | 162700 | Hot Gas Path Inspection (HGPI) | 540972 | 2028-10-14 | 2028-11-12
7HA.01 | NAM North America | 299488 | Gas Turbine | 162701 | Hot Gas Path Inspection (HGPI) | 549774 | 2029-04-14 | 2029-05-09
7HA.01 | Asia | 299239 | Gas Turbine | 167934 | Hot Gas Path Inspection (HGPI) | 544863 | 2027-09-04 | 2027-11-12
7HA.01 | Asia | 299240 | Gas Turbine | 167935 | Major Inspection (MI) | 544864 | 2027-09-04 | 2027-11-16
7HA.01 | Asia | 299241 | Gas Turbine | 167936 | Hot Gas Path Inspection (HGPI) | 544865 | 2027-09-04 | 2027-11-12
7HA.01 | MENA | 299704 | Gas Turbine | 179444 | Hot Gas Path Inspection (HGPI) | 552012 | 2029-09-30 | 2029-10-14
7HA.01 | Asia | 299240 | Gas Turbine | 182550 | Major Inspection (MI) | 553782 | 2027-09-03 | 2027-10-12
7HA.01 | Asia | 299241 | Gas Turbine | 182551 | Hot Gas Path Inspection (HGPI) | 553783 | 2027-10-13 | 2027-11-16
7HA.01 | Asia | 299239 | Gas Turbine | 182554 | Hot Gas Path Inspection (HGPI) | 553784 | 2027-11-17 | 2027-12-21
7HA.01 | Asia | 299242 | Gas Turbine | 185440 | Hot Gas Path Inspection (HGPI) | 555741 | 2028-09-01 | 2028-10-10
7HA.01 | Asia | 299242 | Gas Turbine | 187500 | Large Call-Out | 557187 | 2026-07-13 | 2026-08-03
7HA.01 | Latin America | 299570 | Gas Turbine | 193219 | Large Call-Out | 561017 | 2027-01-08 | 2027-01-15
7HA.02 | NAM North America | 299469 | Gas Turbine | 106580 | Major Inspection (MI) | 502953 | 2026-09-12 | 2026-12-08
7HA.02 | NAM North America | 299422 | Gas Turbine | 112215 | Hot Gas Path Inspection (HGPI) |  | 2028-04-26 | 2028-05-10
7HA.02 | NAM North America | 299421 | Gas Turbine | 113454 | Hot Gas Path Inspection (HGPI) |  | 2027-10-01 | 2027-10-15
7HA.02 | NAM North America | 299421 | Gas Turbine | 119771 | Hot Gas Path Inspection (HGPI) |  | 2027-11-29 | 2027-12-13
7HA.02 | NAM North America | 299422 | Gas Turbine | 123298 | Hot Gas Path Inspection (HGPI) |  | 2028-11-27 | 2028-12-21
7HA.02 | NAM North America | 299435 | Gas Turbine | 139519 | Borescope Inspection (BI) | 525794 | 2026-03-09 | 2026-03-19
7HA.02 | NAM North America | 299421 | Gas Turbine | 140306 | Borescope Inspection (BI) | 526215 | 2026-03-15 | 2026-03-25
7HA.02 | NAM North America | 299421 | Gas Turbine | 140307 | Borescope Inspection (BI) | 526216 | 2026-12-01 | 2026-12-11
7HA.02 | NAM North America | 299422 | Gas Turbine | 140314 | Borescope Inspection (BI) | 526222 | 2026-03-15 | 2026-03-25
7HA.02 | NAM North America | 299422 | Gas Turbine | 140315 | Borescope Inspection (BI) | 526223 | 2026-12-01 | 2026-12-11
7HA.02 | NAM North America | 299422 | Gas Turbine | 140316 | Borescope Inspection (BI) | 526224 | 2027-03-08 | 2027-03-19
7HA.02 | NAM North America | 299422 | Gas Turbine | 140317 | Borescope Inspection (BI) | 526225 | 2027-11-30 | 2027-12-10
7HA.02 | NAM North America | 299423 | Gas Turbine | 140330 | Borescope Inspection (BI) | 526236 | 2026-04-10 | 2026-04-17
7HA.02 | NAM North America | 299423 | Gas Turbine | 140331 | Borescope Inspection (BI) | 526237 | 2026-11-09 | 2026-11-22
7HA.02 | NAM North America | 299423 | Gas Turbine | 140333 | Borescope Inspection (BI) | 526238 | 2027-04-23 | 2027-04-30
7HA.02 | NAM North America | 299424 | Gas Turbine | 140339 | Large Call-Out | 526245 | 2026-04-04 | 2026-04-20
7HA.02 | NAM North America | 299424 | Gas Turbine | 140340 | Borescope Inspection (BI) | 526246 | 2026-11-09 | 2026-11-22
7HA.02 | NAM North America | 299424 | Gas Turbine | 140341 | Borescope Inspection (BI) | 526247 | 2027-04-18 | 2027-04-25
7HA.02 | NAM North America | 299596 | Gas Turbine | 140973 | Major Inspection (MI) | 526443 | 2026-10-20 | 2026-12-07
7HA.02 | NAM North America | 299470 | Gas Turbine | 144964 | Major Inspection (MI) | 541219 | 2027-03-01 | 2027-03-30
7HA.02 | NAM North America | 299516 | Gas Turbine | 146527 | Major Inspection (MI) | 531637 | 2027-03-20 | 2027-05-18
7HA.02 | Latin America | 299590 | Gas Turbine | 146601 | Hot Gas Path Inspection (HGPI) | 541025 | 2027-02-12 | 2027-03-15
7HA.02 | Latin America | 299589 | Gas Turbine | 146602 | Hot Gas Path Inspection (HGPI) | 541024 | 2027-01-16 | 2027-02-10
7HA.02 | Latin America | 299548 | Gas Turbine | 146636 | Hot Gas Path Inspection (HGPI) |  | 2030-11-04 | 2030-12-04
7HA.02 | Latin America | 299562 | Gas Turbine | 146703 | Major Inspection (MI) | 534721 | 2026-01-10 | 2026-02-16
7HA.02 | Latin America | 299561 | Gas Turbine | 146705 | Major Inspection (MI) | 534720 | 2026-01-10 | 2026-02-11
7HA.02 | NAM North America | 299637 | Gas Turbine | 146707 | Hot Gas Path Inspection (HGPI) | 547352 | 2027-02-20 | 2027-03-20
7HA.02 | NAM North America | 299638 | Gas Turbine | 146708 | Hot Gas Path Inspection (HGPI) | 541211 | 2027-10-24 | 2027-11-23
7HA.02 | NAM North America | 299595 | Gas Turbine | 146711 | Hot Gas Path Inspection (HGPI) | 535056 | 2026-04-01 | 2026-05-09
7HA.02 | Asia | 299664 | Gas Turbine | 146716 | Hot Gas Path Inspection (HGPI) | 544744 | 2027-06-01 | 2027-06-26
7HA.02 | Asia | 299603 | Gas Turbine | 146724 | Major Inspection (MI) | 531472 | 2027-10-01 | 2027-11-09
7HA.02 | NAM North America | 299484 | Gas Turbine | 146759 | Major Inspection (MI) | 531749 | 2026-03-16 | 2026-05-22
7HA.02 | NAM North America | 299483 | Gas Turbine | 146763 | Hot Gas Path Inspection (HGPI) | 549435 | 2028-03-06 | 2028-03-31
7HA.02 | NAM North America | 299484 | Gas Turbine | 146764 | Hot Gas Path Inspection (HGPI) | 550719 | 2029-03-19 | 2029-04-13
7HA.02 | NAM North America | 299647 | Gas Turbine | 146774 | Hot Gas Path Inspection (HGPI) | 530763 | 2027-09-25 | 2027-10-24
7HA.02 | NAM North America | 299648 | Gas Turbine | 146775 | Hot Gas Path Inspection (HGPI) | 530764 | 2027-10-23 | 2027-11-21
7HA.02 | NAM North America | 299614 | Gas Turbine | 146813 | Hot Gas Path Inspection (HGPI) | 544928 | 2027-09-01 | 2027-09-30
7HA.02 | NAM North America | 299615 | Gas Turbine | 146814 | Hot Gas Path Inspection (HGPI) | 549884 | 2026-10-01 | 2026-10-30
7HA.02 | NAM North America | 299616 | Gas Turbine | 146817 | Hot Gas Path Inspection (HGPI) | 549885 | 2027-04-01 | 2027-05-01
7HA.02 | NAM North America | 299621 | Gas Turbine | 146849 | Hot Gas Path Inspection (HGPI) | 534219 | 2027-03-08 | 2027-04-08
7HA.02 | NAM North America | 299622 | Gas Turbine | 146851 | Hot Gas Path Inspection (HGPI) | 541307 | 2027-03-08 | 2027-04-08
7HA.02 | NAM North America | 299602 | Gas Turbine | 146856 | Major Inspection (MI) | 541174 | 2029-05-31 | 2029-06-28
7HA.02 | NAM North America | 299541 | Gas Turbine | 146863 | Major Inspection (MI) | 541180 | 2027-09-22 | 2027-10-20
7HA.02 | NAM North America | 299434 | Gas Turbine | 146881 | Major Inspection (MI) | 532319 | 2026-10-03 | 2026-11-06
7HA.02 | NAM North America | 299597 | Gas Turbine | 146892 | Hot Gas Path Inspection (HGPI) | 531779 | 2026-02-16 | 2026-03-24
7HA.02 | NAM North America | 299598 | Gas Turbine | 146893 | Hot Gas Path Inspection (HGPI) | 539683 | 2026-02-16 | 2026-03-28
7HA.02 | NAM North America | 299597 | Gas Turbine | 146894 | Major Inspection (MI) |  | 2029-01-27 | 2029-02-24
7HA.02 | NAM North America | 299601 | Gas Turbine | 146897 | Hot Gas Path Inspection (HGPI) | 531581 | 2026-03-09 | 2026-04-10
7HA.02 | Asia | 299702 | Gas Turbine | 146908 | Hot Gas Path Inspection (HGPI) | 561524 | 2030-07-27 | 2030-08-10
7HA.02 | NAM North America | 299526 | Gas Turbine | 146925 | Major Inspection (MI) | 544849 | 2028-04-03 | 2028-05-19
7HA.02 | NAM North America | 299527 | Gas Turbine | 146926 | Major Inspection (MI) | 544850 | 2028-04-03 | 2028-05-19
7HA.02 | NAM North America | 299435 | Gas Turbine | 150822 | Hot Gas Path Inspection (HGPI) | 532313 | 2029-10-03 | 2030-11-04
7HA.02 | Latin America | 299547 | Gas Turbine | 153673 | Borescope Inspection (BI) | 534380 | 2026-02-28 | 2026-03-01
7HA.02 | Latin America | 299548 | Gas Turbine | 153674 | Borescope Inspection (BI) | 534381 | 2026-03-04 | 2026-03-05
7HA.02 | Latin America | 299549 | Gas Turbine | 153675 | Borescope Inspection (BI) | 534382 | 2026-03-02 | 2026-03-03
7HA.02 | Latin America | 299547 | Gas Turbine | 153899 | Borescope Inspection (BI) | 534554 | 2027-04-12 | 2027-04-13
7HA.02 | Latin America | 299548 | Gas Turbine | 153900 | Borescope Inspection (BI) | 534555 | 2027-04-07 | 2027-04-08
7HA.02 | Latin America | 299549 | Gas Turbine | 153901 | Borescope Inspection (BI) | 534556 | 2027-04-16 | 2027-04-17
7HA.02 | NAM North America | 299637 | Gas Turbine | 154368 | Borescope Inspection (BI) | 534771 | 2026-03-14 | 2026-03-31
7HA.02 | NAM North America | 299637 | Gas Turbine | 154369 | Borescope Inspection (BI) | 534772 | 2026-11-14 | 2026-11-22
7HA.02 | NAM North America | 299638 | Gas Turbine | 154377 | Borescope Inspection (BI) | 534780 | 2026-03-14 | 2026-03-31
7HA.02 | NAM North America | 299638 | Gas Turbine | 154378 | Borescope Inspection (BI) | 534781 | 2026-11-16 | 2026-11-22
7HA.02 | Latin America | 299721 | Gas Turbine | 154755 | Hot Gas Path Inspection (HGPI) | 538252 | 2030-05-14 | 2030-05-28
7HA.02 | NAM North America | 299596 | Gas Turbine | 156570 | Borescope Inspection (BI) | 536322 | 2026-03-19 | 2026-04-05
7HA.02 | Asia | 299603 | Gas Turbine | 158583 | Hot Gas Path Inspection (HGPI) | 537923 | 2030-10-01 | 2030-10-14
7HA.02 | Latin America | 299705 | Gas Turbine | 159175 | Hot Gas Path Inspection (HGPI) | 538257 | 2030-05-14 | 2030-05-28
7HA.02 | Asia | 299603 | Gas Turbine | 160183 | Borescope Inspection (BI) | 538879 | 2026-10-21 | 2026-10-27
7HA.02 | Asia | 299664 | Gas Turbine | 160254 | Borescope Inspection (BI) | 539045 | 2026-04-15 | 2026-04-15
7HA.02 | Asia | 299459 | Gas Turbine | 160359 | Borescope Inspection (BI) | 539042 | 2026-04-10 | 2026-04-12
7HA.02 | NAM North America | 299434 | Gas Turbine | 162353 | Borescope Inspection (BI) | 540742 | 2026-04-09 | 2026-04-18
7HA.02 | NAM North America | 299434 | Gas Turbine | 162354 | Borescope Inspection (BI) | 540744 | 2027-03-02 | 2027-03-11
7HA.02 | NAM North America | 299434 | Gas Turbine | 162355 | Borescope Inspection (BI) | 540745 | 2027-10-11 | 2027-10-21
7HA.02 | NAM North America | 299435 | Gas Turbine | 162364 | Borescope Inspection (BI) | 540749 | 2026-04-10 | 2026-04-18
7HA.02 | NAM North America | 299435 | Gas Turbine | 162365 | Borescope Inspection (BI) | 540750 | 2026-10-11 | 2026-10-21
7HA.02 | NAM North America | 299435 | Gas Turbine | 162366 | Borescope Inspection (BI) | 540751 | 2027-03-08 | 2027-03-15
7HA.02 | NAM North America | 299435 | Gas Turbine | 162367 | Borescope Inspection (BI) | 540752 | 2027-10-11 | 2027-10-21
7HA.02 | Asia | 299680 | Gas Turbine | 162492 | Hot Gas Path Inspection (HGPI) | 550454 | 2028-09-22 | 2028-10-06
7HA.02 | Asia | 299681 | Gas Turbine | 162493 | Hot Gas Path Inspection (HGPI) | 550453 | 2028-09-23 | 2028-10-07
7HA.02 | Asia | 299459 | Gas Turbine | 162508 | Hot Gas Path Inspection (HGPI) | 544271 | 2029-01-15 | 2029-02-20
7HA.02 | Asia | 299460 | Gas Turbine | 162509 | Major Inspection (MI) | 544269 | 2029-07-15 | 2029-09-04
7HA.02 | Latin America | 299574 | Gas Turbine | 162582 | Major Inspection (MI) | 540913 | 2028-11-04 | 2028-12-07
7HA.02 | Latin America | 299575 | Gas Turbine | 162584 | Major Inspection (MI) | 544935 | 2028-11-04 | 2028-12-07
7HA.02 | Latin America | 299562 | Gas Turbine | 162590 | Hot Gas Path Inspection (HGPI) | 540916 | 2029-01-10 | 2029-02-02
7HA.02 | Latin America | 299561 | Gas Turbine | 162592 | Hot Gas Path Inspection (HGPI) | 540917 | 2029-01-10 | 2029-02-02
7HA.02 | NAM North America | 299598 | Gas Turbine | 162729 | Major Inspection (MI) |  | 2029-01-09 | 2029-02-06
7HA.02 | NAM North America | 299423 | Gas Turbine | 163038 | Hot Gas Path Inspection (HGPI) | 541207 | 2028-04-18 | 2028-06-04
7HA.02 | NAM North America | 299424 | Gas Turbine | 163039 | Hot Gas Path Inspection (HGPI) | 541206 | 2028-04-18 | 2028-06-04
7HA.02 | NAM North America | 299601 | Gas Turbine | 163047 | Major Inspection (MI) | 541177 | 2030-05-14 | 2030-06-11
7HA.02 | NAM North America | 299604 | Gas Turbine | 163106 | Major Inspection (MI) | 541221 | 2029-03-01 | 2029-05-04
7HA.02 | NAM North America | 299605 | Gas Turbine | 163109 | Major Inspection (MI) | 562231 | 2029-09-01 | 2029-10-26
7HA.02 | NAM North America | 299621 | Gas Turbine | 163211 | Major Inspection (MI) | 541308 | 2030-12-25 | 2031-01-22
7HA.02 | NAM North America | 299472 | Gas Turbine | 163499 | Major Inspection (MI) | 541548 | 2026-03-03 | 2026-05-08
7HA.02 | NAM North America | 299637 | Gas Turbine | 171969 | Hot Gas Path Inspection (HGPI) | 547351 | 2026-10-12 | 2026-11-04
7HA.02 | NAM North America | 299516 | Gas Turbine | 173995 | Large Call-Out | 548660 | 2026-04-05 | 2026-04-12
7HA.02 | Latin America | 299589 | Gas Turbine | 175965 | Major Inspection (MI) | 549947 | 2029-05-13 | 2029-06-10
7HA.02 | Latin America | 299590 | Gas Turbine | 175968 | Major Inspection (MI) | 549948 | 2030-01-16 | 2030-02-13
7HA.02 | NAM North America | 299638 | Gas Turbine | 175986 | Major Inspection (MI) | 549961 | 2030-11-17 | 2030-12-15
7HA.02 | NAM North America | 299485 | Gas Turbine | 176140 | Hot Gas Path Inspection (HGPI) | 555752 | 2028-09-11 | 2028-10-06
7HA.02 | NAM North America | 299483 | Gas Turbine | 176143 | Major Inspection (MI) | 561797 | 2030-09-02 | 2030-11-27
7HA.02 | Latin America | 299561 | Gas Turbine | 176241 | Large Call-Out | 550112 | 2026-01-10 | 2026-02-12
7HA.02 | Latin America | 299562 | Gas Turbine | 176244 | Large Call-Out | 550115 | 2026-01-10 | 2026-02-12
7HA.02 | Asia | 299603 | Gas Turbine | 178558 | Stand Alone Small Upgrade | 551504 | 2026-02-01 | 2026-02-28
7HA.02 | Asia | 299603 | Gas Turbine | 178559 | Stand Alone Small Upgrade | 551505 | 2026-02-01 | 2026-02-28
7HA.02 | NAM North America | 299647 | Gas Turbine | 184866 | Large Call-Out | 555332 | 2026-04-22 | 2026-05-01
7HA.02 | NAM North America | 299648 | Gas Turbine | 184868 | Large Call-Out | 555334 | 2026-04-28 | 2026-05-07
7HA.02 | NAM North America | 299728 | Gas Turbine | 185101 | Large Call-Out | 555491 | 2026-01-12 | 2026-02-11
7HA.02 | NAM North America | 299595 | Gas Turbine | 186435 | Stand Alone Small Upgrade | 556467 | 2026-10-18 | 2026-11-06
7HA.02 | NAM North America | 299421 | Gas Turbine | 190680 | Hot Gas Path Inspection (HGPI) | 559335 | 2027-11-29 | 2028-01-12
7HA.02 | Asia | 299664 | Gas Turbine | 193398 | Large Call-Out | 561193 | 2026-05-25 | 2026-06-08
7HA.02 | NAM North America | 299728 | Gas Turbine | 193743 | Large Call-Out | 561475 | 2026-07-13 | 2026-07-31
7HA.02 | NAM North America | 299601 | Gas Turbine | 194209 | Major Inspection (MI) | 561879 | 2030-05-14 | 2030-06-11
7HA.02 | NAM North America | 299435 | Gas Turbine | 194535 | Large Call-Out | 562164 | 2026-05-23 | 2026-07-04
7HA.02 | NAM North America | 299728 | Gas Turbine | 194905 | Hot Gas Path Inspection (HGPI) | 562492 | 2030-09-02 | 2030-09-16
7HA.02 | NAM North America | 299483 | Gas Turbine | 195286 | Large Call-Out | 562772 | 2026-06-19 | 2026-08-07
7HA.03 | NAM North America | 299698 | Gas Turbine | 151265 | Hot Gas Path Inspection (HGPI) | 558691 | 2030-02-18 | 2030-03-06
7HA.03 | MENA | 299754 | Gas Turbine | 169223 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299753 | Gas Turbine | 169227 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299752 | Gas Turbine | 169231 | Combustion Inspection (CI) |  | 2028-10-01 | 2028-10-08
7HA.03 | MENA | 299752 | Gas Turbine | 169232 | Hot Gas Path Inspection (HGPI) |  | 2030-04-30 | 2030-05-14
7HA.03 | MENA | 299752 | Gas Turbine | 169544 | Combustion Inspection (CI) |  | 2028-10-01 | 2028-10-08
7HA.03 | MENA | 299752 | Gas Turbine | 169545 | Hot Gas Path Inspection (HGPI) | 546087 | 2030-04-30 | 2030-05-14
7HA.03 | MENA | 299753 | Gas Turbine | 169550 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299754 | Gas Turbine | 169556 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299745 | Gas Turbine | 169612 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299744 | Gas Turbine | 169618 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299743 | Gas Turbine | 169624 | Combustion Inspection (CI) |  | 2028-10-01 | 2028-10-08
7HA.03 | MENA | 299743 | Gas Turbine | 169625 | Hot Gas Path Inspection (HGPI) | 546127 | 2030-04-30 | 2030-05-14
7HA.03 | MENA | 299752 | Gas Turbine | 169657 | Combustion Inspection (CI) |  | 2028-10-01 | 2028-10-08
7HA.03 | MENA | 299752 | Gas Turbine | 169658 | Hot Gas Path Inspection (HGPI) | 546140 | 2030-04-30 | 2030-05-14
7HA.03 | MENA | 299753 | Gas Turbine | 169663 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | MENA | 299754 | Gas Turbine | 169669 | Combustion Inspection (CI) |  | 2029-04-30 | 2029-05-07
7HA.03 | NAM North America | 299720 | Gas Turbine | 184998 | Hot Gas Path Inspection (HGPI) | 555423 | 2028-10-01 | 2028-11-06
7HA.03 | NAM North America | 299764 | Gas Turbine | 185221 | Hot Gas Path Inspection (HGPI) | 555557 | 2028-11-01 | 2028-11-30
7HA.03 | NAM North America | 299719 | Gas Turbine | 185222 | Hot Gas Path Inspection (HGPI) | 555558 | 2028-11-01 | 2028-11-30
7HA.03 | MENA | 299771 | Gas Turbine | 185936 | Combustion Inspection (CI) |  | 2030-01-29 | 2030-02-05
7HA.03 | MENA | 299772 | Gas Turbine | 185940 | Combustion Inspection (CI) |  | 2030-04-30 | 2030-05-07
7HA.03 | MENA | 299773 | Gas Turbine | 185944 | Combustion Inspection (CI) |  | 2030-04-30 | 2030-05-07
7HA.03 | MENA | 299768 | Gas Turbine | 189781 | Combustion Inspection (CI) |  | 2030-10-01 | 2030-10-08
7HA.03 | MENA | 299769 | Gas Turbine | 189784 | Combustion Inspection (CI) |  | 2030-10-01 | 2030-10-08
7HA.03 | MENA | 299770 | Gas Turbine | 189787 | Combustion Inspection (CI) |  | 2030-10-01 | 2030-10-08
7HA.03 | NAM North America | 299698 | Gas Turbine | 195680 | Hot Gas Path Inspection (HGPI) | 559446 | 2030-02-18 | 2030-03-17
9A4 | NAM North America | 290T504 | Generator | 172380 | Major Inspection (Robotic) | 547697 | 2027-02-04 | 2027-04-13
9A4 | NAM North America | 290T506 | Generator | 172381 | Major Inspection (Stator Rewind) | 547698 | 2026-02-19 | 2026-03-30
9A4 | NAM North America | 290T504 | Generator | 172382 | Major Inspection (Stator Rewind) | 547699 | 2027-09-28 | 2027-10-31
9A4 | NAM North America | 290T506 | Generator | 173274 | Major Inspection (Robotic) | 548209 | 2027-08-07 | 2027-10-16
9A4 | NAM North America | 290T505 | Generator | 173301 | Major Inspection (Robotic) | 548226 | 2028-02-05 | 2028-04-15
9A4 | NAM North America | 290T545 | Generator | 174918 | Major Inspection (Robotic) | 537834 | 2026-03-16 | 2026-05-07
9A4 | NAM North America | 290T540 | Generator | 181545 | Major Inspection (Stator Rewind) | 557385 | 2026-03-14 | 2026-05-02
9A4 | NAM North America | 290T566 | Generator | 182022 | Major Inspection (Robotic) | 553494 | 2027-03-13 | 2027-04-12
9A4 | NAM North America | 290T566 | Generator | 182662 | Major Inspection (Robotic) | 553408 | 2027-03-13 | 2027-04-12
9A4 | NAM North America | 290T473 | Generator | 183691 | Major Inspection (Field Rewind) | 554529 | 2027-10-02 | 2027-10-23
9A4 | NAM North America | 290T475 | Generator | 184402 | Major Inspection (Robotic) | 555023 | 2027-04-03 | 2027-05-13
9A4 | NAM North America | 290T476 | Generator | 184404 | Major Inspection (Robotic) | 555025 | 2027-04-01 | 2027-04-19
9A4 | NAM North America | 290T473 | Generator | 191098 | Minor Inspection | 559702 | 2026-04-11 | 2026-05-12
9A4 | NAM North America | 290T570 | Generator | 193825 | Major Inspection (Stator Rewind) | 561554 | 2027-03-15 | 2027-05-07
9A4 | NAM North America | 290T569 | Generator | 193826 | Major Inspection (Stator Rewind) | 561555 | 2028-03-10 | 2028-05-01
9A4 | NAM North America | 290T539 | Generator | 193853 | Major Inspection (Stator Rewind) | 561579 | 2027-10-01 | 2027-12-04
9A4 | NAM North America | 290T541 | Generator | 193854 | Major Inspection (Stator Rewind) | 561580 | 2028-10-01 | 2028-12-04
9A4 | NAM North America | 290T570 | Generator | 195057 | Major Inspection (Rotor Out) | 562620 | 2027-04-01 | 2027-05-20
9A4+ | Latin America | 290T923 | Generator | 184503 | Minor Inspection |  | 2028-10-02 | 2028-10-15
9A5 | Europe | 290T698NB | Generator | 116450 | Major Inspection (Rotor Out) | 516020 | 2028-02-08 | 2028-03-26
9A5 | MENA | 954X191 | Generator | 127187 | Minor Inspection | 517944 | 2026-01-05 | 2026-02-03
9A5 | MENA | 954X190 | Generator | 127189 | Major Inspection (Rotor Out) | 517945 | 2026-02-02 | 2026-03-19
9A5 | MENA | 954X191 | Generator | 137066 | Major Inspection (Rotor Out) | 524420 | 2027-10-03 | 2027-11-02
9A5 | MENA | 954X175 | Generator | 138251 | Minor Inspection | 501264 | 2026-04-10 | 2026-04-27
9A5 | MENA | 954X176 | Generator | 138252 | Minor Inspection | 525019 | 2026-04-12 | 2026-04-27
9A5 | MENA | 954X187 | Generator | 141559 | Major Inspection (Robotic) | 502369 | 2026-11-06 | 2026-12-11
9A5 | MENA | 954X188 | Generator | 141560 | Major Inspection (Robotic) | 526855 | 2027-01-18 | 2027-02-22
9A5 | MENA | GG10484 | Generator | 141561 | Major Inspection (Robotic) | 525990 | 2026-10-01 | 2026-11-05
9A5 | MENA | 954X189 | Generator | 141562 | Major Inspection (Robotic) | 502368 | 2026-12-12 | 2027-01-16
9A5 | MENA | 954X160 | Generator | 144305 | Minor Inspection | 525924 | 2028-10-01 | 2028-10-27
9A5 | MENA | 954X161 | Generator | 144306 | Minor Inspection | 525922 | 2028-10-28 | 2028-11-23
9A5 | MENA | 954X162 | Generator | 144307 | Minor Inspection | 525919 | 2028-11-23 | 2028-12-19
9A5 | MENA | 954X204 | Generator | 150537 | Major Inspection (Robotic) | 532205 | 2028-07-02 | 2028-08-01
9A5 | MENA | GG10485 | Generator | 150538 | Major Inspection (Robotic) | 532206 | 2028-03-31 | 2028-04-30
9A5 | MENA | 954X205 | Generator | 150539 | Major Inspection (Robotic) | 532207 | 2028-05-01 | 2028-05-31
9A5 | MENA | 954X206 | Generator | 151368 | Major Inspection (Robotic) | 532586 | 2028-06-01 | 2028-07-01
9A5 | MENA | 954X111 | Generator | 159012 | Major Inspection (Robotic) | 538165 | 2028-01-29 | 2028-02-26
9A5 | Asia | 954X087 | Generator | 165704 | Major Inspection (Robotic) | 543155 | 2029-12-24 | 2030-01-21
9A5 | Asia | 954X088 | Generator | 165706 | Major Inspection (Robotic) | 543156 | 2030-07-25 | 2030-08-22
9A5 | MENA | GG10549 | Generator | 166326 | Major Inspection (Rotor Out) | 501995 | 2029-04-01 | 2029-04-29
9A5 | MENA | GG10548 | Generator | 166327 | Major Inspection (Robotic) | 501996 | 2028-03-13 | 2028-04-12
9A5 | MENA | 954X500 | Generator | 166677 | Minor Inspection | 543794 | 2027-02-28 | 2027-03-26
9A5 | MENA | 954X501 | Generator | 166678 | Minor Inspection | 543795 | 2027-02-01 | 2027-02-27
9A5 | MENA | 954X110 | Generator | 168101 | Major Inspection (Robotic) | 522451 | 2028-12-01 | 2028-12-31
9A5 | MENA | 954X109 | Generator | 168102 | Major Inspection (Robotic) | 522449 | 2028-12-01 | 2028-12-31
9A5 | Asia | 954X003 | Generator | 170459 | Major Inspection (Rotor Out) | 546404 | 2026-12-10 | 2027-01-12
9A5 | Europe | 954X041 | Generator | 173553 | Major Inspection (Stator Rewind) | 548949 | 2027-09-06 | 2027-11-08
9A5 | Asia | 954X087 | Generator | 179355 | Minor Inspection | 551947 | 2027-01-14 | 2027-02-08
9A5 | MENA | GG10466 | Generator | 181607 | Minor Inspection | 553178 | 2029-03-01 | 2029-03-18
9A5 | MENA | GG10467 | Generator | 182168 | Major Inspection (Robotic) | 553606 | 2027-04-01 | 2027-04-18
9A5 | MENA | GG10464 | Generator | 182172 | Major Inspection (Robotic) | 553610 | 2027-10-01 | 2027-10-15
9A5 | Asia | 954X088 | Generator | 187046 | Minor Inspection | 550641 | 2028-07-31 | 2028-08-14
9A5 | MENA | GG10466 | Generator | 189620 | Large Call-Out | 558990 | 2026-10-04 | 2026-10-19
9A5 | MENA | GG10464 | Generator | 189621 | Large Call-Out | 558991 | 2026-10-24 | 2026-11-08
9A5 | Europe | 954X041 | Generator | 192228 | Minor Inspection | 560408 | 2027-10-19 | 2027-11-02
9E.03 | SSA | 810394 | Gas Turbine | 103139 | Borescope Inspection (BI) | 527455 | 2026-02-09 | 2026-02-13
9E.03 | MENA | 890377 | Gas Turbine | 103392 | Major Inspection (MI) | 501995 | 2029-04-01 | 2029-04-29
9E.03 | MENA | 890296 | Gas Turbine | 104006 | Hot Gas Path Inspection (HGPI) | 501261 | 2027-01-24 | 2027-02-07
9E.03 | SSA | 810395 | Gas Turbine | 104601 | Major Inspection (MI) | 500871 | 2026-01-13 | 2026-03-12
9E.03 | SSA | 890934 | Gas Turbine | 104605 | Hot Gas Path Inspection (HGPI) | 501143 | 2026-09-01 | 2026-10-31
9E.03 | SSA | 890922 | Gas Turbine | 104633 | Hot Gas Path Inspection (HGPI) | 501129 | 2027-07-01 | 2027-07-31
9E.03 | MENA | 890377 | Gas Turbine | 104635 | Hot Gas Path Inspection (HGPI) | 501993 | 2027-04-22 | 2027-05-06
9E.03 | MENA | 890286 | Gas Turbine | 104868 | Hot Gas Path Inspection (HGPI) | 501264 | 2026-04-10 | 2026-04-27
9E.03 | SSA | 890924 | Gas Turbine | 105026 | Hot Gas Path Inspection (HGPI) | 501138 | 2027-03-01 | 2027-03-31
9E.03 | SSA | 890925 | Gas Turbine | 105210 | Hot Gas Path Inspection (HGPI) | 501135 | 2027-06-01 | 2027-06-24
9E.03 | MENA | 890375 | Gas Turbine | 105253 | Major Inspection (MI) | 501996 | 2028-03-13 | 2028-04-12
9E.03 | SSA | 890919 | Gas Turbine | 105355 | Hot Gas Path Inspection (HGPI) | 501134 | 2026-08-01 | 2026-08-25
9E.03 | SSA | 890935 | Gas Turbine | 105502 | Major Inspection (MI) | 501159 | 2026-05-27 | 2026-06-27
9E.03 | SSA | 890921 | Gas Turbine | 105591 | Hot Gas Path Inspection (HGPI) | 501136 | 2029-11-15 | 2029-12-15
9E.03 | MENA | 890315 | Gas Turbine | 105924 | Major Inspection (MI) | 502368 | 2026-12-12 | 2027-01-16
9E.03 | MENA | 890312 | Gas Turbine | 105925 | Major Inspection (MI) | 502369 | 2026-11-06 | 2026-12-11
9E.03 | MENA | 810388 | Gas Turbine | 105947 | Major Inspection (MI) | 502391 | 2026-02-09 | 2026-04-09
9E.03 | MENA | 890161 | Gas Turbine | 105948 | Major Inspection (MI) | 502392 | 2027-01-21 | 2027-03-06
9E.03 | MENA | 810390 | Gas Turbine | 105949 | Major Inspection (MI) | 502393 | 2028-11-01 | 2028-12-02
9E.03 | MENA | 810389 | Gas Turbine | 105952 | Major Inspection (MI) | 502396 | 2028-12-03 | 2029-01-03
9E.03 | MENA | 810387 | Gas Turbine | 105953 | Major Inspection (MI) | 502397 | 2026-01-05 | 2026-02-06
9E.03 | Asia | 890210 | Gas Turbine | 107154 | Combustion Inspection (CI) |  | 2027-11-19 | 2027-11-26
9E.03 | Asia | 890210 | Gas Turbine | 111773 | Major Inspection (MI) |  | 2030-11-03 | 2030-12-01
9E.03 | Asia | 890209 | Gas Turbine | 112189 | Combustion Inspection (CI) |  | 2027-04-10 | 2027-04-17
9E.03 | Asia | 890210 | Gas Turbine | 114038 | Combustion Inspection (CI) |  | 2027-11-19 | 2027-11-26
9E.03 | Asia | 890209 | Gas Turbine | 117795 | Combustion Inspection (CI) |  | 2027-04-10 | 2027-04-17
9E.03 | Asia | 890210 | Gas Turbine | 119611 | Major Inspection (MI) |  | 2030-11-03 | 2030-12-01
9E.03 | Asia | 890209 | Gas Turbine | 123130 | Major Inspection (MI) | 543155 | 2030-04-14 | 2030-05-12
9E.03 | Asia | 890209 | Gas Turbine | 125049 | Major Inspection (MI) |  | 2030-04-14 | 2030-05-12
9E.03 | MENA | 890317 | Gas Turbine | 127186 | Hot Gas Path Inspection (HGPI) | 517944 | 2026-01-05 | 2026-02-03
9E.03 | MENA | 890316 | Gas Turbine | 127188 | Major Inspection (MI) | 517945 | 2026-02-02 | 2026-03-19
9E.03 | MENA | 890230 | Gas Turbine | 127198 | Hot Gas Path Inspection (HGPI) | 517950 | 2027-10-04 | 2027-11-02
9E.03 | MENA | 890225 | Gas Turbine | 132742 | Major Inspection (MI) | 522449 | 2028-12-01 | 2028-12-31
9E.03 | MENA | 890226 | Gas Turbine | 132744 | Major Inspection (MI) | 522451 | 2028-12-01 | 2028-12-31
9E.03 | MENA | 890358 | Gas Turbine | 132962 | Major Inspection (MI) | 525990 | 2026-10-01 | 2026-11-05
9E.03 | MENA | 890296 | Gas Turbine | 133006 | Hot Gas Path Inspection (HGPI) | 525019 | 2026-04-12 | 2026-04-27
9E.03 | MENA | 295230 | Gas Turbine | 133443 | Major Inspection (MI) | 531663 | 2027-11-05 | 2027-12-04
9E.03 | MENA | 295232 | Gas Turbine | 133446 | Major Inspection (MI) | 546652 | 2029-03-01 | 2029-03-31
9E.03 | MENA | 890317 | Gas Turbine | 137065 | Major Inspection (MI) | 524420 | 2027-10-03 | 2027-11-02
9E.03 | MENA | 890313 | Gas Turbine | 139754 | Major Inspection (MI) | 526855 | 2027-01-18 | 2027-02-22
9E.03 | MENA | 890334 | Gas Turbine | 139755 | Major Inspection (MI) | 532205 | 2028-07-02 | 2028-08-01
9E.03 | MENA | 890359 | Gas Turbine | 139756 | Major Inspection (MI) | 532206 | 2028-03-31 | 2028-04-30
9E.03 | MENA | 890337 | Gas Turbine | 139757 | Major Inspection (MI) | 532207 | 2028-05-01 | 2028-05-31
9E.03 | MENA | 890273 | Gas Turbine | 139780 | Hot Gas Path Inspection (HGPI) | 525919 | 2028-11-23 | 2028-12-19
9E.03 | MENA | 890268 | Gas Turbine | 139784 | Hot Gas Path Inspection (HGPI) | 525922 | 2028-10-28 | 2028-11-23
9E.03 | MENA | 890261 | Gas Turbine | 139785 | Hot Gas Path Inspection (HGPI) | 525924 | 2028-10-01 | 2028-10-27
9E.03 | SSA | 890927 | Gas Turbine | 141608 | Major Inspection (MI) | 526897 | 2029-12-01 | 2029-12-30
9E.03 | SSA | 890920 | Gas Turbine | 141610 | Major Inspection (MI) | 526929 | 2029-05-01 | 2029-05-31
9E.03 | SSA | 810394 | Gas Turbine | 142698 | Borescope Inspection (BI) | 527396 | 2026-08-07 | 2026-08-10
9E.03 | Europe | 890080 | Gas Turbine | 146180 | Hot Gas Path Inspection (HGPI) | 529501 | 2027-09-06 | 2027-09-27
9E.03 | MENA | 890261 | Gas Turbine | 148774 | Combustion Inspection (CI) | 530965 | 2026-11-23 | 2026-12-02
9E.03 | MENA | 890268 | Gas Turbine | 148775 | Combustion Inspection (CI) | 530966 | 2026-12-03 | 2026-12-12
9E.03 | MENA | 890273 | Gas Turbine | 148776 | Combustion Inspection (CI) | 530967 | 2026-12-13 | 2026-12-22
9E.03 | SSA | 890207 | Gas Turbine | 149771 | Combustion Inspection (CI) | 544112 | 2026-03-15 | 2026-03-29
9E.03 | SSA | 890199 | Gas Turbine | 149772 | Combustion Inspection (CI) |  | 2026-03-08 | 2026-03-21
9E.03 | SSA | 890207 | Gas Turbine | 149773 | Combustion Inspection (CI) |  | 2026-09-08 | 2026-09-22
9E.03 | SSA | 890199 | Gas Turbine | 149774 | Combustion Inspection (CI) |  | 2027-03-11 | 2027-03-18
9E.03 | SSA | 890207 | Gas Turbine | 149775 | Major Inspection (MI) | 553055 | 2028-02-07 | 2028-04-17
9E.03 | SSA | 890199 | Gas Turbine | 149776 | Major Inspection (MI) |  | 2029-01-08 | 2029-03-19
9E.03 | SSA | 810394 | Gas Turbine | 150287 | Hot Gas Path Inspection (HGPI) | 532023 | 2028-01-10 | 2028-02-14
9E.03 | Latin America | 296897 | Gas Turbine | 150354 | Combustion Inspection (CI) | 550102 | 2027-03-01 | 2027-03-15
9E.03 | Latin America | 296897 | Gas Turbine | 150355 | Major Inspection (MI) | 543267 | 2028-07-18 | 2028-08-15
9E.03 | Latin America | 809395 | Gas Turbine | 150429 | Hot Gas Path Inspection (HGPI) | 549134 | 2027-11-17 | 2027-12-10
9E.03 | Latin America | EGG0268 | Gas Turbine | 150433 | Combustion Inspection (CI) | 544629 | 2027-04-23 | 2027-04-30
9E.03 | Asia | 890233 | Gas Turbine | 150462 | Combustion Inspection (CI) | 543204 | 2027-06-05 | 2027-06-26
9E.03 | SSA | 810395 | Gas Turbine | 150635 | Borescope Inspection (BI) | 532234 | 2027-01-11 | 2027-01-14
9E.03 | SSA | 810394 | Gas Turbine | 150636 | Borescope Inspection (BI) | 532235 | 2027-08-16 | 2027-08-19
9E.03 | MENA | 890227 | Gas Turbine | 151091 | Major Inspection (MI) | 538165 | 2028-01-29 | 2028-02-26
9E.03 | MENA | 890334 | Gas Turbine | 151163 | Major Inspection (MI) |  | 2027-05-24 | 2027-06-21
9E.03 | Europe | 295794 | Gas Turbine | 151173 | Major Inspection (MI) | 534576 | 2026-11-08 | 2026-12-10
9E.03 | Europe | 296538 | Gas Turbine | 151174 | Major Inspection (MI) | 534578 | 2026-10-04 | 2026-11-03
9E.03 | Europe | 296539 | Gas Turbine | 151175 | Hot Gas Path Inspection (HGPI) | 534577 | 2027-05-02 | 2027-05-27
9E.03 | Europe | 295795 | Gas Turbine | 151176 | Major Inspection (MI) | 543540 | 2027-06-18 | 2027-07-16
9E.03 | Europe | 890400 | Gas Turbine | 151233 | Major Inspection (MI) | 539571 | 2027-05-03 | 2027-06-15
9E.03 | Europe | 890002 | Gas Turbine | 151235 | Hot Gas Path Inspection (HGPI) | 536898 | 2026-05-12 | 2026-06-16
9E.03 | MENA | 890163 | Gas Turbine | 151241 | Hot Gas Path Inspection (HGPI) | 542781 | 2028-11-03 | 2028-11-19
9E.03 | MENA | 810388 | Gas Turbine | 151242 | Hot Gas Path Inspection (HGPI) |  | 2028-03-31 | 2028-04-14
9E.03 | MENA | 810391 | Gas Turbine | 151243 | Hot Gas Path Inspection (HGPI) | 543584 | 2030-11-23 | 2030-12-09
9E.03 | MENA | 810387 | Gas Turbine | 151244 | Hot Gas Path Inspection (HGPI) |  | 2028-11-19 | 2028-12-03
9E.03 | MENA | 890161 | Gas Turbine | 151245 | Hot Gas Path Inspection (HGPI) |  | 2029-03-13 | 2029-03-27
9E.03 | MENA | 810389 | Gas Turbine | 151246 | Hot Gas Path Inspection (HGPI) |  | 2029-02-25 | 2029-03-11
9E.03 | MENA | 890338 | Gas Turbine | 151367 | Major Inspection (MI) | 532586 | 2028-06-01 | 2028-07-01
9E.03 | MENA | 890005 | Gas Turbine | 155303 | Combustion Inspection (CI) | 542642 | 2027-01-07 | 2027-01-13
9E.03 | MENA | 890007 | Gas Turbine | 155304 | Hot Gas Path Inspection (HGPI) | 542643 | 2026-12-21 | 2027-01-05
9E.03 | MENA | 890009 | Gas Turbine | 155305 | Major Inspection (MI) | 538160 | 2029-02-22 | 2029-03-22
9E.03 | MENA | 890003 | Gas Turbine | 155306 | Major Inspection (MI) | 538159 | 2028-01-10 | 2028-02-07
9E.03 | MENA | 890005 | Gas Turbine | 155307 | Major Inspection (MI) | 549121 | 2028-04-16 | 2028-05-14
9E.03 | MENA | 890007 | Gas Turbine | 155308 | Combustion Inspection (CI) |  | 2028-04-24 | 2028-05-01
9E.03 | MENA | 890009 | Gas Turbine | 155309 | Major Inspection (MI) |  | 2028-07-28 | 2028-08-25
9E.03 | MENA | 890003 | Gas Turbine | 155310 | Combustion Inspection (CI) |  | 2028-11-25 | 2028-12-02
9E.03 | Europe | 296948 | Gas Turbine | 155695 | Major Inspection (MI) | 536294 | 2026-01-23 | 2026-04-09
9E.03 | Europe | 296947 | Gas Turbine | 155699 | Major Inspection (MI) | 537840 | 2027-04-08 | 2027-05-30
9E.03 | Europe | 296946 | Gas Turbine | 155701 | Hot Gas Path Inspection (HGPI) | 546441 | 2027-10-01 | 2027-10-20
9E.03 | Europe | 296948 | Gas Turbine | 155702 | Hot Gas Path Inspection (HGPI) | 546443 | 2029-01-22 | 2029-02-13
9E.03 | Asia | 890209 | Gas Turbine | 155966 | Borescope Inspection (BI) | 535864 | 2026-01-12 | 2026-01-14
9E.03 | Asia | 890209 | Gas Turbine | 155967 | Borescope Inspection (BI) | 535865 | 2026-10-20 | 2026-10-22
9E.03 | Asia | 890210 | Gas Turbine | 155969 | Borescope Inspection (BI) | 535867 | 2027-04-08 | 2027-04-09
9E.03 | Europe | EGG0236 | Gas Turbine | 161775 | Borescope Inspection (BI) | 552824 | 2026-09-01 | 2026-09-06
9E.03 | Asia | 890210 | Gas Turbine | 165705 | Major Inspection (MI) | 543156 | 2030-07-25 | 2030-08-22
9E.03 | Asia | 890233 | Gas Turbine | 165774 | Major Inspection (MI) | 543205 | 2030-06-01 | 2030-06-30
9E.03 | Europe | 890004 | Gas Turbine | 165779 | Hot Gas Path Inspection (HGPI) | 552288 | 2028-05-16 | 2028-06-20
9E.03 | Europe | 890002 | Gas Turbine | 165780 | Major Inspection (MI) | 552289 | 2029-09-11 | 2029-11-13
9E.03 | Latin America | 296897 | Gas Turbine | 165898 | Combustion Inspection (CI) | 559188 | 2030-02-19 | 2030-02-26
9E.03 | Europe | 890400 | Gas Turbine | 166279 | Hot Gas Path Inspection (HGPI) |  | 2029-07-17 | 2029-07-31
9E.03 | Europe | 295794 | Gas Turbine | 166310 | Hot Gas Path Inspection (HGPI) | 543541 | 2029-09-23 | 2029-10-18
9E.03 | Europe | 296538 | Gas Turbine | 166312 | Hot Gas Path Inspection (HGPI) | 543542 | 2029-05-01 | 2029-05-25
9E.03 | Europe | 296539 | Gas Turbine | 166315 | Major Inspection (MI) | 543543 | 2029-10-28 | 2029-11-29
9E.03 | Europe | 295795 | Gas Turbine | 166316 | Major Inspection (MI) | 543544 | 2027-10-24 | 2027-11-25
9E.03 | Latin America | 890939 | Gas Turbine | 166381 | Major Inspection (MI) | 543572 | 2026-08-04 | 2026-09-19
9E.03 | Latin America | 890939 | Gas Turbine | 166383 | Combustion Inspection (CI) | 563162 | 2028-01-27 | 2028-02-03
9E.03 | Latin America | 890938 | Gas Turbine | 166384 | Combustion Inspection (CI) |  | 2029-08-23 | 2029-08-30
9E.03 | Latin America | 890939 | Gas Turbine | 166385 | Hot Gas Path Inspection (HGPI) | 543573 | 2030-01-26 | 2030-02-09
9E.03 | Latin America | EGG0224 | Gas Turbine | 166389 | Combustion Inspection (CI) | 544627 | 2028-01-18 | 2028-01-25
9E.03 | Latin America | 809396 | Gas Turbine | 166390 | Hot Gas Path Inspection (HGPI) | 543575 | 2028-11-10 | 2028-11-27
9E.03 | MENA | 810390 | Gas Turbine | 166405 | Hot Gas Path Inspection (HGPI) |  | 2028-11-01 | 2028-11-15
9E.03 | MENA | 890177 | Gas Turbine | 166675 | Hot Gas Path Inspection (HGPI) | 543794 | 2027-02-28 | 2027-03-26
9E.03 | MENA | 890180 | Gas Turbine | 166676 | Hot Gas Path Inspection (HGPI) | 543795 | 2027-02-01 | 2027-02-27
9E.03 | Asia | 890034 | Gas Turbine | 170101 | Major Inspection (MI) | 546404 | 2026-12-10 | 2027-01-12
9E.03 | Asia | 890034 | Gas Turbine | 170104 | Combustion Inspection (CI) | 546406 | 2028-02-18 | 2028-02-24
9E.03 | Asia | 890034 | Gas Turbine | 172674 | Combustion Inspection (CI) | 547885 | 2029-07-25 | 2029-07-31
9E.03 | Asia | 890210 | Gas Turbine | 177017 | Hot Gas Path Inspection (HGPI) | 550641 | 2028-07-31 | 2028-08-14
9E.03 | Asia | 890209 | Gas Turbine | 178891 | Hot Gas Path Inspection (HGPI) | 551947 | 2027-01-14 | 2027-02-08
9E.03 | Asia | 890034 | Gas Turbine | 179378 | Combustion Inspection (CI) |  | 2030-11-15 | 2030-11-22
9E.03 | Europe | 295794 | Gas Turbine | 179500 | Hot Gas Path Inspection (HGPI) | 552062 | 2030-04-01 | 2030-04-15
9E.03 | Europe | 296538 | Gas Turbine | 179501 | Hot Gas Path Inspection (HGPI) | 552063 | 2030-11-10 | 2030-11-24
9E.03 | MENA | 296771 | Gas Turbine | 180140 | Combustion Inspection (CI) | 560025 | 2027-10-01 | 2027-10-08
9E.03 | MENA | 296770 | Gas Turbine | 180141 | Combustion Inspection (CI) | 560026 | 2027-10-01 | 2027-10-08
9E.03 | MENA | 296769 | Gas Turbine | 180142 | Combustion Inspection (CI) | 560027 | 2027-10-01 | 2027-10-08
9E.03 | MENA | 296771 | Gas Turbine | 180143 | Hot Gas Path Inspection (HGPI) |  | 2029-12-16 | 2029-12-30
9E.03 | MENA | 296770 | Gas Turbine | 180144 | Hot Gas Path Inspection (HGPI) | 560028 | 2028-10-01 | 2028-10-18
9E.03 | MENA | 296769 | Gas Turbine | 180169 | Major Inspection (MI) | 552403 | 2026-11-15 | 2026-12-14
9E.03 | MENA | 890354 | Gas Turbine | 181606 | Hot Gas Path Inspection (HGPI) | 553178 | 2029-03-01 | 2029-03-18
9E.03 | MENA | 890355 | Gas Turbine | 182167 | Hot Gas Path Inspection (HGPI) | 553606 | 2027-04-01 | 2027-04-18
9E.03 | MENA | 890352 | Gas Turbine | 182171 | Hot Gas Path Inspection (HGPI) | 553610 | 2027-10-10 | 2027-10-25
9E.03 | Europe | EGG0236 | Gas Turbine | 187975 | Major Inspection (MI) | 557435 | 2028-05-07 | 2028-06-23
9E.03 | Latin America | EGG0224 | Gas Turbine | 189681 | Large Call-Out | 558571 | 2026-01-19 | 2026-02-02
9E.03 | Europe | 890080 | Gas Turbine | 192227 | Hot Gas Path Inspection (HGPI) | 560408 | 2027-10-19 | 2027-11-02
9E.03 | MENA | 890354 | Gas Turbine | 192277 | Large Call-Out | 554242 | 2026-03-13 | 2026-03-19
9E.03 | MENA | 890354 | Gas Turbine | 192278 | Large Call-Out | 560451 | 2026-03-14 | 2026-03-19
9E.03 | Europe | 296539 | Gas Turbine | 192299 | Hot Gas Path Inspection (HGPI) | 560463 | 2030-05-29 | 2030-06-12
9E.03 | MENA | 890161 | Gas Turbine | 192783 | Major Inspection (MI) | 560748 | 2026-03-31 | 2026-04-28
9E.03 | MENA | 890163 | Gas Turbine | 192785 | Hot Gas Path Inspection (HGPI) |  | 2028-11-05 | 2028-11-19
9E.03 | MENA | 295231 | Gas Turbine | 192786 | Major Inspection (MI) |  | 2029-10-07 | 2029-11-04
9E.03 | MENA | 295232 | Gas Turbine | 192787 | Major Inspection (MI) |  | 2029-10-23 | 2029-11-20
9E.03 | Latin America | 296897 | Gas Turbine | 196416 | Stand Alone Small Upgrade | 563666 | 2026-08-30 | 2026-09-03
9E.04 | SSA | 891007 | Gas Turbine | 150449 | Combustion Inspection (CI) | 532137 | 2026-05-05 | 2026-05-12
9E.04 | SSA | 891007 | Gas Turbine | 150450 | Combustion Inspection (CI) | 532138 | 2027-04-05 | 2027-04-12
9E.04 | SSA | 891007 | Gas Turbine | 150451 | Combustion Inspection (CI) | 532139 | 2028-04-05 | 2028-04-12
9EC | Europe | 316X990 | Generator | 166886 | Major Inspection (Robotic) | 536294 | 2026-01-23 | 2026-04-09
9EC | Latin America | 290T404 | Generator | 167417 | Major Inspection (Rotor Out) | 504858 | 2026-04-02 | 2026-05-15
9EC | Europe | 316X953 | Generator | 170166 | Minor Inspection | 546441 | 2027-10-01 | 2027-10-20
9EC | Europe | 316X990 | Generator | 170168 | Minor Inspection | 546443 | 2029-01-22 | 2029-02-13
9EC | Europe | 316X955 | Generator | 170214 | Major Inspection (Robotic) | 537840 | 2027-01-26 | 2027-03-01
9FA.03 | MENA | 298815 | Gas Turbine | 102662 | Major Inspection (MI) | 502141 | 2028-10-03 | 2028-10-30
9FA.03 | MENA | 299253 | Gas Turbine | 102798 | Stand Alone Large Upgrade | 500127 | 2028-01-02 | 2028-01-27
9FA.03 | MENA | 299305 | Gas Turbine | 103362 | Stand Alone Large Upgrade | 500113 | 2028-11-15 | 2028-12-14
9FA.03 | MENA | 299281 | Gas Turbine | 103510 | Stand Alone Large Upgrade | 500075 | 2028-01-01 | 2028-01-24
9FA.03 | MENA | 299311 | Gas Turbine | 103563 | Stand Alone Large Upgrade | 500076 | 2028-04-01 | 2028-04-24
9FA.03 | MENA | 299282 | Gas Turbine | 104057 | Stand Alone Large Upgrade | 500074 | 2028-02-01 | 2028-02-24
9FA.03 | MENA | 299303 | Gas Turbine | 104108 | Stand Alone Large Upgrade | 500115 | 2027-12-01 | 2027-12-31
9FA.03 | MENA | 299254 | Gas Turbine | 104418 | Stand Alone Large Upgrade | 500128 | 2028-09-25 | 2028-10-20
9FA.03 | MENA | 299310 | Gas Turbine | 104532 | Stand Alone Large Upgrade | 500077 | 2028-03-01 | 2028-03-24
9FA.03 | MENA | 299302 | Gas Turbine | 104800 | Stand Alone Large Upgrade | 500112 | 2027-11-01 | 2027-11-30
9FA.03 | MENA | 299304 | Gas Turbine | 105557 | Stand Alone Large Upgrade | 500114 | 2028-10-15 | 2028-11-15
9FA.03 | MENA | 299109 | Gas Turbine | 105687 | Combustion Inspection (CI) | 500834 | 2027-04-01 | 2027-04-14
9FA.03 | MENA | 298446 | Gas Turbine | 105887 | Hot Gas Path Inspection (HGPI) | 502331 | 2027-03-01 | 2027-04-01
9FA.03 | MENA | 299302 | Gas Turbine | 105911 | Hot Gas Path Inspection (HGPI) | 502355 | 2027-05-01 | 2027-05-21
9FA.03 | Europe | 298338 | Gas Turbine | 106465 | Hot Gas Path Inspection (HGPI) | 502838 | 2026-09-07 | 2026-09-21
9FA.03 | Europe | 298403 | Gas Turbine | 106466 | Hot Gas Path Inspection (HGPI) | 502839 | 2026-03-23 | 2026-06-09
9FA.03 | China | 298523 | Gas Turbine | 106527 | Hot Gas Path Inspection (HGPI) | 502900 | 2026-03-10 | 2026-04-08
9FA.03 | China | 298434 | Gas Turbine | 106558 | Combustion Inspection (CI) | 502931 | 2029-10-19 | 2029-11-02
9FA.03 | Europe | 298328 | Gas Turbine | 106639 | Major Inspection (MI) | 503012 | 2026-04-16 | 2026-05-18
9FA.03 | China | 299143 | Gas Turbine | 106667 | Major Inspection (MI) | 503040 | 2029-03-02 | 2029-04-15
9FA.03 | China | 299144 | Gas Turbine | 111317 | Hot Gas Path Inspection (HGPI) |  | 2030-04-11 | 2030-04-25
9FA.03 | China | 298982 | Gas Turbine | 113731 | Hot Gas Path Inspection (HGPI) |  | 2029-04-18 | 2029-05-02
9FA.03 | China | 297913 | Gas Turbine | 114756 | Hot Gas Path Inspection (HGPI) |  | 2026-04-22 | 2026-05-06
9FA.03 | China | 297913 | Gas Turbine | 115945 | Hot Gas Path Inspection (HGPI) |  | 2026-04-22 | 2026-05-06
9FA.03 | China | 297913 | Gas Turbine | 116460 | Hot Gas Path Inspection (HGPI) |  | 2030-04-08 | 2030-04-22
9FA.03 | Europe | 298214 | Gas Turbine | 116646 | Major Inspection (MI) | 513583 | 2026-09-21 | 2026-11-27
9FA.03 | China | 299144 | Gas Turbine | 117283 | Hot Gas Path Inspection (HGPI) |  | 2030-04-11 | 2030-04-25
9FA.03 | China | 299146 | Gas Turbine | 118486 | Major Inspection (MI) | 513798 | 2026-03-03 | 2026-04-15
9FA.03 | Europe | 298152 | Gas Turbine | 118625 | Major Inspection (MI) | 516230 | 2028-04-01 | 2028-05-03
9FA.03 | Europe | 298275 | Gas Turbine | 118633 | Major Inspection (MI) | 513589 | 2026-09-21 | 2026-11-27
9FA.03 | China | 298982 | Gas Turbine | 120615 | Major Inspection (MI) | 554457 | 2026-11-05 | 2026-12-10
9FA.03 | China | 297913 | Gas Turbine | 120974 | Hot Gas Path Inspection (HGPI) |  | 2030-04-08 | 2030-04-22
9FA.03 | Europe | 298377 | Gas Turbine | 124892 | Hot Gas Path Inspection (HGPI) | 513539 | 2026-10-20 | 2027-01-16
9FA.03 | MENA | 299304 | Gas Turbine | 125884 | Borescope Inspection (BI) | 516766 | 2026-02-01 | 2026-02-03
9FA.03 | MENA | 299303 | Gas Turbine | 125885 | Borescope Inspection (BI) | 516767 | 2026-01-15 | 2026-01-17
9FA.03 | MENA | 298941 | Gas Turbine | 136094 | Hot Gas Path Inspection (HGPI) | 523641 | 2026-11-09 | 2026-11-22
9FA.03 | China | 296440 | Gas Turbine | 137087 | Major Inspection (MI) | 543004 | 2026-01-01 | 2026-03-01
9FA.03 | China | 298428 | Gas Turbine | 137547 | Hot Gas Path Inspection (HGPI) | 539327 | 2026-04-18 | 2026-05-22
9FA.03 | Asia | 298916 | Gas Turbine | 138595 | Hot Gas Path Inspection (HGPI) | 525202 | 2030-05-12 | 2030-05-31
9FA.03 | Europe | 299225 | Gas Turbine | 145249 | Major Inspection (MI) | 541375 | 2028-08-01 | 2028-08-31
9FA.03 | Europe | 299226 | Gas Turbine | 145250 | Major Inspection (MI) | 541471 | 2028-12-01 | 2028-12-31
9FA.03 | Europe | 297920 | Gas Turbine | 151856 | Borescope Inspection (BI) | 532966 | 2026-11-04 | 2026-11-06
9FA.03 | Europe | 297725 | Gas Turbine | 151873 | Borescope Inspection (BI) | 532979 | 2026-09-23 | 2026-09-25
9FA.03 | Europe | 297812 | Gas Turbine | 152107 | Borescope Inspection (BI) | 533180 | 2026-09-02 | 2026-09-04
9FA.03 | Europe | 297812 | Gas Turbine | 152108 | Major Inspection (MI) | 533181 | 2028-04-03 | 2028-04-30
9FA.03 | Europe | 297813 | Gas Turbine | 152113 | Borescope Inspection (BI) | 533184 | 2026-05-05 | 2026-05-07
9FA.03 | Europe | 297813 | Gas Turbine | 152114 | Major Inspection (MI) | 533185 | 2028-04-03 | 2028-04-30
9FA.03 | MENA | 299222 | Gas Turbine | 153130 | Hot Gas Path Inspection (HGPI) | 534044 | 2026-11-25 | 2026-12-15
9FA.03 | MENA | 299224 | Gas Turbine | 153131 | Hot Gas Path Inspection (HGPI) | 534194 | 2026-11-05 | 2026-11-25
9FA.03 | MENA | 299223 | Gas Turbine | 153132 | Hot Gas Path Inspection (HGPI) | 534688 | 2026-12-15 | 2027-01-04
9FA.03 | MENA | 299220 | Gas Turbine | 153133 | Hot Gas Path Inspection (HGPI) | 534689 | 2027-11-03 | 2027-11-22
9FA.03 | MENA | 299221 | Gas Turbine | 153134 | Hot Gas Path Inspection (HGPI) | 534690 | 2027-12-20 | 2028-01-03
9FA.03 | China | 296439 | Gas Turbine | 154336 | Major Inspection (MI) | 554594 | 2027-09-30 | 2027-12-26
9FA.03 | China | 272002 | Gas Turbine | 154338 | Major Inspection (MI) | 553732 | 2028-09-16 | 2028-12-12
9FA.03 | China | 900111 | Gas Turbine | 154340 | Major Inspection (MI) | 554665 | 2027-10-06 | 2027-11-15
9FA.03 | Latin America | 299230 | Gas Turbine | 154380 | Hot Gas Path Inspection (HGPI) | 554019 | 2028-03-02 | 2028-04-03
9FA.03 | Latin America | 299229 | Gas Turbine | 154381 | Hot Gas Path Inspection (HGPI) | 545807 | 2028-01-25 | 2028-02-26
9FA.03 | Latin America | 297017 | Gas Turbine | 154383 | Major Inspection (MI) | 543467 | 2028-03-21 | 2028-05-07
9FA.03 | Latin America | 297011 | Gas Turbine | 154384 | Hot Gas Path Inspection (HGPI) | 543466 | 2028-03-21 | 2028-04-07
9FA.03 | China | 298780 | Gas Turbine | 154581 | Major Inspection (MI) | 539537 | 2026-09-24 | 2026-11-07
9FA.03 | Asia | 299260 | Gas Turbine | 154721 | Major Inspection (MI) | 540973 | 2028-08-01 | 2028-08-31
9FA.03 | Asia | 298967 | Gas Turbine | 154725 | Major Inspection (MI) | 541110 | 2027-05-05 | 2027-06-02
9FA.03 | Asia | 298872 | Gas Turbine | 154726 | Major Inspection (MI) | 550304 | 2028-08-04 | 2028-09-02
9FA.03 | MENA | 299305 | Gas Turbine | 154747 | Borescope Inspection (BI) | 553151 | 2026-02-05 | 2026-02-07
9FA.03 | China | 297912 | Gas Turbine | 154996 | Hot Gas Path Inspection (HGPI) | 539095 | 2028-04-13 | 2028-04-27
9FA.03 | China | 298433 | Gas Turbine | 155073 | Combustion Inspection (CI) | 546355 | 2027-04-30 | 2027-05-07
9FA.03 | MENA | 299108 | Gas Turbine | 155080 | Hot Gas Path Inspection (HGPI) | 537817 | 2027-03-13 | 2027-04-02
9FA.03 | MENA | 299106 | Gas Turbine | 155081 | Hot Gas Path Inspection (HGPI) | 537815 | 2027-04-30 | 2027-05-20
9FA.03 | MENA | 299107 | Gas Turbine | 155082 | Hot Gas Path Inspection (HGPI) | 537816 | 2027-05-27 | 2027-06-16
9FA.03 | MENA | 299104 | Gas Turbine | 155083 | Hot Gas Path Inspection (HGPI) | 537813 | 2028-06-09 | 2028-06-29
9FA.03 | MENA | 299109 | Gas Turbine | 155084 | Hot Gas Path Inspection (HGPI) | 537818 | 2028-07-14 | 2028-08-03
9FA.03 | MENA | 298651 | Gas Turbine | 155094 | Hot Gas Path Inspection (HGPI) | 537245 | 2026-01-16 | 2026-02-04
9FA.03 | China | 298522 | Gas Turbine | 155157 | Hot Gas Path Inspection (HGPI) | 542014 | 2027-03-09 | 2027-04-07
9FA.03 | Asia | 299036 | Gas Turbine | 155159 | Hot Gas Path Inspection (HGPI) | 552617 | 2029-06-27 | 2029-07-11
9FA.03 | Asia | 299037 | Gas Turbine | 155161 | Hot Gas Path Inspection (HGPI) | 552618 | 2029-06-27 | 2029-07-11
9FA.03 | MENA | 298463 | Gas Turbine | 155163 | Combustion Inspection (CI) | 537810 | 2027-04-03 | 2027-04-10
9FA.03 | MENA | 298464 | Gas Turbine | 155164 | Combustion Inspection (CI) | 537812 | 2027-04-17 | 2027-04-24
9FA.03 | MENA | 298463 | Gas Turbine | 155165 | Major Inspection (MI) | 545934 | 2028-11-30 | 2028-12-28
9FA.03 | MENA | 298942 | Gas Turbine | 155166 | Hot Gas Path Inspection (HGPI) | 538132 | 2027-11-08 | 2027-11-22
9FA.03 | MENA | 298940 | Gas Turbine | 155167 | Major Inspection (MI) | 538133 | 2028-11-07 | 2028-11-20
9FA.03 | MENA | 299100 | Gas Turbine | 155183 | Combustion Inspection (CI) | 540552 | 2027-10-10 | 2027-10-17
9FA.03 | MENA | 299101 | Gas Turbine | 155184 | Combustion Inspection (CI) | 540553 | 2028-08-10 | 2028-08-17
9FA.03 | MENA | 298586 | Gas Turbine | 155238 | Major Inspection (MI) | 544997 | 2028-02-14 | 2028-03-17
9FA.03 | MENA | 298587 | Gas Turbine | 155239 | Major Inspection (MI) | 544998 | 2027-02-01 | 2027-03-05
9FA.03 | MENA | 299281 | Gas Turbine | 155294 | Hot Gas Path Inspection (HGPI) |  | 2028-07-31 | 2028-08-14
9FA.03 | MENA | 299282 | Gas Turbine | 155295 | Hot Gas Path Inspection (HGPI) |  | 2028-08-31 | 2028-09-14
9FA.03 | MENA | 299310 | Gas Turbine | 155296 | Hot Gas Path Inspection (HGPI) |  | 2028-05-31 | 2028-06-14
9FA.03 | MENA | 299311 | Gas Turbine | 155300 | Hot Gas Path Inspection (HGPI) | 538202 | 2028-06-30 | 2028-07-14
9FA.03 | MENA | 298816 | Gas Turbine | 155317 | Major Inspection (MI) | 535713 | 2026-03-17 | 2026-06-24
9FA.03 | MENA | 298812 | Gas Turbine | 155318 | Hot Gas Path Inspection (HGPI) | 537976 | 2026-06-23 | 2026-07-27
9FA.03 | MENA | 299477 | Gas Turbine | 155319 | Major Inspection (MI) | 538140 | 2027-03-18 | 2027-04-14
9FA.03 | MENA | 299162 | Gas Turbine | 155323 | Major Inspection (MI) | 538143 | 2027-05-10 | 2027-07-13
9FA.03 | MENA | 298816 | Gas Turbine | 155325 | Hot Gas Path Inspection (HGPI) | 538145 | 2028-03-31 | 2028-04-14
9FA.03 | MENA | 298811 | Gas Turbine | 155326 | Major Inspection (MI) | 538146 | 2028-11-25 | 2028-12-23
9FA.03 | MENA | 299280 | Gas Turbine | 155357 | Hot Gas Path Inspection (HGPI) | 538162 | 2030-11-02 | 2030-12-01
9FA.03 | Europe | 298243 | Gas Turbine | 155380 | Major Inspection (MI) | 554548 | 2028-03-01 | 2028-04-14
9FA.03 | Asia | 299260 | Gas Turbine | 155580 | Borescope Inspection (BI) | 535616 | 2026-12-18 | 2026-12-20
9FA.03 | Asia | 298916 | Gas Turbine | 155628 | Borescope Inspection (BI) | 535658 | 2026-04-18 | 2026-04-20
9FA.03 | Europe | 298081 | Gas Turbine | 157976 | Large Call-Out | 537489 | 2026-02-23 | 2026-04-28
9FA.03 | Europe | 298082 | Gas Turbine | 157977 | Major Inspection (MI) | 537490 | 2026-03-13 | 2026-06-13
9FA.03 | MENA | 298653 | Gas Turbine | 158022 | Hot Gas Path Inspection (HGPI) | 538807 | 2026-02-01 | 2026-02-18
9FA.03 | Europe | 298359 | Gas Turbine | 158116 | Large Call-Out | 537602 | 2027-02-01 | 2027-05-10
9FA.03 | Europe | 298360 | Gas Turbine | 158121 | Large Call-Out | 537604 | 2027-02-01 | 2027-05-10
9FA.03 | MENA | 299105 | Gas Turbine | 158377 | Hot Gas Path Inspection (HGPI) | 537814 | 2028-07-09 | 2028-07-29
9FA.03 | MENA | 299222 | Gas Turbine | 158717 | Major Inspection (MI) | 538010 | 2030-03-31 | 2030-04-28
9FA.03 | MENA | 299224 | Gas Turbine | 158719 | Major Inspection (MI) | 538011 | 2030-03-31 | 2030-04-28
9FA.03 | MENA | 299477 | Gas Turbine | 158965 | Hot Gas Path Inspection (HGPI) | 538147 | 2030-01-01 | 2030-01-15
9FA.03 | MENA | 298812 | Gas Turbine | 158967 | Major Inspection (MI) |  | 2029-01-28 | 2029-02-25
9FA.03 | MENA | 298815 | Gas Turbine | 158971 | Combustion Inspection (CI) |  | 2029-03-31 | 2029-04-07
9FA.03 | MENA | 299162 | Gas Turbine | 158974 | Hot Gas Path Inspection (HGPI) | 538149 | 2030-03-27 | 2030-04-10
9FA.03 | China | 298522 | Gas Turbine | 160190 | Borescope Inspection (BI) | 538886 | 2026-06-25 | 2026-06-26
9FA.03 | China | 298523 | Gas Turbine | 160191 | Borescope Inspection (BI) | 538887 | 2026-05-23 | 2026-05-24
9FA.03 | China | 297912 | Gas Turbine | 160262 | Borescope Inspection (BI) | 538947 | 2026-01-01 | 2026-06-30
9FA.03 | China | 297912 | Gas Turbine | 160263 | Borescope Inspection (BI) | 538948 | 2026-07-01 | 2026-12-31
9FA.03 | China | 298433 | Gas Turbine | 160727 | Borescope Inspection (BI) | 539339 | 2027-05-26 | 2027-05-28
9FA.03 | China | 298433 | Gas Turbine | 160730 | Borescope Inspection (BI) | 539342 | 2026-05-25 | 2026-05-27
9FA.03 | China | 298434 | Gas Turbine | 160732 | Borescope Inspection (BI) | 539344 | 2027-11-01 | 2027-11-03
9FA.03 | China | 298434 | Gas Turbine | 160734 | Borescope Inspection (BI) | 539345 | 2026-11-03 | 2026-11-05
9FA.03 | China | 298434 | Gas Turbine | 160738 | Hot Gas Path Inspection (HGPI) | 539349 | 2026-03-05 | 2026-04-08
9FA.03 | Europe | 298376 | Gas Turbine | 167261 | Hot Gas Path Inspection (HGPI) | 544265 | 2026-01-19 | 2026-02-26
9FA.03 | MENA | 298588 | Gas Turbine | 168099 | Major Inspection (MI) | 544999 | 2030-09-01 | 2030-09-29
9FA.03 | MENA | 298649 | Gas Turbine | 168338 | Major Inspection (MI) | 545201 | 2028-02-07 | 2028-02-28
9FA.03 | MENA | 298650 | Gas Turbine | 168368 | Major Inspection (MI) | 545225 | 2028-02-29 | 2028-03-21
9FA.03 | MENA | 298654 | Gas Turbine | 168370 | Major Inspection (MI) | 545226 | 2029-01-16 | 2029-02-06
9FA.03 | MENA | 298652 | Gas Turbine | 168373 | Major Inspection (MI) | 545227 | 2029-02-07 | 2029-02-28
9FA.03 | MENA | 298653 | Gas Turbine | 168374 | Major Inspection (MI) | 545228 | 2029-10-01 | 2029-10-29
9FA.03 | MENA | 298651 | Gas Turbine | 168377 | Major Inspection (MI) | 545229 | 2029-10-01 | 2029-10-29
9FA.03 | China | 297913 | Gas Turbine | 168492 | Hot Gas Path Inspection (HGPI) | 546483 | 2029-08-13 | 2029-09-21
9FA.03 | Latin America | 296818 | Gas Turbine | 168782 | Hot Gas Path Inspection (HGPI) | 545549 | 2029-08-22 | 2029-09-05
9FA.03 | China | 298776 | Gas Turbine | 168983 | Hot Gas Path Inspection (HGPI) | 554620 | 2028-06-10 | 2028-06-24
9FA.03 | China | 298779 | Gas Turbine | 168985 | Hot Gas Path Inspection (HGPI) | 554619 | 2030-11-06 | 2030-11-20
9FA.03 | China | 298523 | Gas Turbine | 168998 | Combustion Inspection (CI) | 553354 | 2030-03-12 | 2030-03-19
9FA.03 | China | 298522 | Gas Turbine | 168999 | Combustion Inspection (CI) | 558953 | 2029-07-05 | 2029-07-12
9FA.03 | China | 298434 | Gas Turbine | 169019 | Combustion Inspection (CI) | 554556 | 2029-03-12 | 2029-03-25
9FA.03 | China | 298433 | Gas Turbine | 169020 | Hot Gas Path Inspection (HGPI) |  | 2029-12-04 | 2029-12-18
9FA.03 | China | 272001 | Gas Turbine | 169123 | Major Inspection (MI) | 554595 | 2028-09-16 | 2028-12-24
9FA.03 | MENA | 298588 | Gas Turbine | 169164 | Hot Gas Path Inspection (HGPI) | 545877 | 2027-03-08 | 2027-03-29
9FA.03 | MENA | 299108 | Gas Turbine | 169184 | Combustion Inspection (CI) |  | 2028-11-11 | 2028-11-18
9FA.03 | MENA | 299106 | Gas Turbine | 169185 | Combustion Inspection (CI) |  | 2028-05-10 | 2028-05-17
9FA.03 | MENA | 299107 | Gas Turbine | 169186 | Combustion Inspection (CI) |  | 2028-09-09 | 2028-09-16
9FA.03 | MENA | 299108 | Gas Turbine | 169188 | Major Inspection (MI) | 545888 | 2030-10-17 | 2030-11-14
9FA.03 | MENA | 299107 | Gas Turbine | 169190 | Major Inspection (MI) | 545889 | 2030-07-05 | 2030-08-02
9FA.03 | MENA | 299106 | Gas Turbine | 169192 | Major Inspection (MI) | 545890 | 2030-02-09 | 2030-03-09
9FA.03 | China | 298516 | Gas Turbine | 169205 | Hot Gas Path Inspection (HGPI) | 550160 | 2026-09-01 | 2026-09-15
9FA.03 | China | 298517 | Gas Turbine | 169206 | Hot Gas Path Inspection (HGPI) |  | 2027-02-17 | 2027-03-03
9FA.03 | China | 299197 | Gas Turbine | 169209 | Major Inspection (MI) | 561158 | 2030-03-04 | 2030-04-01
9FA.03 | China | 299145 | Gas Turbine | 169210 | Major Inspection (MI) | 561157 | 2030-08-06 | 2030-09-03
9FA.03 | MENA | 298464 | Gas Turbine | 169282 | Major Inspection (MI) | 545935 | 2028-04-01 | 2028-04-29
9FA.03 | MENA | 298463 | Gas Turbine | 169283 | Combustion Inspection (CI) |  | 2030-11-19 | 2030-11-26
9FA.03 | MENA | 299223 | Gas Turbine | 169458 | Major Inspection (MI) | 546040 | 2030-03-31 | 2030-04-28
9FA.03 | Europe | 298231 | Gas Turbine | 170877 | Major Inspection (MI) | 546820 | 2027-03-01 | 2027-04-17
9FA.03 | China | 296437 | Gas Turbine | 171855 | Hot Gas Path Inspection (HGPI) | 547260 | 2027-01-01 | 2027-04-15
9FA.03 | Europe | 297920 | Gas Turbine | 176028 | Combustion Inspection (CI) | 560596 | 2027-06-07 | 2027-06-21
9FA.03 | MENA | 299281 | Gas Turbine | 176700 | Stand Alone Large Upgrade | 550457 | 2028-09-01 | 2028-10-03
9FA.03 | MENA | 299282 | Gas Turbine | 176702 | Stand Alone Large Upgrade | 550458 | 2028-10-01 | 2028-11-02
9FA.03 | MENA | 299310 | Gas Turbine | 176704 | Stand Alone Large Upgrade | 550459 | 2028-11-01 | 2028-12-03
9FA.03 | MENA | 299311 | Gas Turbine | 176706 | Stand Alone Large Upgrade | 550460 | 2028-12-01 | 2029-01-02
9FA.03 | MENA | 299253 | Gas Turbine | 176708 | Stand Alone Large Upgrade | 550461 | 2027-10-15 | 2027-11-05
9FA.03 | MENA | 299254 | Gas Turbine | 176709 | Stand Alone Large Upgrade | 550462 | 2027-11-15 | 2027-12-05
9FA.03 | Asia | 809955 | Gas Turbine | 176901 | Hot Gas Path Inspection (HGPI) | 550580 | 2027-03-01 | 2027-03-20
9FA.03 | China | 296438 | Gas Turbine | 179659 | Major Inspection (MI) | 552131 | 2026-11-15 | 2027-01-11
9FA.03 | Europe | 298405 | Gas Turbine | 179842 | Stand Alone Large Upgrade | 552230 | 2027-07-12 | 2027-12-07
9FA.03 | Asia | 299137 | Gas Turbine | 180726 | Major Inspection (MI) | 552749 | 2028-03-15 | 2028-06-19
9FA.03 | Asia | 809956 | Gas Turbine | 181180 | Hot Gas Path Inspection (HGPI) | 552903 | 2028-01-05 | 2028-02-03
9FA.03 | MENA | 299101 | Gas Turbine | 181795 | Major Inspection (MI) | 553335 | 2028-02-14 | 2028-03-13
9FA.03 | MENA | 299100 | Gas Turbine | 181797 | Major Inspection (MI) | 553336 | 2028-09-28 | 2028-10-26
9FA.03 | Europe | 298083 | Gas Turbine | 182040 | Major Inspection (MI) | 553513 | 2030-09-08 | 2030-10-30
9FA.03 | MENA | 298448 | Gas Turbine | 182112 | Large Call-Out | 553564 | 2026-01-30 | 2026-04-28
9FA.03 | China | 296440 | Gas Turbine | 182274 | Stand Alone Small Upgrade | 553745 | 2026-01-01 | 2026-03-31
9FA.03 | Europe | 298033 | Gas Turbine | 182573 | Large Call-Out | 553801 | 2026-09-28 | 2026-10-23
9FA.03 | Asia | 298967 | Gas Turbine | 182848 | Hot Gas Path Inspection (HGPI) |  | 2030-03-01 | 2030-03-15
9FA.03 | MENA | 299254 | Gas Turbine | 183071 | Large Call-Out | 554156 | 2026-10-15 | 2026-11-05
9FA.03 | MENA | 299253 | Gas Turbine | 183072 | Large Call-Out | 554157 | 2026-09-15 | 2026-10-05
9FA.03 | MENA | 298587 | Gas Turbine | 183163 | Hot Gas Path Inspection (HGPI) | 554210 | 2030-03-06 | 2030-03-20
9FA.03 | Europe | 298279 | Gas Turbine | 183669 | Hot Gas Path Inspection (HGPI) | 554516 | 2026-07-24 | 2026-08-07
9FA.03 | Europe | 299320 | Gas Turbine | 183953 | Major Inspection (MI) | 554692 | 2029-06-18 | 2029-07-27
9FA.03 | MENA | 298444 | Gas Turbine | 186028 | Large Call-Out | 556174 | 2027-01-15 | 2027-02-15
9FA.03 | MENA | 298816 | Gas Turbine | 186157 | Combustion Inspection (CI) | 560553 | 2027-09-25 | 2027-10-16
9FA.03 | MENA | 298444 | Gas Turbine | 187415 | Large Call-Out | 502231 | 2027-01-15 | 2027-02-15
9FA.03 | Europe | 298033 | Gas Turbine | 189213 | Large Call-Out | 558296 | 2026-09-24 | 2026-10-28
9FA.03 | Europe | 297725 | Gas Turbine | 189665 | Combustion Inspection (CI) | 559688 | 2027-11-03 | 2027-11-17
9FA.03 | Europe | 297725 | Gas Turbine | 189667 | Hot Gas Path Inspection (HGPI) | 558556 | 2029-09-04 | 2029-09-18
9FA.03 | Europe | 298279 | Gas Turbine | 190261 | Major Inspection (MI) | 559038 | 2028-06-19 | 2028-11-06
9FA.03 | MENA | 298448 | Gas Turbine | 191166 | Hot Gas Path Inspection (HGPI) | 559719 | 2028-03-01 | 2028-03-21
9FA.03 | MENA | 299107 | Gas Turbine | 192364 | Large Call-Out | 560552 | 2026-03-21 | 2026-04-18
9FA.03 | China | 298523 | Gas Turbine | 193612 | Large Call-Out | 561486 | 2026-06-05 | 2026-06-17
9FA.03 | MENA | 298811 | Gas Turbine | 194098 | Stand Alone Small Upgrade | 561800 | 2027-01-15 | 2027-02-28
9FA.03 | Europe | 298376 | Gas Turbine | 194305 | Major Inspection (MI) | 561957 | 2029-09-03 | 2029-11-30
9FA.03 | Europe | 298377 | Gas Turbine | 194307 | Major Inspection (MI) | 561958 | 2030-06-03 | 2030-07-20
9FA.03 | China | 298426 | Gas Turbine | 194784 | Major Inspection (MI) |  | 2029-12-30 | 2030-01-27
9FA.03 | Europe | 298214 | Gas Turbine | 195859 | Major Inspection (MI) | 563195 | 2026-09-01 | 2026-09-29
9FA.03 | Europe | 298275 | Gas Turbine | 195860 | Major Inspection (MI) | 563194 | 2026-09-01 | 2026-09-29
9FA.03 | Europe | 298359 | Gas Turbine | 195884 | Hot Gas Path Inspection (HGPI) | 563210 | 2027-02-01 | 2027-02-15
9FA.03 | Europe | 297920 | Gas Turbine | 196101 | Major Inspection (MI) | 563394 | 2030-03-11 | 2030-04-11
9FA.04 | MENA | 299296 | Gas Turbine | 102835 | Hot Gas Path Inspection (HGPI) | 500123 | 2029-02-01 | 2029-03-02
9FA.04 | MENA | 299308 | Gas Turbine | 102905 | Hot Gas Path Inspection (HGPI) | 500415 | 2027-02-01 | 2027-03-02
9FA.04 | MENA | 299371 | Gas Turbine | 103839 | Major Inspection (MI) | 500034 | 2027-10-06 | 2027-10-29
9FA.04 | MENA | 299373 | Gas Turbine | 103912 | Major Inspection (MI) | 500035 | 2028-04-06 | 2028-05-20
9FA.04 | MENA | 299283 | Gas Turbine | 103921 | Hot Gas Path Inspection (HGPI) | 500120 | 2030-10-01 | 2030-10-30
9FA.04 | MENA | 299297 | Gas Turbine | 103991 | Hot Gas Path Inspection (HGPI) | 500122 | 2028-02-01 | 2028-03-01
9FA.04 | MENA | 299309 | Gas Turbine | 104284 | Hot Gas Path Inspection (HGPI) | 500416 | 2027-03-03 | 2027-04-01
9FA.04 | MENA | 299372 | Gas Turbine | 105866 | Major Inspection (MI) | 502310 | 2030-04-01 | 2030-05-15
9FA.04 | MENA | 299307 | Gas Turbine | 105893 | Hot Gas Path Inspection (HGPI) | 502337 | 2026-02-09 | 2026-03-14
9FA.04 | MENA | 299284 | Gas Turbine | 105902 | Hot Gas Path Inspection (HGPI) | 502346 | 2028-03-15 | 2028-04-13
9FA.04 | Europe | 297560 | Gas Turbine | 106641 | Major Inspection (MI) | 503014 | 2030-10-01 | 2030-10-30
9FA.04 | Europe | 297566 | Gas Turbine | 106668 | Hot Gas Path Inspection (HGPI) | 503041 | 2027-03-01 | 2027-03-31
9FA.04 | Europe | 297562 | Gas Turbine | 110535 | Major Inspection (MI) | 504791 | 2027-10-01 | 2027-10-30
9FA.04 | Europe | 298048 | Gas Turbine | 110700 | Major Inspection (MI) | 515514 | 2028-05-12 | 2028-06-22
9FA.04 | Europe | 297561 | Gas Turbine | 111498 | Major Inspection (MI) | 507313 | 2030-10-01 | 2030-10-31
9FA.04 | Europe | 297563 | Gas Turbine | 112503 | Major Inspection (MI) | 504793 | 2027-10-01 | 2027-10-30
9FA.04 | Latin America | 298101 | Gas Turbine | 112926 | Hot Gas Path Inspection (HGPI) | 512412 | 2028-08-14 | 2028-08-28
9FA.04 | Europe | 298155 | Gas Turbine | 115259 | Major Inspection (MI) | 509860 | 2028-10-02 | 2028-11-10
9FA.04 | Europe | 297558 | Gas Turbine | 120185 | Major Inspection (MI) | 504813 | 2029-04-01 | 2029-04-30
9FA.04 | Europe | 297566 | Gas Turbine | 121014 | Hot Gas Path Inspection (HGPI) | 503998 | 2028-10-05 | 2028-10-30
9FA.04 | Europe | 297559 | Gas Turbine | 123464 | Major Inspection (MI) | 504790 | 2029-04-01 | 2029-04-30
9FA.04 | Europe | 298089 | Gas Turbine | 137937 | Major Inspection (MI) | 541461 | 2027-10-04 | 2027-11-12
9FA.04 | MENA | 299346 | Gas Turbine | 141864 | Hot Gas Path Inspection (HGPI) | 545002 | 2028-07-28 | 2028-08-11
9FA.04 | MENA | 299345 | Gas Turbine | 141865 | Hot Gas Path Inspection (HGPI) | 545003 | 2028-07-28 | 2028-08-11
9FA.04 | MENA | 299344 | Gas Turbine | 141866 | Hot Gas Path Inspection (HGPI) | 545004 | 2028-04-14 | 2028-04-28
9FA.04 | MENA | 299343 | Gas Turbine | 141868 | Hot Gas Path Inspection (HGPI) | 545005 | 2028-04-14 | 2028-04-28
9FA.04 | MENA | 299415 | Gas Turbine | 141869 | Hot Gas Path Inspection (HGPI) | 545006 | 2028-10-10 | 2028-10-24
9FA.04 | Europe | 298047 | Gas Turbine | 144359 | Major Inspection (MI) | 529938 | 2026-07-07 | 2026-08-12
9FA.04 | MENA | 898982 | Gas Turbine | 145514 | Hot Gas Path Inspection (HGPI) | 546020 | 2026-11-10 | 2026-12-01
9FA.04 | MENA | 898983 | Gas Turbine | 145515 | Hot Gas Path Inspection (HGPI) | 546021 | 2027-10-01 | 2027-10-19
9FA.04 | Asia | 299522 | Gas Turbine | 147414 | Borescope Inspection (BI) | 530197 | 2028-03-07 | 2028-03-11
9FA.04 | MENA | 298460 | Gas Turbine | 150522 | Hot Gas Path Inspection (HGPI) | 541317 | 2029-01-15 | 2029-02-07
9FA.04 | MENA | 298683 | Gas Turbine | 151302 | Hot Gas Path Inspection (HGPI) | 532532 | 2027-10-01 | 2027-10-30
9FA.04 | MENA | 298684 | Gas Turbine | 151303 | Major Inspection (MI) | 532533 | 2029-07-23 | 2029-08-20
9FA.04 | China | 298615 | Gas Turbine | 152758 | Borescope Inspection (BI) | 533678 | 2026-04-15 | 2026-04-20
9FA.04 | China | 298615 | Gas Turbine | 152759 | Borescope Inspection (BI) | 533679 | 2026-09-15 | 2026-09-20
9FA.04 | China | 298615 | Gas Turbine | 152760 | Borescope Inspection (BI) | 533680 | 2027-04-15 | 2027-04-20
9FA.04 | China | 298615 | Gas Turbine | 152761 | Borescope Inspection (BI) | 533681 | 2027-09-15 | 2027-09-20
9FA.04 | China | 298616 | Gas Turbine | 152764 | Borescope Inspection (BI) | 533687 | 2026-04-15 | 2026-04-20
9FA.04 | China | 298616 | Gas Turbine | 152765 | Borescope Inspection (BI) | 533688 | 2026-09-15 | 2026-09-20
9FA.04 | China | 298616 | Gas Turbine | 152766 | Borescope Inspection (BI) | 533689 | 2027-04-15 | 2027-04-20
9FA.04 | China | 298616 | Gas Turbine | 152767 | Borescope Inspection (BI) | 533690 | 2027-09-15 | 2027-09-20
9FA.04 | China | 272004 | Gas Turbine | 154339 | Hot Gas Path Inspection (HGPI) |  | 2028-09-10 | 2028-09-24
9FA.04 | Latin America | 299523 | Gas Turbine | 154423 | Major Inspection (MI) | 545829 | 2028-03-07 | 2028-04-04
9FA.04 | Asia | 298717 | Gas Turbine | 154722 | Major Inspection (MI) | 547028 | 2026-03-27 | 2026-07-01
9FA.04 | MENA | 299216 | Gas Turbine | 154734 | Borescope Inspection (BI) | 535007 | 2026-12-15 | 2026-12-18
9FA.04 | MENA | 299217 | Gas Turbine | 154735 | Borescope Inspection (BI) | 535008 | 2026-11-15 | 2026-11-18
9FA.04 | Asia | 299522 | Gas Turbine | 154857 | Hot Gas Path Inspection (HGPI) | 545503 | 2028-08-27 | 2028-09-24
9FA.04 | China | 298438 | Gas Turbine | 154862 | Hot Gas Path Inspection (HGPI) | 540332 | 2028-03-20 | 2028-04-13
9FA.04 | China | 298439 | Gas Turbine | 154863 | Hot Gas Path Inspection (HGPI) | 540333 | 2029-03-20 | 2029-04-13
9FA.04 | MENA | 298459 | Gas Turbine | 155088 | Hot Gas Path Inspection (HGPI) | 541318 | 2029-10-01 | 2029-10-24
9FA.04 | MENA | 299414 | Gas Turbine | 155169 | Hot Gas Path Inspection (HGPI) | 545007 | 2029-12-05 | 2029-12-19
9FA.04 | MENA | 299416 | Gas Turbine | 155170 | Hot Gas Path Inspection (HGPI) | 545008 | 2029-03-15 | 2029-03-29
9FA.04 | MENA | 299417 | Gas Turbine | 155171 | Hot Gas Path Inspection (HGPI) | 545009 | 2029-07-04 | 2029-07-18
9FA.04 | MENA | 299042 | Gas Turbine | 155172 | Hot Gas Path Inspection (HGPI) | 545001 | 2029-06-20 | 2029-07-19
9FA.04 | MENA | 298801 | Gas Turbine | 155174 | Hot Gas Path Inspection (HGPI) | 546667 | 2027-02-26 | 2027-03-29
9FA.04 | MENA | 298803 | Gas Turbine | 155175 | Hot Gas Path Inspection (HGPI) | 552829 | 2028-03-06 | 2028-04-05
9FA.04 | MENA | 299368 | Gas Turbine | 155240 | Major Inspection (MI) | 538195 | 2027-12-01 | 2028-01-14
9FA.04 | MENA | 299370 | Gas Turbine | 155241 | Major Inspection (MI) | 538196 | 2029-02-25 | 2029-03-29
9FA.04 | MENA | 299369 | Gas Turbine | 155242 | Major Inspection (MI) | 538197 | 2028-09-15 | 2028-10-13
9FA.04 | Europe | 298401 | Gas Turbine | 155248 | Major Inspection (MI) | 546682 | 2026-09-15 | 2026-12-15
9FA.04 | MENA | 299163 | Gas Turbine | 155320 | Major Inspection (MI) | 538141 | 2026-11-07 | 2026-12-04
9FA.04 | MENA | 298813 | Gas Turbine | 155321 | Hot Gas Path Inspection (HGPI) | 538142 | 2027-11-15 | 2027-12-10
9FA.04 | MENA | 299164 | Gas Turbine | 155324 | Major Inspection (MI) | 538144 | 2027-10-21 | 2027-11-17
9FA.04 | MENA | 298814 | Gas Turbine | 155327 | Major Inspection (MI) |  | 2029-10-01 | 2029-10-29
9FA.04 | MENA | 299300 | Gas Turbine | 155351 | Hot Gas Path Inspection (HGPI) | 538153 | 2027-12-27 | 2028-01-25
9FA.04 | MENA | 299277 | Gas Turbine | 155360 | Hot Gas Path Inspection (HGPI) | 538161 | 2029-10-01 | 2029-10-31
9FA.04 | MENA | 299278 | Gas Turbine | 155361 | Hot Gas Path Inspection (HGPI) | 538484 | 2029-11-01 | 2029-12-01
9FA.04 | MENA | 299279 | Gas Turbine | 155362 | Hot Gas Path Inspection (HGPI) | 545010 | 2030-10-01 | 2030-10-31
9FA.04 | Asia | 299522 | Gas Turbine | 155733 | Borescope Inspection (BI) | 535728 | 2027-03-07 | 2027-03-11
9FA.04 | MENA | 298813 | Gas Turbine | 158969 | Major Inspection (MI) | 538148 | 2030-03-31 | 2030-04-28
9FA.04 | MENA | 299163 | Gas Turbine | 158970 | Hot Gas Path Inspection (HGPI) | 538150 | 2029-03-31 | 2029-04-14
9FA.04 | MENA | 299164 | Gas Turbine | 158976 | Hot Gas Path Inspection (HGPI) | 538151 | 2030-03-31 | 2030-04-14
9FA.04 | MENA | 299299 | Gas Turbine | 158978 | Hot Gas Path Inspection (HGPI) | 538152 | 2027-10-04 | 2027-11-02
9FA.04 | MENA | 299301 | Gas Turbine | 158980 | Hot Gas Path Inspection (HGPI) | 538154 | 2028-03-01 | 2028-03-30
9FA.04 | MENA | 299296 | Gas Turbine | 159019 | Major Inspection (MI) | 538167 | 2030-03-29 | 2030-04-26
9FA.04 | MENA | 299297 | Gas Turbine | 159022 | Major Inspection (MI) | 538168 | 2030-04-27 | 2030-05-25
9FA.04 | MENA | 298804 | Gas Turbine | 159024 | Hot Gas Path Inspection (HGPI) | 552831 | 2029-03-05 | 2029-04-05
9FA.04 | MENA | 298802 | Gas Turbine | 159025 | Major Inspection (MI) |  | 2030-02-17 | 2030-03-17
9FA.04 | MENA | 299373 | Gas Turbine | 159089 | Major Inspection (MI) | 538200 | 2027-09-21 | 2027-10-19
9FA.04 | MENA | 299372 | Gas Turbine | 159091 | Major Inspection (MI) | 538201 | 2026-11-05 | 2026-12-03
9FA.04 | China | 298439 | Gas Turbine | 160857 | Borescope Inspection (BI) | 539441 | 2026-11-20 | 2026-11-22
9FA.04 | China | 298438 | Gas Turbine | 160859 | Borescope Inspection (BI) | 539443 | 2026-12-20 | 2026-12-22
9FA.04 | China | 298438 | Gas Turbine | 160862 | Borescope Inspection (BI) | 539445 | 2026-10-20 | 2026-10-22
9FA.04 | China | 298439 | Gas Turbine | 160864 | Borescope Inspection (BI) | 539447 | 2026-09-28 | 2026-09-30
9FA.04 | Europe | 297992 | Gas Turbine | 163065 | Major Inspection (MI) | 541186 | 2029-06-01 | 2029-06-30
9FA.04 | Europe | 297993 | Gas Turbine | 163068 | Major Inspection (MI) | 541187 | 2029-06-15 | 2029-07-14
9FA.04 | MENA | 299298 | Gas Turbine | 167139 | Hot Gas Path Inspection (HGPI) | 544147 | 2027-11-07 | 2027-12-06
9FA.04 | Asia | 298716 | Gas Turbine | 168276 | Major Inspection (MI) | 546286 | 2027-03-27 | 2027-05-23
9FA.04 | China | 298615 | Gas Turbine | 168677 | Major Inspection (MI) | 545467 | 2028-12-12 | 2029-01-09
9FA.04 | China | 298616 | Gas Turbine | 168679 | Major Inspection (MI) | 545468 | 2029-12-15 | 2030-01-12
9FA.04 | MENA | 298683 | Gas Turbine | 170400 | Hot Gas Path Inspection (HGPI) |  | 2028-03-05 | 2028-03-19
9FA.04 | MENA | 898953 | Gas Turbine | 170813 | Hot Gas Path Inspection (HGPI) | 546781 | 2026-01-02 | 2026-02-04
9FA.04 | MENA | 299550 | Gas Turbine | 170817 | Hot Gas Path Inspection (HGPI) | 546783 | 2026-10-01 | 2026-10-22
9FA.04 | Europe | 299268 | Gas Turbine | 172526 | Hot Gas Path Inspection (HGPI) | 547806 | 2028-09-06 | 2028-10-06
9FA.04 | Europe | 299268 | Gas Turbine | 172527 | Major Inspection (MI) | 547807 | 2030-12-15 | 2031-01-12
9FA.04 | Asia | 298717 | Gas Turbine | 176249 | Major Inspection (MI) | 554446 | 2029-07-31 | 2030-01-31
9FA.04 | Asia | 298716 | Gas Turbine | 176250 | Major Inspection (MI) | 561280 | 2030-07-31 | 2031-01-31
9FA.04 | Asia | 299259 | Gas Turbine | 180689 | Major Inspection (MI) | 552709 | 2028-03-27 | 2028-05-23
9FA.04 | MENA | 299041 | Gas Turbine | 182992 | Hot Gas Path Inspection (HGPI) | 554095 | 2029-05-25 | 2029-06-08
9FA.04 | MENA | 299306 | Gas Turbine | 183630 | Major Inspection (MI) | 554498 | 2028-11-01 | 2028-11-28
9FA.04 | MENA | 299307 | Gas Turbine | 183634 | Major Inspection (MI) | 554499 | 2030-03-01 | 2030-03-28
9FA.04 | MENA | 299217 | Gas Turbine | 183666 | Major Inspection (MI) | 554515 | 2030-11-20 | 2030-12-18
9FA.04 | Europe | 298401 | Gas Turbine | 183711 | Major Inspection (MI) | 554536 | 2026-04-22 | 2026-05-20
9FA.04 | Europe | 298401 | Gas Turbine | 183713 | Hot Gas Path Inspection (HGPI) | 554537 | 2030-11-30 | 2030-12-14
9FA.04 | Europe | 298155 | Gas Turbine | 183714 | Major Inspection (MI) | 554539 | 2027-03-12 | 2027-04-09
9FA.04 | Europe | 298089 | Gas Turbine | 183715 | Major Inspection (MI) | 554538 | 2027-03-12 | 2027-04-09
9FA.04 | MENA | 898950 | Gas Turbine | 183901 | Hot Gas Path Inspection (HGPI) | 554660 | 2030-03-31 | 2030-04-14
9FA.04 | MENA | 898952 | Gas Turbine | 183903 | Hot Gas Path Inspection (HGPI) | 554662 | 2030-09-30 | 2030-10-14
9FA.04 | Europe | 298153 | Gas Turbine | 188510 | Large Call-Out | 557823 | 2026-01-05 | 2026-01-27
9FA.04 | Europe | 298047 | Gas Turbine | 189093 | Stand Alone Large Upgrade | 558199 | 2029-06-01 | 2029-08-31
9FA.04 | Europe | 298048 | Gas Turbine | 189094 | Stand Alone Large Upgrade | 558200 | 2030-06-01 | 2030-08-31
9FA.04 | MENA | 299299 | Gas Turbine | 192371 | Hot Gas Path Inspection (HGPI) | 546228 | 2027-03-17 | 2027-04-15
9FA.04 | MENA | 298742 | Gas Turbine | 193144 | Hot Gas Path Inspection (HGPI) | 560951 | 2026-04-12 | 2026-05-03
9FA.04 | MENA | 298743 | Gas Turbine | 193147 | Hot Gas Path Inspection (HGPI) | 560953 | 2027-01-02 | 2027-01-31
9FA.04 | MENA | 299042 | Gas Turbine | 194058 | Large Call-Out | 561768 | 2026-05-04 | 2026-12-31
9FA.04 | Europe | 298048 | Gas Turbine | 194083 | Large Call-Out | 561784 | 2026-05-11 | 2026-06-08
9FA.04 | Europe | 297992 | Gas Turbine | 195185 | Large Call-Out | 562688 | 2026-06-12 | 2026-07-04
9FA.04 | MENA | 299278 | Gas Turbine | 195658 | Hot Gas Path Inspection (HGPI) | 563039 | 2028-07-25 | 2028-08-08
9FA.04 | MENA | 299277 | Gas Turbine | 195662 | Hot Gas Path Inspection (HGPI) | 563040 | 2028-10-03 | 2028-10-17
9FA.04 | MENA | 299279 | Gas Turbine | 195666 | Hot Gas Path Inspection (HGPI) | 563041 | 2030-01-08 | 2030-01-22
9FA.04 | MENA | 299296 | Gas Turbine | 196219 | Large Call-Out | 563490 | 2026-07-14 | 2026-08-18
9FA.04 | MENA | 299297 | Gas Turbine | 196220 | Large Call-Out | 563492 | 2026-07-14 | 2026-07-21
9FA.05 | Asia | 299682 | Gas Turbine | 162190 | Hot Gas Path Inspection (HGPI) | 540657 | 2029-09-01 | 2029-09-24
9FB.01 | Europe | 298440 | Gas Turbine | 116929 | Major Inspection (MI) | 516221 | 2028-11-01 | 2028-12-01
9FB.02 | MENA | 298669 | Gas Turbine | 106279 | Hot Gas Path Inspection (HGPI) | 502670 | 2026-05-06 | 2026-06-06
9FB.02 | MENA | 298670 | Gas Turbine | 106280 | Major Inspection (MI) | 502671 | 2026-02-04 | 2026-03-15
9FB.02 | Europe | 298414 | Gas Turbine | 106562 | Hot Gas Path Inspection (HGPI) | 502935 | 2026-07-13 | 2026-08-31
9FB.02 | Europe | 898772 | Gas Turbine | 106634 | Major Inspection (MI) | 503007 | 2028-09-10 | 2028-10-08
9FB.02 | Europe | 298585 | Gas Turbine | 112068 | Major Inspection (MI) | 515624 | 2028-09-04 | 2028-09-29
9FB.02 | Europe | 298584 | Gas Turbine | 113425 | Major Inspection (MI) | 511122 | 2027-09-06 | 2027-10-11
9FB.02 | Europe | 298410 | Gas Turbine | 119417 | Major Inspection (MI) | 509193 | 2027-04-14 | 2027-05-18
9FB.02 | MENA | 298668 | Gas Turbine | 125867 | Large Call-Out | 516753 | 2026-01-01 | 2026-01-21
9FB.02 | MENA | 898771 | Gas Turbine | 138886 | Borescope Inspection (BI) | 525396 | 2026-10-20 | 2026-10-24
9FB.02 | MENA | 898773 | Gas Turbine | 138891 | Borescope Inspection (BI) | 525401 | 2026-01-05 | 2026-01-07
9FB.02 | MENA | 898773 | Gas Turbine | 138892 | Borescope Inspection (BI) | 525402 | 2027-02-15 | 2027-02-19
9FB.02 | MENA | 898770 | Gas Turbine | 138898 | Borescope Inspection (BI) | 525408 | 2026-12-01 | 2026-12-05
9FB.02 | Europe | 298762 | Gas Turbine | 144394 | Hot Gas Path Inspection (HGPI) | 528777 | 2028-11-15 | 2028-12-04
9FB.02 | Europe | 298765 | Gas Turbine | 144398 | Hot Gas Path Inspection (HGPI) | 528498 | 2026-03-30 | 2026-06-07
9FB.02 | MENA | 298668 | Gas Turbine | 144405 | Hot Gas Path Inspection (HGPI) | 536780 | 2028-04-01 | 2028-04-30
9FB.02 | MENA | 898771 | Gas Turbine | 144408 | Major Inspection (MI) | 528979 | 2027-01-01 | 2027-01-29
9FB.02 | MENA | 898773 | Gas Turbine | 144411 | Major Inspection (MI) | 528980 | 2028-09-01 | 2028-10-20
9FB.02 | Europe | 298533 | Gas Turbine | 145206 | Major Inspection (MI) | 528929 | 2028-04-24 | 2028-05-31
9FB.02 | Europe | 298534 | Gas Turbine | 145676 | Major Inspection (MI) | 529205 | 2027-03-01 | 2027-06-10
9FB.02 | Europe | 298584 | Gas Turbine | 151900 | Borescope Inspection (BI) | 533005 | 2026-02-23 | 2026-11-25
9FB.02 | Europe | 298585 | Gas Turbine | 151904 | Borescope Inspection (BI) | 533009 | 2026-02-26 | 2026-02-28
9FB.02 | Europe | 298764 | Gas Turbine | 158015 | Major Inspection (MI) | 537525 | 2028-07-03 | 2028-09-07
9FB.02 | MENA | 898770 | Gas Turbine | 158884 | Major Inspection (MI) | 538106 | 2029-12-12 | 2030-01-09
9FB.02 | Europe | 298767 | Gas Turbine | 159038 | Hot Gas Path Inspection (HGPI) | 538174 | 2029-08-04 | 2029-08-18
9FB.02 | Europe | 298759 | Gas Turbine | 162025 | Major Inspection (MI) | 540436 | 2027-03-01 | 2027-04-30
9FB.02 | Europe | 898775 | Gas Turbine | 164432 | Hot Gas Path Inspection (HGPI) | 542315 | 2027-04-01 | 2027-04-30
9FB.02 | Europe | 898774 | Gas Turbine | 164434 | Hot Gas Path Inspection (HGPI) | 542316 | 2029-04-01 | 2029-04-30
9FB.02 | Europe | 298417 | Gas Turbine | 167032 | Major Inspection (MI) | 544055 | 2026-02-23 | 2026-05-18
9FB.02 | Europe | 298763 | Gas Turbine | 175648 | Major Inspection (MI) | 549755 | 2029-04-02 | 2029-06-08
9FB.02 | Europe | 298761 | Gas Turbine | 175651 | Major Inspection (MI) | 549756 | 2028-04-03 | 2028-06-09
9FB.02 | Europe | 298765 | Gas Turbine | 175652 | Major Inspection (MI) | 549757 | 2030-04-01 | 2030-06-07
9FB.02 | Europe | 298760 | Gas Turbine | 182859 | Hot Gas Path Inspection (HGPI) | 553998 | 2029-04-01 | 2029-04-20
9FB.02 | Europe | 298421 | Gas Turbine | 183441 | Major Inspection (MI) | 554386 | 2028-09-14 | 2028-10-23
9FB.02 | MENA | 298669 | Gas Turbine | 187652 | Hot Gas Path Inspection (HGPI) |  | 2026-06-14 | 2026-06-28
9FB.02 | Europe | 298412 | Gas Turbine | 187653 | Hot Gas Path Inspection (HGPI) | 557285 | 2028-04-19 | 2028-05-26
9FB.02 | Europe | 298763 | Gas Turbine | 187659 | Major Inspection (MI) |  | 2028-12-26 | 2029-01-23
9FB.02 | Europe | 298765 | Gas Turbine | 187660 | Major Inspection (MI) |  | 2029-12-18 | 2030-01-15
9FB.02 | Europe | 298759 | Gas Turbine | 187693 | Major Inspection (MI) |  | 2026-10-31 | 2026-11-28
9FB.02 | Europe | 298420 | Gas Turbine | 189095 | Stand Alone Large Upgrade | 558201 | 2029-01-01 | 2029-04-30
9FB.02 | Europe | 298761 | Gas Turbine | 193876 | Large Call-Out | 561600 | 2027-07-07 | 2027-07-27
9FB.02 | MENA | 298668 | Gas Turbine | 196152 | Large Call-Out |  | 2026-11-15 | 2026-11-26
9FB.02 | MENA | 298669 | Gas Turbine | 196153 | Large Call-Out |  | 2026-10-15 | 2026-10-26
9FB.03 | Europe | 898780 | Gas Turbine | 106352 | Combustion Inspection (CI) | 502725 | 2030-05-04 | 2030-05-17
9FB.03 | China | 898795 | Gas Turbine | 107471 | Large Call-Out | 504590 | 2027-03-01 | 2027-03-31
9FB.03 | China | 898797 | Gas Turbine | 108603 | Large Call-Out | 507235 | 2030-04-01 | 2030-04-20
9FB.03 | Europe | 898791 | Gas Turbine | 112730 | Major Inspection (MI) | 503652 | 2029-04-01 | 2029-04-30
9FB.03 | Europe | 898781 | Gas Turbine | 120490 | Major Inspection (MI) | 503483 | 2026-04-05 | 2026-10-01
9FB.03 | Europe | 898782 | Gas Turbine | 120908 | Major Inspection (MI) | 513305 | 2026-04-11 | 2026-10-01
9FB.03 | China | 898798 | Gas Turbine | 144420 | Hot Gas Path Inspection (HGPI) | 535599 | 2027-10-10 | 2027-11-13
9FB.03 | China | 898786 | Gas Turbine | 144425 | Hot Gas Path Inspection (HGPI) | 546317 | 2026-03-23 | 2026-04-18
9FB.03 | China | 898783 | Gas Turbine | 144426 | Hot Gas Path Inspection (HGPI) | 546318 | 2027-10-31 | 2027-11-14
9FB.03 | China | 898805 | Gas Turbine | 144451 | Hot Gas Path Inspection (HGPI) | 532129 | 2027-03-01 | 2027-03-30
9FB.03 | Europe | 898793 | Gas Turbine | 148642 | Hot Gas Path Inspection (HGPI) | 538216 | 2028-03-01 | 2028-03-27
9FB.03 | Europe | 898790 | Gas Turbine | 151994 | Major Inspection (MI) | 533082 | 2027-05-17 | 2027-07-02
9FB.03 | China | 898796 | Gas Turbine | 155559 | Borescope Inspection (BI) | 535595 | 2026-12-14 | 2026-12-17
9FB.03 | China | 898798 | Gas Turbine | 155560 | Borescope Inspection (BI) | 535596 | 2026-03-23 | 2026-03-27
9FB.03 | China | 898804 | Gas Turbine | 158110 | Combustion Inspection (CI) | 553355 | 2028-10-07 | 2028-10-17
9FB.03 | China | 898786 | Gas Turbine | 158579 | Combustion Inspection (CI) | 554494 | 2028-05-31 | 2028-06-10
9FB.03 | China | 898784 | Gas Turbine | 158580 | Hot Gas Path Inspection (HGPI) | 554493 | 2028-05-14 | 2028-06-09
9FB.03 | China | 898783 | Gas Turbine | 158581 | Combustion Inspection (CI) |  | 2030-10-08 | 2030-10-15
9FB.03 | China | 898786 | Gas Turbine | 158582 | Major Inspection (MI) |  | 2030-10-31 | 2030-11-28
9FB.03 | China | 898805 | Gas Turbine | 158628 | Combustion Inspection (CI) | 558952 | 2029-06-28 | 2029-07-05
9FB.03 | China | 898804 | Gas Turbine | 160188 | Borescope Inspection (BI) | 538884 | 2026-11-24 | 2026-11-25
9FB.03 | China | 898805 | Gas Turbine | 160189 | Borescope Inspection (BI) | 538885 | 2026-11-26 | 2026-11-27
9FB.03 | China | 898783 | Gas Turbine | 160728 | Borescope Inspection (BI) | 539340 | 2026-09-20 | 2026-09-22
9FB.03 | China | 898784 | Gas Turbine | 160729 | Borescope Inspection (BI) | 539341 | 2026-09-23 | 2026-09-25
9FB.03 | China | 898786 | Gas Turbine | 160731 | Borescope Inspection (BI) | 539343 | 2026-07-20 | 2026-07-22
9FB.03 | Europe | 898788 | Gas Turbine | 164130 | Major Inspection (MI) | 542045 | 2028-04-17 | 2028-05-21
9FB.03 | China | 898789 | Gas Turbine | 167317 | Hot Gas Path Inspection (HGPI) | 544383 | 2028-08-22 | 2028-09-05
9FB.03 | China | 898784 | Gas Turbine | 172683 | Combustion Inspection (CI) |  | 2030-06-20 | 2030-06-27
9FB.03 | Europe | 898779 | Gas Turbine | 180339 | Major Inspection (MI) | 552475 | 2028-09-04 | 2028-10-13
9FB.03 | China | 898795 | Gas Turbine | 182302 | Combustion Inspection (CI) | 553673 | 2027-05-15 | 2027-05-26
9FB.03 | China | 898797 | Gas Turbine | 182303 | Combustion Inspection (CI) | 553674 | 2026-06-01 | 2026-06-12
9FB.03 | China | 898789 | Gas Turbine | 186663 | Large Call-Out | 556568 | 2026-05-28 | 2026-06-15
9FB.03 | China | 898789 | Gas Turbine | 187206 | Large Call-Out | 556951 | 2026-06-16 | 2026-06-25
9FB.03 | Europe | 898781 | Gas Turbine | 187628 | Major Inspection (MI) |  | 2026-01-05 | 2026-02-02
9FB.03 | Europe | 898782 | Gas Turbine | 187629 | Major Inspection (MI) |  | 2026-01-31 | 2026-02-28
9FB.03 | China | 898805 | Gas Turbine | 188173 | Large Call-Out | 557568 | 2026-01-15 | 2026-01-29
9FB.03 | China | 898804 | Gas Turbine | 191878 | Large Call-Out | 560296 | 2026-09-07 | 2026-09-25
9FB.03 | China | 898797 | Gas Turbine | 193272 | Combustion Inspection (CI) | 561053 | 2028-06-20 | 2028-06-30
9FB.03 | Europe | 898788 | Gas Turbine | 193884 | Stand Alone Small Upgrade | 563192 | 2026-09-06 | 2026-09-19
9FB.03 | China | 898797 | Gas Turbine | 196291 | Large Call-Out |  | 2026-10-01 | 2026-10-23
9FB.FA | Europe | 298757 | Gas Turbine | 151959 | Borescope Inspection (BI) | 533052 | 2026-01-20 | 2026-01-24
9FB.FA | Europe | 298758 | Gas Turbine | 151960 | Borescope Inspection (BI) | 533053 | 2026-02-02 | 2026-02-07
9FB.FA | Europe | 298757 | Gas Turbine | 151968 | Hot Gas Path Inspection (HGPI) | 533059 | 2028-02-07 | 2028-02-27
9FB.FA | Europe | 298758 | Gas Turbine | 151970 | Hot Gas Path Inspection (HGPI) | 533060 | 2028-02-14 | 2028-03-05
9FB.FA | Europe | 298525 | Gas Turbine | 166718 | Hot Gas Path Inspection (HGPI) | 543830 | 2026-11-02 | 2027-01-20
9FB.FA | Europe | 298526 | Gas Turbine | 166720 | Hot Gas Path Inspection (HGPI) | 543831 | 2027-02-04 | 2027-03-01
9FB.FA | Europe | 298757 | Gas Turbine | 187665 | Hot Gas Path Inspection (HGPI) | 557289 | 2026-12-06 | 2026-12-20
9FB.FA | Europe | 298758 | Gas Turbine | 187667 | Hot Gas Path Inspection (HGPI) | 557290 | 2027-02-24 | 2027-03-10
9FB.FA | Europe | 298757 | Gas Turbine | 191758 | Large Call-Out | 560092 | 2026-03-05 | 2026-04-18
9H2 | Latin America | 335X981 | Generator | 165897 | Major Inspection (Robotic) | 543267 | 2028-07-18 | 2028-08-15
9H2 | Europe | 335X937 | Generator | 166306 | Major Inspection (Rotor Out) | 534576 | 2026-11-10 | 2026-12-13
9H2 | Europe | 335X983 | Generator | 166307 | Major Inspection (Robotic) | 534578 | 2026-10-04 | 2026-11-03
9H2 | Europe | 335X938 | Generator | 166308 | Major Inspection (Robotic) | 543540 | 2027-06-18 | 2027-07-16
9H2 | Europe | 335X984 | Generator | 166309 | Minor Inspection | 534577 | 2027-05-02 | 2027-05-20
9H2 | Europe | 335X937 | Generator | 166311 | Minor Inspection | 543541 | 2029-09-23 | 2029-10-07
9H2 | Europe | 335X983 | Generator | 166313 | Minor Inspection | 543542 | 2029-05-01 | 2029-05-25
9H2 | Europe | 335X984 | Generator | 166314 | Major Inspection (Robotic) | 543543 | 2029-10-28 | 2029-11-25
9H2 | Europe | 335X938 | Generator | 166317 | Major Inspection (Rotor Out) | 543544 | 2027-10-24 | 2027-11-24
9H2 | Europe | 335X937 | Generator | 179499 | Minor Inspection | 552062 | 2030-04-01 | 2030-04-29
9H2 | Europe | 335X983 | Generator | 179502 | Minor Inspection | 552063 | 2030-11-10 | 2030-12-08
9H2 | MENA | 335X979 | Generator | 180171 | Major Inspection (Robotic) | 552403 | 2026-11-15 | 2026-12-14
9H2 | Europe | 335X984 | Generator | 192300 | Minor Inspection | 560463 | 2030-05-29 | 2030-06-12
9H2 | MENA | 335X977 | Generator | 192822 | Minor Inspection | 560028 | 2028-10-01 | 2028-10-18
9HA.01 | MENA | 899011 | Gas Turbine | 105929 | Major Inspection (MI) | 502373 | 2026-02-01 | 2026-08-31
9HA.01 | MENA | 899010 | Gas Turbine | 105930 | Major Inspection (MI) | 502374 | 2026-02-07 | 2026-04-20
9HA.01 | MENA | 899021 | Gas Turbine | 130977 | Major Inspection (MI) | 523705 | 2026-01-08 | 2026-02-21
9HA.01 | MENA | 899011 | Gas Turbine | 146661 | Combustion Inspection (CI) | 537571 | 2028-01-01 | 2028-01-13
9HA.01 | MENA | 899010 | Gas Turbine | 146662 | Combustion Inspection (CI) | 540551 | 2028-01-01 | 2028-01-13
9HA.01 | MENA | 899011 | Gas Turbine | 146663 | Hot Gas Path Inspection (HGPI) | 541063 | 2030-02-01 | 2030-02-22
9HA.01 | MENA | 899015 | Gas Turbine | 146664 | Combustion Inspection (CI) | 540516 | 2027-03-28 | 2027-04-09
9HA.01 | MENA | 899012 | Gas Turbine | 146665 | Combustion Inspection (CI) | 540515 | 2027-03-15 | 2027-03-27
9HA.01 | MENA | 899015 | Gas Turbine | 146666 | Hot Gas Path Inspection (HGPI) | 541057 | 2028-10-01 | 2028-10-30
9HA.01 | Europe | 899004 | Gas Turbine | 146730 | Hot Gas Path Inspection (HGPI) | 534094 | 2026-12-20 | 2027-01-03
9HA.01 | Asia | 899032 | Gas Turbine | 146778 | Major Inspection (MI) | 550257 | 2026-04-03 | 2026-06-27
9HA.01 | Asia | 899037 | Gas Turbine | 146779 | Major Inspection (MI) | 546280 | 2027-04-02 | 2027-05-30
9HA.01 | MENA | 899013 | Gas Turbine | 146840 | Combustion Inspection (CI) | 540311 | 2027-02-01 | 2027-02-13
9HA.01 | MENA | 899014 | Gas Turbine | 146841 | Combustion Inspection (CI) | 540312 | 2027-02-01 | 2027-02-13
9HA.01 | MENA | 899013 | Gas Turbine | 146842 | Hot Gas Path Inspection (HGPI) | 541060 | 2028-09-01 | 2028-09-30
9HA.01 | MENA | 899029 | Gas Turbine | 146858 | Major Inspection (MI) | 533498 | 2027-01-14 | 2027-02-22
9HA.01 | MENA | 899048 | Gas Turbine | 146866 | Hot Gas Path Inspection (HGPI) | 550360 | 2027-11-16 | 2027-12-10
9HA.01 | MENA | 899056 | Gas Turbine | 146869 | Hot Gas Path Inspection (HGPI) | 550361 | 2028-11-15 | 2028-12-09
9HA.01 | Europe | 899054 | Gas Turbine | 148592 | Combustion Inspection (CI) | 530827 | 2026-04-05 | 2026-06-04
9HA.01 | MENA | 899010 | Gas Turbine | 148634 | Stand Alone Small Upgrade | 530864 | 2026-02-09 | 2026-06-30
9HA.01 | Asia | 899016 | Gas Turbine | 155853 | Borescope Inspection (BI) | 550745 | 2026-10-15 | 2026-10-17
9HA.01 | Europe | 899054 | Gas Turbine | 157707 | Borescope Inspection (BI) | 537263 | 2026-04-01 | 2026-04-11
9HA.01 | Europe | 899054 | Gas Turbine | 157708 | Borescope Inspection (BI) | 537264 | 2026-10-17 | 2026-10-31
9HA.01 | MENA | 899029 | Gas Turbine | 158950 | Combustion Inspection (CI) |  | 2028-12-15 | 2028-12-22
9HA.01 | MENA | 899021 | Gas Turbine | 158952 | Hot Gas Path Inspection (HGPI) | 538136 | 2029-12-01 | 2029-12-15
9HA.01 | MENA | 899019 | Gas Turbine | 158953 | Hot Gas Path Inspection (HGPI) | 538137 | 2028-12-01 | 2028-12-15
9HA.01 | Europe | 899076 | Gas Turbine | 159114 | Hot Gas Path Inspection (HGPI) | 538215 | 2030-09-04 | 2030-09-18
9HA.01 | MENA | 899036 | Gas Turbine | 159563 | Hot Gas Path Inspection (HGPI) | 538575 | 2026-11-17 | 2026-12-11
9HA.01 | Asia | 899016 | Gas Turbine | 161769 | Major Inspection (MI) | 546946 | 2029-07-10 | 2029-11-26
9HA.01 | Asia | 899017 | Gas Turbine | 162033 | Major Inspection (MI) | 550743 | 2028-09-16 | 2028-10-14
9HA.01 | Asia | 899032 | Gas Turbine | 162034 | Major Inspection (MI) | 561134 | 2030-04-01 | 2030-05-15
9HA.01 | Asia | 899058 | Gas Turbine | 162330 | Combustion Inspection (CI) | 550552 | 2027-01-10 | 2027-01-21
9HA.01 | Asia | 899059 | Gas Turbine | 162331 | Combustion Inspection (CI) | 550792 | 2026-10-05 | 2026-10-16
9HA.01 | Asia | 899058 | Gas Turbine | 162332 | Hot Gas Path Inspection (HGPI) | 549572 | 2028-11-07 | 2028-11-30
9HA.01 | Asia | 899059 | Gas Turbine | 162333 | Hot Gas Path Inspection (HGPI) | 556807 | 2028-12-01 | 2028-12-24
9HA.01 | China | 899023 | Gas Turbine | 162384 | Hot Gas Path Inspection (HGPI) | 541632 | 2029-04-08 | 2029-05-17
9HA.01 | MENA | 899029 | Gas Turbine | 162697 | Hot Gas Path Inspection (HGPI) | 540970 | 2030-12-03 | 2030-12-17
9HA.01 | Europe | 899054 | Gas Turbine | 162753 | Hot Gas Path Inspection (HGPI) | 550184 | 2028-04-02 | 2028-04-28
9HA.01 | Europe | 899054 | Gas Turbine | 162754 | Combustion Inspection (CI) |  | 2030-03-13 | 2030-03-20
9HA.01 | MENA | 899012 | Gas Turbine | 162814 | Hot Gas Path Inspection (HGPI) | 541058 | 2028-10-31 | 2028-11-29
9HA.01 | MENA | 899015 | Gas Turbine | 162816 | Combustion Inspection (CI) |  | 2029-07-14 | 2029-07-21
9HA.01 | MENA | 899012 | Gas Turbine | 162817 | Combustion Inspection (CI) |  | 2030-11-16 | 2030-11-23
9HA.01 | MENA | 899014 | Gas Turbine | 162826 | Hot Gas Path Inspection (HGPI) | 541061 | 2028-09-01 | 2028-09-30
9HA.01 | MENA | 899013 | Gas Turbine | 162828 | Combustion Inspection (CI) |  | 2030-08-21 | 2030-08-28
9HA.01 | MENA | 899014 | Gas Turbine | 162829 | Combustion Inspection (CI) |  | 2030-02-19 | 2030-02-26
9HA.01 | MENA | 899010 | Gas Turbine | 162836 | Hot Gas Path Inspection (HGPI) | 541064 | 2030-02-01 | 2030-02-22
9HA.01 | Asia | 899024 | Gas Turbine | 168207 | Hot Gas Path Inspection (HGPI) | 552229 | 2030-02-10 | 2030-02-24
9HA.01 | Asia | 899024 | Gas Turbine | 168208 | Combustion Inspection (CI) |  | 2027-12-31 | 2028-01-07
9HA.01 | Asia | 899044 | Gas Turbine | 168210 | Hot Gas Path Inspection (HGPI) | 551948 | 2029-12-31 | 2030-01-14
9HA.01 | Asia | 899044 | Gas Turbine | 168211 | Combustion Inspection (CI) |  | 2027-12-31 | 2028-01-07
9HA.01 | Europe | 899043 | Gas Turbine | 172416 | Hot Gas Path Inspection (HGPI) | 547716 | 2029-08-14 | 2029-09-10
9HA.01 | Europe | 899043 | Gas Turbine | 172662 | Combustion Inspection (CI) | 547874 | 2027-03-03 | 2027-03-14
9HA.01 | Europe | 899045 | Gas Turbine | 174779 | Combustion Inspection (CI) | 550402 | 2027-05-15 | 2027-05-26
9HA.01 | Europe | 899045 | Gas Turbine | 174780 | Hot Gas Path Inspection (HGPI) | 550419 | 2029-09-30 | 2029-10-27
9HA.01 | MENA | 899056 | Gas Turbine | 176170 | Combustion Inspection (CI) |  | 2028-11-20 | 2028-12-01
9HA.01 | MENA | 899048 | Gas Turbine | 176172 | Major Inspection (MI) | 550077 | 2029-12-08 | 2030-01-05
9HA.01 | MENA | 899036 | Gas Turbine | 176175 | Combustion Inspection (CI) |  | 2030-11-01 | 2030-11-08
9HA.01 | MENA | 899056 | Gas Turbine | 176178 | Major Inspection (MI) | 550078 | 2030-11-14 | 2030-12-12
9HA.01 | Europe | 899042 | Gas Turbine | 176325 | Combustion Inspection (CI) | 557357 | 2027-04-18 | 2027-05-16
9HA.01 | Europe | 899042 | Gas Turbine | 176326 | Hot Gas Path Inspection (HGPI) | 557935 | 2029-05-06 | 2029-06-07
9HA.01 | Europe | 899042 | Gas Turbine | 176327 | Combustion Inspection (CI) |  | 2030-09-18 | 2030-09-25
9HA.01 | Europe | 899003 | Gas Turbine | 177993 | Combustion Inspection (CI) | 551284 | 2028-04-29 | 2028-08-01
9HA.01 | MENA | 899015 | Gas Turbine | 181571 | Hot Gas Path Inspection (HGPI) | 553149 | 2027-01-01 | 2027-01-20
9HA.01 | MENA | 899012 | Gas Turbine | 181591 | Hot Gas Path Inspection (HGPI) | 553163 | 2028-01-31 | 2028-02-08
9HA.01 | Europe | 899003 | Gas Turbine | 183452 | Large Call-Out |  | 2026-05-04 | 2026-05-22
9HA.01 | Europe | 899003 | Gas Turbine | 183456 | Large Call-Out | 554398 | 2026-05-23 | 2026-06-19
9HA.01 | China | 899023 | Gas Turbine | 187648 | Large Call-Out | 557759 | 2026-03-01 | 2026-03-25
9HA.01 | MENA | 899015 | Gas Turbine | 187937 | Hot Gas Path Inspection (HGPI) | 557402 | 2026-12-10 | 2026-12-31
9HA.01 | Asia | 899044 | Gas Turbine | 188710 | Combustion Inspection (CI) | 558211 | 2028-01-20 | 2028-01-27
9HA.01 | Asia | 899024 | Gas Turbine | 188714 | Combustion Inspection (CI) | 559115 | 2028-01-07 | 2028-01-14
9HA.01 | China | 899905 | Gas Turbine | 188883 | Combustion Inspection (CI) | 558841 | 2027-02-16 | 2027-03-02
9HA.01 | China | 899906 | Gas Turbine | 188884 | Combustion Inspection (CI) | 558797 | 2027-12-21 | 2027-12-28
9HA.01 | China | 899905 | Gas Turbine | 188885 | Hot Gas Path Inspection (HGPI) |  | 2030-07-11 | 2030-07-25
9HA.01 | Europe | 899076 | Gas Turbine | 193535 | Combustion Inspection (CI) | 561282 | 2028-08-01 | 2028-08-08
9HA.01 | Europe | 899060 | Gas Turbine | 193537 | Combustion Inspection (CI) | 561285 | 2028-08-01 | 2028-08-08
9HA.01 | MENA | 899012 | Gas Turbine | 196183 | Large Call-Out | 563562 | 2026-10-01 | 2026-10-20
9HA.01 | MENA | 899015 | Gas Turbine | 196184 | Large Call-Out | 563561 | 2026-10-01 | 2026-10-20
9HA.01 | MENA | 899013 | Gas Turbine | 196194 | Large Call-Out | 563560 | 2026-10-01 | 2026-10-20
9HA.01 | MENA | 899014 | Gas Turbine | 196195 | Large Call-Out | 563563 | 2026-10-01 | 2026-10-20
9HA.02 | Asia | 899040 | Gas Turbine | 131774 | Hot Gas Path Inspection (HGPI) | 521686 | 2028-03-19 | 2028-04-15
9HA.02 | Asia | 899026 | Gas Turbine | 146674 | Major Inspection (MI) | 542233 | 2027-11-07 | 2027-12-26
9HA.02 | Asia | 899025 | Gas Turbine | 146675 | Major Inspection (MI) | 542234 | 2028-09-10 | 2028-10-29
9HA.02 | Asia | 899055 | Gas Turbine | 146718 | Hot Gas Path Inspection (HGPI) | 550736 | 2026-05-08 | 2026-06-27
9HA.02 | Asia | 899057 | Gas Turbine | 146719 | Hot Gas Path Inspection (HGPI) | 550748 | 2026-09-20 | 2026-11-07
9HA.02 | Asia | 899052 | Gas Turbine | 146720 | Major Inspection (MI) | 550749 | 2027-09-27 | 2027-12-07
9HA.02 | Asia | 899041 | Gas Turbine | 146733 | Hot Gas Path Inspection (HGPI) | 538295 | 2028-07-01 | 2028-07-27
9HA.02 | Asia | 899040 | Gas Turbine | 146736 | Hot Gas Path Inspection (HGPI) | 538294 | 2028-12-01 | 2028-12-27
9HA.02 | China | 899062 | Gas Turbine | 146978 | Hot Gas Path Inspection (HGPI) | 545080 | 2028-10-01 | 2028-10-25
9HA.02 | Europe | 899047 | Gas Turbine | 147053 | Hot Gas Path Inspection (HGPI) | 556904 | 2028-03-20 | 2028-04-03
9HA.02 | Asia | 899040 | Gas Turbine | 155497 | Borescope Inspection (BI) | 535536 | 2026-02-15 | 2026-02-18
9HA.02 | Asia | 899040 | Gas Turbine | 155498 | Borescope Inspection (BI) | 535537 | 2026-05-01 | 2026-05-04
9HA.02 | Asia | 899040 | Gas Turbine | 155500 | Borescope Inspection (BI) | 535539 | 2026-07-30 | 2026-08-02
9HA.02 | Asia | 899040 | Gas Turbine | 155501 | Borescope Inspection (BI) | 535540 | 2026-10-01 | 2026-10-04
9HA.02 | Asia | 899040 | Gas Turbine | 155502 | Borescope Inspection (BI) | 535541 | 2026-05-17 | 2026-05-22
9HA.02 | Asia | 899041 | Gas Turbine | 155565 | Borescope Inspection (BI) | 535602 | 2026-02-16 | 2026-02-19
9HA.02 | Asia | 899041 | Gas Turbine | 155566 | Borescope Inspection (BI) | 535604 | 2026-05-02 | 2026-05-05
9HA.02 | Asia | 899041 | Gas Turbine | 155567 | Borescope Inspection (BI) | 535605 | 2026-07-31 | 2026-08-03
9HA.02 | Asia | 899041 | Gas Turbine | 155568 | Borescope Inspection (BI) | 535606 | 2026-10-02 | 2026-10-05
9HA.02 | Asia | 899041 | Gas Turbine | 155569 | Borescope Inspection (BI) | 535607 | 2026-08-18 | 2026-08-22
9HA.02 | Asia | 899040 | Gas Turbine | 159405 | Borescope Inspection (BI) | 538440 | 2027-01-23 | 2027-01-29
9HA.02 | Asia | 899041 | Gas Turbine | 159406 | Borescope Inspection (BI) | 538441 | 2027-01-18 | 2027-01-23
9HA.02 | Asia | 899052 | Gas Turbine | 159789 | Borescope Inspection (BI) | 550751 | 2027-05-05 | 2027-05-19
9HA.02 | Asia | 899055 | Gas Turbine | 159792 | Borescope Inspection (BI) | 550754 | 2027-05-26 | 2027-06-09
9HA.02 | Asia | 899057 | Gas Turbine | 159794 | Borescope Inspection (BI) | 550756 | 2026-05-01 | 2026-05-15
9HA.02 | Asia | 899057 | Gas Turbine | 159795 | Borescope Inspection (BI) | 550757 | 2027-12-01 | 2027-12-07
9HA.02 | China | 899063 | Gas Turbine | 160100 | Major Inspection (MI) | 538815 | 2026-03-22 | 2026-05-01
9HA.02 | Asia | 899034 | Gas Turbine | 160437 | Borescope Inspection (BI) | 539114 | 2026-10-24 | 2026-10-25
9HA.02 | Asia | 899035 | Gas Turbine | 160442 | Borescope Inspection (BI) | 539119 | 2026-05-15 | 2026-05-20
9HA.02 | Asia | 899035 | Gas Turbine | 160444 | Borescope Inspection (BI) | 539121 | 2026-09-30 | 2026-10-01
9HA.02 | China | 899064 | Gas Turbine | 162020 | Hot Gas Path Inspection (HGPI) | 540501 | 2028-10-11 | 2028-11-14
9HA.02 | China | 899063 | Gas Turbine | 162021 | Hot Gas Path Inspection (HGPI) | 543755 | 2028-02-27 | 2028-03-27
9HA.02 | Asia | 899055 | Gas Turbine | 162427 | Major Inspection (MI) | 550758 | 2028-04-03 | 2028-06-13
9HA.02 | Asia | 899057 | Gas Turbine | 162428 | Major Inspection (MI) | 553733 | 2028-09-25 | 2028-12-05
9HA.02 | Asia | 899051 | Gas Turbine | 162430 | Major Inspection (MI) | 554992 | 2027-07-03 | 2027-08-14
9HA.02 | Asia | 899049 | Gas Turbine | 162431 | Major Inspection (MI) | 554804 | 2027-10-09 | 2027-11-20
9HA.02 | Asia | 899053 | Gas Turbine | 162432 | Major Inspection (MI) | 554993 | 2027-08-14 | 2027-09-25
9HA.02 | Asia | 899034 | Gas Turbine | 162455 | Major Inspection (MI) | 550737 | 2027-10-02 | 2027-11-13
9HA.02 | Asia | 899035 | Gas Turbine | 162456 | Major Inspection (MI) | 554497 | 2028-02-05 | 2028-03-18
9HA.02 | Asia | 899026 | Gas Turbine | 162514 | Hot Gas Path Inspection (HGPI) | 559070 | 2030-06-23 | 2030-07-26
9HA.02 | Asia | 899034 | Gas Turbine | 175677 | Hot Gas Path Inspection (HGPI) |  | 2030-11-20 | 2030-12-04
9HA.02 | Europe | 899067 | Gas Turbine | 175771 | Hot Gas Path Inspection (HGPI) |  | 2030-03-03 | 2030-03-17
9HA.02 | Asia | 899050 | Gas Turbine | 176990 | Hot Gas Path Inspection (HGPI) | 550623 | 2029-06-26 | 2029-07-29
9HA.02 | Asia | 899065 | Gas Turbine | 176994 | Hot Gas Path Inspection (HGPI) | 550624 | 2029-08-07 | 2029-09-09
9HA.02 | Asia | 899053 | Gas Turbine | 180043 | Large Call-Out | 552358 | 2026-03-21 | 2026-04-16
9HA.02 | China | 899069 | Gas Turbine | 181227 | Combustion Inspection (CI) |  | 2026-12-30 | 2027-01-06
9HA.02 | China | 899069 | Gas Turbine | 181228 | Hot Gas Path Inspection (HGPI) |  | 2029-03-29 | 2029-04-12
9HA.02 | China | 899077 | Gas Turbine | 181230 | Combustion Inspection (CI) |  | 2028-01-01 | 2028-01-08
9HA.02 | Europe | 899061 | Gas Turbine | 182763 | Large Call-Out |  | 2028-06-07 | 2028-07-05
9HA.02 | Asia | 899051 | Gas Turbine | 183982 | Large Call-Out | 554710 | 2026-01-24 | 2026-02-15
9HA.02 | China | 899064 | Gas Turbine | 186328 | Large Call-Out | 556494 | 2026-04-05 | 2026-04-29
9HA.02 | China | 899063 | Gas Turbine | 186329 | Large Call-Out | 556493 | 2026-09-28 | 2026-10-28
9HA.02 | China | 899062 | Gas Turbine | 187074 | Hot Gas Path Inspection (HGPI) | 556842 | 2028-04-07 | 2028-05-01
9HA.02 | China | 899062 | Gas Turbine | 187115 | Hot Gas Path Inspection (HGPI) | 556886 | 2028-10-01 | 2028-11-04
9HA.02 | Asia | 899050 | Gas Turbine | 187349 | Large Call-Out | 550623 | 2027-12-01 | 2027-12-28
9HA.02 | Asia | 899034 | Gas Turbine | 189043 | Large Call-Out | 558162 | 2026-06-26 | 2026-08-30
9HA.02 | Asia | 899035 | Gas Turbine | 189044 | Large Call-Out | 558161 | 2026-04-26 | 2026-05-17
9HA.02 | Asia | 899050 | Gas Turbine | 189282 | Combustion Inspection (CI) | 558413 | 2027-12-01 | 2027-12-15
9HA.02 | Asia | 899065 | Gas Turbine | 189283 | Combustion Inspection (CI) | 558416 | 2028-02-01 | 2028-02-15
9HA.02 | China | 899084 | Gas Turbine | 189648 | Combustion Inspection (CI) | 561155 | 2027-12-31 | 2028-01-07
9HA.02 | China | 899080 | Gas Turbine | 189649 | Combustion Inspection (CI) | 561156 | 2029-01-30 | 2029-02-06
9HA.02 | China | 899084 | Gas Turbine | 189650 | Hot Gas Path Inspection (HGPI) | 561382 | 2030-03-30 | 2030-04-13
9HA.02 | Asia | 899049 | Gas Turbine | 190167 | Large Call-Out | 559162 | 2026-07-03 | 2026-08-01
50WG19L-080LL | SSA | 340X919 | Generator | 139109 | Minor Inspection | 501129 | 2027-07-01 | 2027-07-31
50WT19L-088LL3 | SSA | 340X914 | Generator | 139108 | Minor Inspection | 501134 | 2026-08-01 | 2026-08-25
50WT19L-088LL3 | SSA | 340X915 | Generator | 141734 | Major Inspection (Rotor Out) | 526929 | 2029-05-01 | 2029-05-31
50WT21H-120 | Europe | SG2619 | Generator | 131905 | Major Inspection (Rotor Out) | 503615 | 2028-10-16 | 2028-11-23
50WT21H-120 | Asia | SG2709 | Generator | 138357 | Minor Inspection | 525089 | 2026-07-19 | 2026-08-17
50WT21H-120 | Europe | SG2617 | Generator | 138704 | Minor Inspection | 525250 | 2027-08-20 | 2027-10-14
50WT21H-120 | Europe | SG2672 | Generator | 148664 | Major Inspection (Rotor Out) | 506623 | 2026-08-23 | 2026-11-18
50WT21H-120 | Europe | SG2662 | Generator | 148670 | Major Inspection (Rotor Out) | 530893 | 2028-04-07 | 2028-06-05
50WT21H-120 | Europe | SG2663 | Generator | 148677 | Minor Inspection | 530894 | 2027-05-07 | 2027-07-05
50WT21H-120 | Europe | SG2617 | Generator | 149762 | Borescope Inspection (BI) |  | 2026-06-02 | 2026-06-06
50WT21H-120 | MENA | SG2693 | Generator | 153872 | Minor Inspection | 534531 | 2026-09-15 | 2026-11-13
50WT21H-120 | MENA | SG2694 | Generator | 153875 | Minor Inspection | 534532 | 2029-09-30 | 2029-10-28
50WT21H-120 | MENA | SG2694 | Generator | 153876 | Minor Inspection | 534269 | 2026-01-25 | 2026-03-25
50WT21H-120 | MENA | SG2695 | Generator | 153880 | Minor Inspection | 534535 | 2027-10-01 | 2027-11-29
50WT21H-120 | Europe | SG2618 | Generator | 155274 | Large Call-Out | 535408 | 2026-06-12 | 2026-10-27
50WT21H-120 | MENA | SG2693 | Generator | 155713 | Minor Inspection | 535724 | 2030-01-02 | 2030-03-02
50WT21H-120 | Europe | HT100194 | Generator | 157508 | Major Inspection (Rotor Out) | 537108 | 2030-04-06 | 2030-07-25
50WT21H-120 | Europe | HT100187 | Generator | 157644 | Major Inspection (Rotor Out) | 537215 | 2029-07-07 | 2029-10-25
50WT21H-120 | Europe | HT100195 | Generator | 157646 | Major Inspection (Rotor Out) | 537216 | 2028-07-15 | 2028-11-02
50WT21H-120 | Europe | HT100191 | Generator | 157649 | Major Inspection (Rotor Out) | 537217 | 2029-03-03 | 2029-06-21
50WT21H-120 | Europe | HT100198 | Generator | 166838 | Major Inspection (Rotor Out) | 543937 | 2028-03-04 | 2028-06-22
50WT21H-120 | Europe | HT100207 | Generator | 166839 | Major Inspection (Rotor Out) | 543938 | 2030-07-06 | 2030-10-24
50WT21H-120 | Europe | HT100202 | Generator | 166841 | Major Inspection (Rotor Out) | 543939 | 2028-07-15 | 2028-11-02
50WT21H-120 | Europe | HT100208 | Generator | 166842 | Major Inspection (Rotor Out) | 543941 | 2029-04-07 | 2029-07-26
50WT21H-120 | Europe | HT100206 | Generator | 166843 | Major Inspection (Rotor Out) | 543942 | 2030-03-08 | 2030-06-26
50WT21H-120 | Europe |  | Generator | 170458 | Minor Inspection | 533732 | 2026-10-15 | 2026-11-18
50WT21H-120 | Europe | SG2621 | Generator | 175226 | Major Inspection (Rotor Out) | 549461 | 2028-08-14 | 2028-09-27
50WT21H-120 | Europe | SG2619 | Generator | 175477 | Large Call-Out | 550366 | 2027-10-25 | 2027-12-02
50WT21H-120 | MENA | SG2694 | Generator | 176193 | Minor Inspection | 534270 | 2026-02-09 | 2026-05-15
50WT21H-120 | MENA | SG2693 | Generator | 179668 | Minor Inspection | 534530 | 2026-10-20 | 2026-12-18
50WT21H-120 | MENA | SG2695 | Generator | 179669 | Minor Inspection | 534534 | 2027-10-20 | 2027-12-18
50WT21H-120 | Europe | SG2663 | Generator | 180448 | Major Inspection (Rotor Out) | 552533 | 2027-07-30 | 2027-10-28
50WT21H-120 | Europe | SG2662 | Generator | 180528 | Major Inspection (Robotic) | 552591 | 2030-07-08 | 2030-08-02
50WT21H-120 | Asia | SG2709 | Generator | 180692 | Minor Inspection | 552712 | 2030-12-09 | 2031-01-03
50WT21H-120 | Europe | SG2622 | Generator | 180744 | Major Inspection (Rotor Out) |  | 2029-10-08 | 2029-11-25
50WT21H-120 | Europe |  | Generator | 181871 | Minor Inspection | 553368 | 2028-03-01 | 2028-04-04
50WT21H-120 | Europe | SG2622 | Generator | 182679 | Major Inspection (Rotor Out) | 553877 | 2029-10-08 | 2029-11-25
50WT21H-120 | Asia | SG2704 | Generator | 187043 | Minor Inspection | 556813 | 2029-03-03 | 2029-03-28
50WT21H-120 | Asia | SG2623 | Generator | 188539 | Major Inspection (Robotic) | 557844 | 2027-04-16 | 2027-05-10
50WT21H-120 | MENA | SG2693 | Generator | 189544 | Major Inspection (Stator Rewind) | 558490 | 2026-10-20 | 2026-12-18
50WT21H-120 | Europe | SG2617 | Generator | 190574 | Large Call-Out |  | 2029-04-15 | 2029-08-15
50WT21H-120 | Europe | HT100162 | Generator | 191771 | Major Inspection (Rotor Out) | 560112 | 2029-03-27 | 2029-05-01
50WT21H-120 | Europe | HT100163 | Generator | 191772 | Minor Inspection | 560111 | 2027-03-22 | 2027-04-04
50WT21H-120 | Europe | HT100164 | Generator | 191786 | Minor Inspection | 560110 | 2027-02-26 | 2027-03-09
50WT21H-120 | Europe | HT100206 | Generator | 195754 | Major Inspection (Robotic) | 563107 | 2029-01-15 | 2029-01-24
50WT21H-120 EVO1 | Asia | SG2707 | Generator | 187045 | Major Inspection (Robotic) | 556814 | 2028-10-26 | 2028-11-20
50WX23Z-109 | MENA | GM224353 | Generator | 178945 | Minor Inspection | 547636 | 2029-01-15 | 2029-02-07
50WX23Z-109 | MENA | GM224352 | Generator | 192367 | Minor Inspection | 560527 | 2029-10-01 | 2029-10-24
50WX23Z-109LL | Europe | 814916 | Generator | 190894 | Major Inspection (Rotor Out) | 559491 | 2029-04-02 | 2029-05-31
50WY21Z-092 | Europe | 819226 | Generator | 157274 | Minor Inspection | 536898 | 2026-05-11 | 2026-06-27
50WY21Z-092 | Europe | GM224338 | Generator | 175346 | Major Inspection (Rotor Out) | 549556 | 2027-02-20 | 2027-04-17
50WY21Z-092 | Europe | 819225 | Generator | 179931 | Minor Inspection | 552288 | 2028-05-16 | 2028-06-20
50WY21Z-092 | Europe | 819226 | Generator | 179932 | Major Inspection (Robotic) | 552289 | 2029-09-11 | 2029-11-13
50WY21Z-092LLT | MENA | GG0281 | Generator | 144579 | Major Inspection (Rotor Out) | 521315 | 2026-10-15 | 2026-11-25
50WY21Z-092LLT | Europe | GG0210 | Generator | 154641 | Borescope Inspection (BI) | 534978 | 2028-05-08 | 2028-05-13
50WY21Z-092LLT | MENA | GG0286 | Generator | 177277 | Major Inspection (Robotic) | 546456 | 2030-03-16 | 2030-03-21
50WY21Z-092LLT | MENA | GG0248 | Generator | 190544 | Major Inspection (Rotor Out) | 559267 | 2028-02-01 | 2028-03-01
50WY21Z-092LLT | MENA | GG0263 | Generator | 190545 | Major Inspection (Rotor Out) | 559268 | 2028-03-01 | 2028-03-31
50WY21Z-092LLT | MENA | GG0265 | Generator | 190546 | Major Inspection (Rotor Out) | 559269 | 2028-10-01 | 2028-10-31
50WY21Z-092LLT | MENA | GG0266 | Generator | 190547 | Major Inspection (Rotor Out) | 559270 | 2030-04-01 | 2030-04-30
50WY21Z-092LLT | MENA | GG0249 | Generator | 190723 | Major Inspection (Rotor Out) | 559374 | 2028-10-01 | 2028-10-30
50WY21Z-092LLT | Latin America | GG0297 | Generator | 194068 | Major Inspection (Robotic) | 561779 | 2026-09-09 | 2026-10-08
50WY21Z-092LLT | Latin America | GG0296 | Generator | 194071 | Major Inspection (Robotic) | 561780 | 2026-10-13 | 2026-11-11
50WY21Z-092LLT | Latin America | DG1313 | Generator | 194326 | Major Inspection (Robotic) | 561975 | 2026-10-05 | 2026-11-04
50WY21Z-095 | MENA | GG0424 | Generator | 151877 | Minor Inspection | 521577 | 2026-01-07 | 2026-02-28
50WY21Z-095 | MENA | GG0421 | Generator | 159026 | Major Inspection (Rotor Out) | 532404 | 2026-12-15 | 2027-02-17
50WY21Z-095 | MENA | GG0424 | Generator | 159027 | Major Inspection (Robotic) | 538169 | 2030-09-01 | 2030-10-13
50WY21Z-095 | MENA | GG0420 | Generator | 159030 | Minor Inspection | 538170 | 2029-09-26 | 2029-11-06
50WY21Z-095 | MENA | GG0428 | Generator | 177266 | Major Inspection (Rotor Out) | 550862 | 2028-04-03 | 2028-05-04
50WY21Z-095 | MENA | GG0427 | Generator | 177268 | Major Inspection (Rotor Out) | 550863 | 2028-02-28 | 2028-03-30
50WY21Z-095 | MENA | DG1324 | Generator | 178975 | Minor Inspection | 551769 | 2028-02-05 | 2028-02-11
50WY21Z-095 | MENA | GG0406 | Generator | 180771 | Major Inspection (Rotor Out) | 552787 | 2028-05-20 | 2028-06-26
50WY21Z-095 | MENA | GG0405 | Generator | 180772 | Major Inspection (Robotic) | 552788 | 2029-01-01 | 2029-01-26
50WY21Z-095 | MENA | GG0409 | Generator | 181623 | Major Inspection (Robotic) | 553187 | 2029-08-15 | 2029-09-09
50WY21Z-095 | MENA | GG0406 | Generator | 187272 | Minor Inspection | 556339 | 2026-11-15 | 2026-11-20
50WY21Z-095 | MENA | GG0405 | Generator | 187382 | Minor Inspection | 556246 | 2026-11-22 | 2026-11-27
50WY21Z-095 | MENA | GG0408 | Generator | 189209 | Large Call-Out | 558292 | 2026-01-28 | 2026-05-15
50WY21Z-095 | MENA | GG0420 | Generator | 190751 | Major Inspection (Field Rewind) | 559497 | 2026-09-15 | 2027-01-15
50WY21Z-095 | MENA | GG0424 | Generator | 192524 | Major Inspection (Field Rewind) | 561075 | 2027-01-20 | 2027-05-22
50WY23Z | Europe | GG2648 | Generator | 149827 | Major Inspection (Robotic) | 531712 | 2026-07-06 | 2026-08-31
50WY23Z | Europe | GG2678 | Generator | 169060 | Major Inspection (Rotor Out) | 545791 | 2029-06-12 | 2029-07-29
50WY23Z | Europe | GG2691 | Generator | 169063 | Major Inspection (Rotor Out) | 545793 | 2029-06-23 | 2029-08-09
50WY23Z | Europe | GG2689 | Generator | 169066 | Major Inspection (Rotor Out) | 545794 | 2029-07-04 | 2029-08-20
50WY23Z-109LL | Europe | GG2605 | Generator | 190896 | Major Inspection (Rotor Out) | 559493 | 2027-05-27 | 2027-07-30
50WY23Z-109LL | Europe | GG2607 | Generator | 190899 | Major Inspection (Rotor Out) | 559496 | 2029-04-02 | 2029-05-31
51PA | Asia | T260 | Gas Turbine | 150367 | Major Inspection (MI) |  | 2026-12-05 | 2027-01-02
51PA | Asia | T260 | Gas Turbine | 150368 | Combustion Inspection (CI) |  | 2028-05-10 | 2028-05-17
51PA | NAM North America | 295353 | Gas Turbine | 157910 | Hot Gas Path Inspection (HGPI) | 537446 | 2026-03-16 | 2026-03-27
60WT21H-102 | Latin America | DG1109 | Generator | 131151 | Major Inspection (Rotor Out) | 513719 | 2027-07-07 | 2027-08-05
60WT21H-102 | Latin America | 811299 | Generator | 184539 | Major Inspection (Rotor Out) | 555096 | 2027-03-01 | 2027-04-14
60WT21H-102 | Latin America | 811299 | Generator | 184541 | Major Inspection (Rotor Out) | 544404 | 2027-03-01 | 2027-04-14
60WT21H-102 | NAM North America | 818199 | Generator | 190062 | Large Call-Out | 558947 | 2026-04-15 | 2026-04-28
60WX21Z-095 | NAM North America | 100058 | Generator | 177742 | Major Inspection (Robotic) |  | 2026-11-09 | 2026-11-13
60WY18L-066LLT | NAM North America | 819848 | Generator | 170031 | Minor Inspection | 538844 | 2026-04-20 | 2026-05-20
60WY18L-066LLT | NAM North America | 819846 | Generator | 170932 | Minor Inspection | 538852 | 2027-02-01 | 2027-03-03
60WY18L-066LLT | NAM North America | 819851 | Generator | 172505 | Minor Inspection | 538850 | 2026-11-02 | 2026-12-03
60WY18L-066LLT | NAM North America | 819850 | Generator | 175471 | Minor Inspection | 538847 | 2026-02-23 | 2026-03-27
60WY18L-066LLT | NAM North America | 819857 | Generator | 175775 | Major Inspection (Robotic) | 504595 | 2027-09-01 | 2027-09-29
60WY18L-066LLT | NAM North America | 819849 | Generator | 175778 | Major Inspection (Robotic) | 549845 | 2027-10-04 | 2027-11-05
60WY18L-066LLT | NAM North America | 819853 | Generator | 175779 | Minor Inspection | 549846 | 2028-02-28 | 2028-03-20
60WY18L-066LLT | NAM North America | 819856 | Generator | 175780 | Minor Inspection | 549847 | 2028-01-10 | 2028-02-22
60WY18L-066LLT | NAM North America | 819855 | Generator | 175782 | Major Inspection (Robotic) | 549848 | 2028-09-01 | 2028-09-26
60WY18L-066LLT | NAM North America | 819852 | Generator | 175785 | Minor Inspection | 549849 | 2029-02-17 | 2029-03-14
60WY18L-066LLT | NAM North America | 819847 | Generator | 175786 | Minor Inspection | 549850 | 2029-02-12 | 2029-03-12
60WY18L-066LLT | NAM North America | HM300525 | Generator | 182797 | Major Inspection (Rotor Out) | 554105 | 2026-02-15 | 2026-02-28
60WY18L-066LLT | NAM North America | 819854 | Generator | 183702 | Minor Inspection | 554531 | 2028-11-25 | 2028-12-20
60WY18L-066LLT | NAM North America | HM300525 | Generator | 183839 | Minor Inspection | 534189 | 2026-02-15 | 2026-03-07
60WY18L-066LLT | NAM North America | VG0114 | Generator | 183840 | Minor Inspection | 545911 | 2027-02-21 | 2027-03-14
60WY18L-066LLT | NAM North America | HM300525 | Generator | 183841 | Minor Inspection | 545913 | 2028-02-20 | 2028-03-05
60WY18L-066LLT | NAM North America | VG0114 | Generator | 183842 | Minor Inspection | 554608 | 2029-02-25 | 2029-03-09
60WY18L-066LLT | NAM North America | HM300525 | Generator | 183843 | Minor Inspection | 554609 | 2030-02-10 | 2030-03-08
60WY18L-066LLT | NAM North America | 819857 | Generator | 194667 | Minor Inspection | 555879 | 2027-09-01 | 2027-09-26
60WY18L-066LLT | NAM North America | 819850 | Generator | 195483 | Major Inspection (Robotic) | 562925 | 2030-01-24 | 2030-02-18
60WY18L-066LLT | NAM North America | 819851 | Generator | 195485 | Major Inspection (Robotic) | 562926 | 2030-04-30 | 2030-05-25
60WY18Z-078LL | Latin America | DG2465 | Generator | 167869 | Minor Inspection | 544802 | 2028-08-19 | 2028-09-18
60WY18Z-090LLT | Latin America | VG0354 | Generator | 149832 | Minor Inspection | 531715 | 2026-11-27 | 2027-01-05
60WY18Z-090LLT | Latin America | VG0355 | Generator | 149834 | Major Inspection (Rotor Out) | 531716 | 2026-07-14 | 2026-08-20
60WY18Z-090LLT | Latin America | VG0355 | Generator | 183509 | Major Inspection (Robotic) | 554430 | 2030-07-03 | 2030-08-01
60WY18Z-090LLT | Latin America | VG0355 | Generator | 185723 | Major Inspection (Robotic) | 555954 | 2028-07-03 | 2028-07-28
60WY18Z-090LLT | Latin America | VG0354 | Generator | 185724 | Major Inspection (Robotic) | 555955 | 2029-01-09 | 2029-02-03
60WY21Z | NAM North America | 811119 | Generator | 175492 | Minor Inspection | 549636 | 2027-03-19 | 2027-04-13
60WY21Z | NAM North America | 815516 | Generator | 179650 | Major Inspection (Stator Rewind) | 552124 | 2026-11-03 | 2026-12-19
60WY21Z | NAM North America | 815517 | Generator | 179651 | Major Inspection (Stator Rewind) | 552125 | 2029-03-02 | 2029-05-15
60WY21Z | NAM North America | 815518 | Generator | 179653 | Major Inspection (Stator Rewind) | 552127 | 2027-10-02 | 2027-12-15
60WY21Z | NAM North America | GM22429 | Generator | 185216 | Major Inspection (Rotor Out) | 551239 | 2027-04-15 | 2027-05-12
60WY21Z | NAM North America | 811119 | Generator | 189640 | Major Inspection (Rotor Out) | 549638 | 2030-03-02 | 2030-04-30
60WY23Z | Latin America | SG2454 | Generator | 131828 | Minor Inspection | 504425 | 2027-11-13 | 2027-12-18
60WY23Z | Latin America | SG2450 | Generator | 132549 | Major Inspection (Rotor Out) | 504424 | 2026-01-18 | 2026-02-23
60WY23Z | Latin America | HM301270 | Generator | 167695 | Major Inspection (Rotor Out) | 504427 | 2026-12-06 | 2027-01-17
60WY23Z | Latin America | SG2448 | Generator | 167697 | Minor Inspection | 504428 | 2027-01-10 | 2027-02-13
60WY23Z | Latin America | HM301270 | Generator | 167707 | Minor Inspection | 504436 | 2030-01-14 | 2030-02-18
60WY23Z | Latin America | SG2448 | Generator | 167708 | Minor Inspection | 504437 | 2030-02-10 | 2030-03-13
60WY23Z | Latin America | SG2450 | Generator | 167854 | Minor Inspection | 504429 | 2029-01-21 | 2029-02-26
60WY23Z | Latin America | SG2454 | Generator | 167856 | Minor Inspection | 504435 | 2029-10-01 | 2029-10-31
60WY23Z | Latin America | GG2500 | Generator | 167867 | Minor Inspection | 504431 | 2028-08-19 | 2028-09-18
60WY23Z | NAM North America | SG2416 | Generator | 169451 | Major Inspection (Robotic) | 521852 | 2026-09-21 | 2026-12-04
60WY23Z | Latin America | SG2427 | Generator | 183604 | Minor Inspection | 550497 | 2027-11-01 | 2027-12-06
60WY23Z | NAM North America | SG2429 | Generator | 184980 | Minor Inspection |  | 2029-03-05 | 2029-04-03
60WY23Z | NAM North America | SG2429 | Generator | 185084 | Major Inspection (Rotor Out) |  | 2029-04-13 | 2029-05-12
60WY23Z | NAM North America | HM301227 | Generator | 185098 | Major Inspection (Rotor Out) |  | 2029-04-17 | 2029-05-21
60WY23Z | NAM North America | SG2437 | Generator | 185102 | Major Inspection (Rotor Out) |  | 2029-10-05 | 2029-11-05
60WY23Z | NAM North America | SG2436 | Generator | 185109 | Major Inspection (Rotor Out) |  | 2029-10-02 | 2029-11-02
60WY23Z | NAM North America | SG2439 | Generator | 185129 | Minor Inspection |  | 2029-03-05 | 2029-03-19
60WY23Z | NAM North America | SG2422 | Generator | 185133 | Minor Inspection |  | 2029-10-08 | 2029-10-22
60WY23Z | NAM North America | SG2438 | Generator | 185138 | Major Inspection (Rotor Out) |  | 2029-04-03 | 2029-05-03
60WY23Z | Latin America | HM301270 | Generator | 195683 | Major Inspection (Robotic) | 504432 | 2027-12-18 | 2028-01-17
61B | SSA | 850142 | Gas Turbine | 105904 | Hot Gas Path Inspection (HGPI) | 502348 | 2026-07-17 | 2026-08-06
61B | SSA | 850136 | Gas Turbine | 105922 | Major Inspection (MI) | 502366 | 2026-03-09 | 2026-03-31
61B | Europe | EGG0040 | Gas Turbine | 106550 | Hot Gas Path Inspection (HGPI) | 502923 | 2029-08-31 | 2029-09-14
61B | China | 850059 | Gas Turbine | 108775 | Major Inspection (MI) |  | 2026-05-01 | 2026-05-29
61B | Latin America | 850115 | Gas Turbine | 109450 | Major Inspection (MI) | 508232 | 2028-02-01 | 2028-03-10
61B | Europe | 810336 | Gas Turbine | 109570 | Major Inspection (MI) | 540593 | 2027-10-31 | 2027-11-28
61B | Asia | 850212 | Gas Turbine | 111526 | Hot Gas Path Inspection (HGPI) |  | 2028-08-13 | 2028-08-27
61B | Asia | EGG0102 | Gas Turbine | 111901 | Major Inspection (MI) |  | 2026-01-12 | 2026-02-09
61B | Latin America | 900224 | Gas Turbine | 112769 | Combustion Inspection (CI) | 513011 | 2027-07-19 | 2027-07-26
61B | China | 850059 | Gas Turbine | 112991 | Major Inspection (MI) |  | 2026-05-01 | 2026-05-29
61B | Europe | 810314 | Gas Turbine | 114104 | Hot Gas Path Inspection (HGPI) | 510499 | 2026-01-26 | 2026-02-17
61B | Asia | 850214 | Gas Turbine | 115120 | Hot Gas Path Inspection (HGPI) |  | 2028-01-01 | 2028-01-15
61B | NAM North America | 297310 | Gas Turbine | 115433 | Hot Gas Path Inspection (HGPI) | 505733 | 2028-09-30 | 2028-10-14
61B | Asia | 850212 | Gas Turbine | 121001 | Hot Gas Path Inspection (HGPI) |  | 2028-08-13 | 2028-08-27
61B | Latin America | 900224 | Gas Turbine | 121452 | Major Inspection (MI) | 505218 | 2028-05-03 | 2028-06-06
61B | Asia | EGG0102 | Gas Turbine | 121664 | Major Inspection (MI) |  | 2026-01-12 | 2026-02-09
61B | Latin America | 850126 | Gas Turbine | 123345 | Combustion Inspection (CI) | 508409 | 2030-06-17 | 2030-06-24
61B | Latin America | 850126 | Gas Turbine | 123473 | Major Inspection (MI) | 508333 | 2029-03-17 | 2029-04-14
61B | Asia | 850214 | Gas Turbine | 123927 | Hot Gas Path Inspection (HGPI) |  | 2028-01-01 | 2028-01-15
61B | NAM North America | 297310 | Gas Turbine | 124615 | Combustion Inspection (CI) | 505728 | 2027-02-01 | 2027-02-07
61B | Asia | 900572 | Gas Turbine | 132959 | Hot Gas Path Inspection (HGPI) | 525142 | 2026-01-15 | 2026-02-04
61B | Europe | 810555 | Gas Turbine | 133076 | Major Inspection (MI) | 531312 | 2028-05-22 | 2028-06-19
61B | Europe | 850158 | Gas Turbine | 133080 | Major Inspection (MI) | 524633 | 2026-10-01 | 2026-10-30
61B | Asia | 850212 | Gas Turbine | 138984 | Major Inspection (MI) | 525477 | 2027-03-22 | 2027-04-30
61B | NAM North America | 297311 | Gas Turbine | 149740 | Major Inspection (MI) | 531654 | 2028-03-01 | 2028-04-15
61B | NAM North America | 810723 | Gas Turbine | 150339 | Hot Gas Path Inspection (HGPI) | 532073 | 2028-04-01 | 2028-04-15
61B | NAM North America | 810722 | Gas Turbine | 150340 | Hot Gas Path Inspection (HGPI) | 532074 | 2029-04-01 | 2029-04-15
61B | Asia | EGG0194 | Gas Turbine | 150365 | Major Inspection (MI) | 533236 | 2026-10-12 | 2026-11-20
61B | Asia | 850238 | Gas Turbine | 150366 | Hot Gas Path Inspection (HGPI) | 533237 | 2027-04-22 | 2027-05-06
61B | Asia | 297044 | Gas Turbine | 150497 | Hot Gas Path Inspection (HGPI) | 536560 | 2026-12-21 | 2027-01-03
61B | Asia | 900573 | Gas Turbine | 150575 | Hot Gas Path Inspection (HGPI) | 536562 | 2026-11-18 | 2026-12-08
61B | Asia | EGG0141 | Gas Turbine | 150700 | Hot Gas Path Inspection (HGPI) | 543192 | 2029-12-06 | 2029-12-20
61B | Asia | EGG0140 | Gas Turbine | 150701 | Combustion Inspection (CI) | 550738 | 2028-04-24 | 2028-05-01
61B | Latin America | 297106 | Gas Turbine | 150703 | Major Inspection (MI) | 532305 | 2028-04-16 | 2028-05-14
61B | China | 850056 | Gas Turbine | 150710 | Major Inspection (MI) | 546316 | 2026-04-27 | 2026-05-26
61B | Asia | 850232 | Gas Turbine | 150716 | Hot Gas Path Inspection (HGPI) | 536612 | 2029-02-17 | 2029-02-26
61B | Asia | 850224 | Gas Turbine | 150717 | Hot Gas Path Inspection (HGPI) | 543392 | 2028-07-22 | 2028-07-31
61B | Asia | 850061 | Gas Turbine | 150718 | Major Inspection (MI) | 543391 | 2028-01-13 | 2028-01-31
61B | Asia | 297585 | Gas Turbine | 150831 | Major Inspection (MI) | 536528 | 2027-01-15 | 2027-02-12
61B | Asia | 296672 | Gas Turbine | 150832 | Major Inspection (MI) | 536531 | 2028-01-12 | 2028-01-30
61B | Asia | 850144 | Gas Turbine | 150833 | Major Inspection (MI) | 541038 | 2027-06-14 | 2027-07-02
61B | Asia | 850149 | Gas Turbine | 150834 | Major Inspection (MI) | 541039 | 2027-10-10 | 2027-10-28
61B | Asia | 850170 | Gas Turbine | 150835 | Major Inspection (MI) | 541040 | 2028-09-05 | 2028-09-23
61B | SSA | 809938 | Gas Turbine | 150836 | Major Inspection (MI) | 540568 | 2026-11-13 | 2026-12-12
61B | SSA | 809939 | Gas Turbine | 150837 | Major Inspection (MI) | 540569 | 2027-04-15 | 2027-05-13
61B | NAM North America | 295362 | Gas Turbine | 150846 | Major Inspection (MI) | 532376 | 2026-09-21 | 2026-10-29
61B | NAM North America | 810723 | Gas Turbine | 150907 | Borescope Inspection (BI) | 532339 | 2026-03-29 | 2026-03-29
61B | NAM North America | 810722 | Gas Turbine | 150909 | Borescope Inspection (BI) | 532340 | 2026-03-27 | 2026-03-27
61B | Europe | 810336 | Gas Turbine | 151077 | Major Inspection (MI) | 543311 | 2026-09-01 | 2026-10-16
61B | NAM North America | 810405 | Gas Turbine | 151105 | Hot Gas Path Inspection (HGPI) | 532466 | 2026-05-04 | 2026-06-02
61B | NAM North America | 810404 | Gas Turbine | 151106 | Hot Gas Path Inspection (HGPI) | 534339 | 2027-04-01 | 2027-04-15
61B | Europe | 810314 | Gas Turbine | 151183 | Major Inspection (MI) | 543227 | 2030-08-13 | 2030-09-10
61B | NAM North America | 297311 | Gas Turbine | 151190 | Combustion Inspection (CI) | 546628 | 2027-04-01 | 2027-04-19
61B | Europe | 282125 | Gas Turbine | 151251 | Combustion Inspection (CI) | 552821 | 2027-02-25 | 2027-04-24
61B | Latin America | 296996 | Gas Turbine | 152367 | Hot Gas Path Inspection (HGPI) | 535304 | 2026-03-31 | 2026-05-11
61B | Asia | 900572 | Gas Turbine | 155751 | Borescope Inspection (BI) | 550796 | 2026-12-01 | 2026-12-03
61B | Asia | 900572 | Gas Turbine | 155753 | Borescope Inspection (BI) | 550798 | 2026-09-15 | 2026-09-16
61B | Asia | 850067 | Gas Turbine | 155755 | Borescope Inspection (BI) | 550799 | 2026-07-19 | 2026-07-19
61B | Asia | 850065 | Gas Turbine | 155757 | Borescope Inspection (BI) | 550800 | 2026-07-26 | 2026-07-26
61B | Asia | 297042 | Gas Turbine | 155769 | Borescope Inspection (BI) | 535760 | 2026-11-25 | 2026-11-26
61B | Asia | 297044 | Gas Turbine | 155774 | Borescope Inspection (BI) | 535764 | 2026-06-21 | 2026-06-22
61B | Asia | 850214 | Gas Turbine | 155978 | Major Inspection (MI) | 535869 | 2026-07-18 | 2026-08-17
61B | Asia | 297041 | Gas Turbine | 160434 | Borescope Inspection (BI) | 539111 | 2026-06-08 | 2026-06-09
61B | Asia | 297042 | Gas Turbine | 160435 | Borescope Inspection (BI) | 539112 | 2026-10-01 | 2026-10-02
61B | China | 850056 | Gas Turbine | 160724 | Borescope Inspection (BI) | 539336 | 2026-10-01 | 2026-10-03
61B | China | 850059 | Gas Turbine | 160726 | Borescope Inspection (BI) | 539338 | 2026-10-04 | 2026-10-06
61B | Europe | 297035 | Gas Turbine | 161014 | Combustion Inspection (CI) | 539589 | 2026-03-07 | 2026-03-19
61B | Europe | 282125 | Gas Turbine | 161776 | Borescope Inspection (BI) | 552823 | 2026-03-16 | 2026-03-20
61B | Asia | 850064 | Gas Turbine | 162792 | Major Inspection (MI) | 541041 | 2028-10-02 | 2028-10-20
61B | Asia | 296672 | Gas Turbine | 162794 | Hot Gas Path Inspection (HGPI) | 541042 | 2030-09-07 | 2030-09-21
61B | NAM North America | 810406 | Gas Turbine | 165115 | Major Inspection (MI) | 542818 | 2029-10-01 | 2029-10-29
61B | NAM North America | 810405 | Gas Turbine | 165117 | Major Inspection (MI) | 542819 | 2030-04-01 | 2030-04-29
61B | Asia | 850214 | Gas Turbine | 165342 | Hot Gas Path Inspection (HGPI) |  | 2030-03-10 | 2030-03-24
61B | Latin America | 296996 | Gas Turbine | 165663 | Major Inspection (MI) | 543136 | 2030-02-28 | 2030-03-28
61B | Asia | EGG0194 | Gas Turbine | 165712 | Combustion Inspection (CI) | 550635 | 2028-10-16 | 2028-10-23
61B | Asia | 850238 | Gas Turbine | 165713 | Combustion Inspection (CI) | 558891 | 2029-03-28 | 2029-04-04
61B | Asia | EGG0142 | Gas Turbine | 165761 | Hot Gas Path Inspection (HGPI) | 560103 | 2028-11-12 | 2028-11-26
61B | Asia | 297042 | Gas Turbine | 165848 | Major Inspection (MI) | 543238 | 2027-12-30 | 2028-01-27
61B | NAM North America | 295363 | Gas Turbine | 165956 | Major Inspection (MI) | 543314 | 2028-02-07 | 2028-03-20
61B | NAM North America | 295361 | Gas Turbine | 165958 | Hot Gas Path Inspection (HGPI) | 543315 | 2029-04-18 | 2029-05-16
61B | NAM North America | 295362 | Gas Turbine | 165960 | Hot Gas Path Inspection (HGPI) | 543316 | 2030-10-01 | 2030-10-15
61B | SSA | 810357 | Gas Turbine | 166163 | Major Inspection (MI) | 543436 | 2028-03-18 | 2028-04-15
61B | SSA | 810359 | Gas Turbine | 166165 | Hot Gas Path Inspection (HGPI) | 543437 | 2028-05-15 | 2028-06-04
61B | SSA | 809939 | Gas Turbine | 166168 | Hot Gas Path Inspection (HGPI) | 543438 | 2030-04-09 | 2030-04-23
61B | Asia | 297585 | Gas Turbine | 166225 | Hot Gas Path Inspection (HGPI) | 543495 | 2030-09-07 | 2030-09-21
61B | Europe | EGG0117 | Gas Turbine | 166328 | Hot Gas Path Inspection (HGPI) | 544701 | 2029-05-17 | 2029-05-31
61B | Europe | 297035 | Gas Turbine | 166330 | Combustion Inspection (CI) |  | 2027-02-21 | 2027-02-28
61B | MENA | 850123 | Gas Turbine | 166339 | Major Inspection (MI) | 543554 | 2030-11-30 | 2030-12-28
61B | MENA | 850119 | Gas Turbine | 166342 | Major Inspection (MI) | 543555 | 2030-06-11 | 2030-07-09
61B | NAM North America | 297311 | Gas Turbine | 166525 | Combustion Inspection (CI) |  | 2030-12-01 | 2030-12-08
61B | Latin America | 850115 | Gas Turbine | 174930 | Combustion Inspection (CI) |  | 2030-10-06 | 2030-10-13
61B | Europe | 295305 | Gas Turbine | 176867 | Major Inspection (MI) |  | 2027-03-20 | 2027-05-08
61B | Europe | 850106 | Gas Turbine | 177228 | Major Inspection (MI) | 550841 | 2027-05-19 | 2027-06-18
61B | Latin America | 850040 | Gas Turbine | 178545 | Major Inspection (MI) | 551496 | 2026-03-05 | 2026-04-14
61B | Asia | EGG0102 | Gas Turbine | 179066 | Major Inspection (MI) | 551814 | 2029-04-01 | 2029-05-30
61B | Asia | 900572 | Gas Turbine | 179243 | Major Inspection (MI) | 551860 | 2030-03-19 | 2030-04-16
61B | China | 850059 | Gas Turbine | 179882 | Major Inspection (MI) | 552260 | 2027-03-01 | 2027-03-31
61B | NAM North America | 295931 | Gas Turbine | 180859 | Major Inspection (MI) | 552835 | 2028-04-19 | 2028-06-05
61B | Latin America | 850040 | Gas Turbine | 181458 | Combustion Inspection (CI) |  | 2030-01-28 | 2030-02-04
61B | Latin America | 850041 | Gas Turbine | 181459 | Major Inspection (MI) | 553093 | 2027-02-01 | 2027-03-08
61B | Asia | 297043 | Gas Turbine | 182991 | Major Inspection (MI) | 554094 | 2027-07-17 | 2027-08-14
61B | Asia | 297043 | Gas Turbine | 184335 | Major Inspection (MI) | 554960 | 2027-03-17 | 2027-04-14
61B | Asia | 850139 | Gas Turbine | 186386 | Hot Gas Path Inspection (HGPI) | 556439 | 2030-12-02 | 2030-12-12
61B | Asia | 850137 | Gas Turbine | 186388 | Hot Gas Path Inspection (HGPI) | 556440 | 2028-11-02 | 2028-11-12
61B | Asia | 850116 | Gas Turbine | 186389 | Hot Gas Path Inspection (HGPI) | 556441 | 2029-01-02 | 2029-01-12
61B | Asia | 850139 | Gas Turbine | 186396 | Hot Gas Path Inspection (HGPI) | 556448 | 2028-05-07 | 2028-05-21
61B | Asia | 850137 | Gas Turbine | 186400 | Hot Gas Path Inspection (HGPI) | 556449 | 2028-08-06 | 2028-08-20
61B | Asia | 850116 | Gas Turbine | 186402 | Hot Gas Path Inspection (HGPI) | 556450 | 2028-11-05 | 2028-11-19
61B | Asia | 850140 | Gas Turbine | 186406 | Major Inspection (MI) | 556451 | 2030-11-11 | 2030-12-09
61B | Asia | 850135 | Gas Turbine | 186462 | Hot Gas Path Inspection (HGPI) | 556483 | 2027-10-02 | 2027-10-12
61B | Asia | 850140 | Gas Turbine | 186465 | Hot Gas Path Inspection (HGPI) | 556484 | 2028-05-02 | 2028-05-12
61B | Asia | 850121 | Gas Turbine | 186466 | Hot Gas Path Inspection (HGPI) | 556485 | 2028-07-02 | 2028-07-12
61B | Europe | 850102 | Gas Turbine | 186798 | Major Inspection (MI) | 556674 | 2028-05-15 | 2028-06-14
61B | Europe | 850006 | Gas Turbine | 187312 | Major Inspection (MI) | 557032 | 2029-05-07 | 2029-05-31
61B | Asia | 850135 | Gas Turbine | 191894 | Hot Gas Path Inspection (HGPI) |  | 2028-02-02 | 2028-02-16
61B | Asia | 850140 | Gas Turbine | 191895 | Hot Gas Path Inspection (HGPI) |  | 2028-05-08 | 2028-05-22
61B | Asia | 850139 | Gas Turbine | 191896 | Hot Gas Path Inspection (HGPI) |  | 2029-01-24 | 2029-02-07
61B | Asia | 850137 | Gas Turbine | 191897 | Hot Gas Path Inspection (HGPI) |  | 2029-01-25 | 2029-02-08
61B | Asia | 850116 | Gas Turbine | 191898 | Hot Gas Path Inspection (HGPI) |  | 2029-05-31 | 2029-06-14
61B | SSA | 809938 | Gas Turbine | 192458 | Hot Gas Path Inspection (HGPI) | 560561 | 2029-06-18 | 2029-07-02
61B | SSA | 809939 | Gas Turbine | 192459 | Hot Gas Path Inspection (HGPI) |  | 2030-05-31 | 2030-06-14
61B | Latin America | 850041 | Gas Turbine | 192934 | Combustion Inspection (CI) |  | 2030-06-24 | 2030-07-01
61B | NAM North America | 295363 | Gas Turbine | 192961 | Combustion Inspection (CI) |  | 2029-02-10 | 2029-02-17
61B | Asia | EGG0141 | Gas Turbine | 193559 | Combustion Inspection (CI) | 561312 | 2027-05-15 | 2027-05-22
71C | NAM North America | 238048 | Gas Turbine | 167019 | Hot Gas Path Inspection (HGPI) |  | 2028-04-26 | 2028-05-10
71E | NAM North America | 281915 | Gas Turbine | 109373 | Hot Gas Path Inspection (HGPI) | 508367 | 2028-05-15 | 2028-06-28
71E | NAM North America | 281915 | Gas Turbine | 114308 | Major Inspection (MI) | 508366 | 2028-12-18 | 2029-01-15
71E | NAM North America | 281868 | Gas Turbine | 151102 | Hot Gas Path Inspection (HGPI) | 543612 | 2027-08-31 | 2027-09-14
71E | NAM North America | 281869 | Gas Turbine | 151103 | Hot Gas Path Inspection (HGPI) | 552297 | 2028-07-05 | 2028-07-19
71E | NAM North America | 281928 | Gas Turbine | 165495 | Hot Gas Path Inspection (HGPI) | 543020 | 2026-04-01 | 2026-04-17
71E | NAM North America | 281868 | Gas Turbine | 166442 | Major Inspection (MI) | 543614 | 2030-12-23 | 2031-01-20
71E | NAM North America | 281917 | Gas Turbine | 182831 | Major Inspection (MI) | 553980 | 2027-03-12 | 2027-04-19
71EA | NAM North America | 297282 | Gas Turbine | 106663 | Major Inspection (MI) | 503036 | 2029-10-01 | 2029-11-04
71EA | NAM North America | 297286 | Gas Turbine | 106664 | Major Inspection (MI) | 503037 | 2030-10-01 | 2030-11-04
71EA | NAM North America | 297284 | Gas Turbine | 106665 | Major Inspection (MI) | 503038 | 2029-10-01 | 2029-11-04
71EA | NAM North America | 299043 | Gas Turbine | 108765 | Major Inspection (MI) | 515758 | 2029-09-12 | 2029-10-12
71EA | NAM North America | 298583 | Gas Turbine | 110618 | Major Inspection (MI) | 504524 | 2030-07-29 | 2030-08-26
71EA | NAM North America | 299044 | Gas Turbine | 112895 | Hot Gas Path Inspection (HGPI) | 515764 | 2026-10-07 | 2026-10-24
71EA | NAM North America | 297538 | Gas Turbine | 113238 | Major Inspection (MI) | 504806 | 2026-03-07 | 2026-04-23
71EA | NAM North America | 299210 | Gas Turbine | 114322 | Hot Gas Path Inspection (HGPI) | 504522 | 2028-09-13 | 2028-09-27
71EA | NAM North America | 298583 | Gas Turbine | 114710 | Hot Gas Path Inspection (HGPI) | 504526 | 2026-09-11 | 2026-09-25
71EA | NAM North America | 299044 | Gas Turbine | 119316 | Major Inspection (MI) | 515763 | 2030-09-11 | 2030-10-11
71EA | NAM North America | 297646 | Gas Turbine | 121931 | Major Inspection (MI) | 505716 | 2026-02-09 | 2026-03-20
71EA | MENA | 299329 | Gas Turbine | 135158 | Hot Gas Path Inspection (HGPI) | 522942 | 2028-01-06 | 2028-01-21
71EA | NAM North America | 297553 | Gas Turbine | 140720 | Major Inspection (MI) | 526378 | 2028-03-01 | 2028-04-04
71EA | Latin America | 297130 | Gas Turbine | 142588 | Combustion Inspection (CI) | 527326 | 2026-04-23 | 2026-05-11
71EA | NAM North America | 297090 | Gas Turbine | 147849 | Hot Gas Path Inspection (HGPI) | 530398 | 2026-06-18 | 2026-06-29
71EA | NAM North America | 297673 | Gas Turbine | 147938 | Borescope Inspection (BI) | 530464 | 2026-10-16 | 2026-10-20
71EA | NAM North America | 296592 | Gas Turbine | 150343 | Major Inspection (MI) |  | 2028-07-31 | 2028-08-28
71EA | NAM North America | 297286 | Gas Turbine | 150638 | Major Inspection (MI) | 543212 | 2026-03-01 | 2026-03-29
71EA | NAM North America | 298318 | Gas Turbine | 150857 | Hot Gas Path Inspection (HGPI) | 543312 | 2028-05-15 | 2028-05-31
71EA | NAM North America | 296594 | Gas Turbine | 150899 | Hot Gas Path Inspection (HGPI) | 539682 | 2026-10-19 | 2026-11-02
71EA | NAM North America | 296593 | Gas Turbine | 150901 | Hot Gas Path Inspection (HGPI) | 552218 | 2028-03-02 | 2028-03-16
71EA | NAM North America | 297155 | Gas Turbine | 150911 | Borescope Inspection (BI) | 532342 | 2026-04-01 | 2026-04-02
71EA | NAM North America | 297156 | Gas Turbine | 150914 | Borescope Inspection (BI) | 532345 | 2026-05-09 | 2026-05-10
71EA | NAM North America | 297643 | Gas Turbine | 151012 | Major Inspection (MI) | 538625 | 2026-05-14 | 2026-06-21
71EA | NAM North America | 297642 | Gas Turbine | 151013 | Major Inspection (MI) | 543371 | 2027-04-20 | 2027-05-22
71EA | MENA | 298489 | Gas Turbine | 151094 | Hot Gas Path Inspection (HGPI) | 537975 | 2026-11-23 | 2026-12-08
71EA | NAM North America | 297090 | Gas Turbine | 151095 | Combustion Inspection (CI) | 548491 | 2027-05-11 | 2027-05-17
71EA | NAM North America | 299321 | Gas Turbine | 151172 | Hot Gas Path Inspection (HGPI) | 544899 | 2028-09-30 | 2028-10-13
71EA | NAM North America | 298445 | Gas Turbine | 151178 | Major Inspection (MI) | 543457 | 2027-09-20 | 2027-10-14
71EA | NAM North America | 297716 | Gas Turbine | 151179 | Combustion Inspection (CI) |  | 2026-02-01 | 2026-02-08
71EA | NAM North America | 297717 | Gas Turbine | 151180 | Combustion Inspection (CI) |  | 2026-12-11 | 2026-12-18
71EA | NAM North America | 297716 | Gas Turbine | 151181 | Hot Gas Path Inspection (HGPI) | 538470 | 2028-04-04 | 2028-04-24
71EA | NAM North America | 297282 | Gas Turbine | 154393 | Borescope Inspection (BI) | 534791 | 2026-05-08 | 2026-05-21
71EA | NAM North America | 298682 | Gas Turbine | 157322 | Combustion Inspection (CI) | 537448 | 2026-05-02 | 2026-05-09
71EA | NAM North America | 298681 | Gas Turbine | 157323 | Combustion Inspection (CI) | 545964 | 2026-05-15 | 2026-05-22
71EA | NAM North America | 298529 | Gas Turbine | 157324 | Major Inspection (MI) | 543569 | 2026-09-24 | 2026-10-22
71EA | NAM North America | 298774 | Gas Turbine | 157325 | Combustion Inspection (CI) | 548487 | 2027-04-05 | 2027-04-12
71EA | NAM North America | 298775 | Gas Turbine | 157326 | Combustion Inspection (CI) | 561750 | 2027-03-29 | 2027-04-04
71EA | NAM North America | 299322 | Gas Turbine | 158216 | Hot Gas Path Inspection (HGPI) | 537685 | 2029-09-20 | 2029-10-01
71EA | NAM North America | 297662 | Gas Turbine | 158693 | Borescope Inspection (BI) | 537997 | 2026-03-03 | 2026-03-04
71EA | MENA | 299330 | Gas Turbine | 159071 | Hot Gas Path Inspection (HGPI) | 538189 | 2028-06-03 | 2028-06-17
71EA | NAM North America | 298301 | Gas Turbine | 160560 | Borescope Inspection (BI) | 539222 | 2026-11-08 | 2026-11-09
71EA | NAM North America | 298302 | Gas Turbine | 160562 | Borescope Inspection (BI) | 539224 | 2026-11-09 | 2026-11-10
71EA | NAM North America | 298303 | Gas Turbine | 160563 | Major Inspection (MI) | 539225 | 2026-03-26 | 2026-05-20
71EA | NAM North America | 298529 | Gas Turbine | 165196 | Combustion Inspection (CI) | 561760 | 2028-10-12 | 2028-10-19
71EA | NAM North America | 298682 | Gas Turbine | 165198 | Major Inspection (MI) | 542857 | 2029-10-28 | 2029-11-16
71EA | NAM North America | 298681 | Gas Turbine | 165199 | Major Inspection (MI) | 542858 | 2029-08-21 | 2029-09-18
71EA | NAM North America | 297553 | Gas Turbine | 165783 | Major Inspection (MI) |  | 2026-11-30 | 2026-12-28
71EA | NAM North America | 297297 | Gas Turbine | 165785 | Major Inspection (MI) | 543213 | 2029-06-20 | 2029-07-18
71EA | Latin America | 299248 | Gas Turbine | 165834 | Major Inspection (MI) | 543232 | 2028-11-10 | 2028-11-24
71EA | NAM North America | 298318 | Gas Turbine | 165953 | Major Inspection (MI) | 543313 | 2030-09-21 | 2030-10-19
71EA | NAM North America | 295504 | Gas Turbine | 165964 | Major Inspection (MI) | 543318 | 2028-02-22 | 2028-03-21
71EA | NAM North America | 297142 | Gas Turbine | 166190 | Major Inspection (MI) | 543458 | 2028-03-25 | 2028-04-22
71EA | NAM North America | 297523 | Gas Turbine | 166347 | Combustion Inspection (CI) | 560978 | 2027-04-11 | 2027-05-08
71EA | NAM North America | 297522 | Gas Turbine | 166348 | Combustion Inspection (CI) | 560979 | 2027-04-11 | 2027-05-08
71EA | NAM North America | 297526 | Gas Turbine | 166349 | Combustion Inspection (CI) |  | 2030-07-18 | 2030-07-25
71EA | NAM North America | 297527 | Gas Turbine | 166350 | Combustion Inspection (CI) |  | 2030-11-06 | 2030-11-13
71EA | NAM North America | 297156 | Gas Turbine | 166354 | Major Inspection (MI) | 543560 | 2027-05-18 | 2027-06-10
71EA | NAM North America | 297155 | Gas Turbine | 166355 | Major Inspection (MI) | 543561 | 2028-04-13 | 2028-05-29
71EA | NAM North America | 297065 | Gas Turbine | 166357 | Combustion Inspection (CI) | 543735 | 2026-05-04 | 2026-05-14
71EA | NAM North America | 297065 | Gas Turbine | 166358 | Major Inspection (MI) | 543562 | 2028-09-24 | 2028-10-29
71EA | NAM North America | 297065 | Gas Turbine | 166361 | Combustion Inspection (CI) | 543738 | 2030-10-01 | 2030-10-08
71EA | NAM North America | 299261 | Gas Turbine | 166362 | Hot Gas Path Inspection (HGPI) | 543563 | 2027-03-01 | 2027-03-29
71EA | NAM North America | 299262 | Gas Turbine | 166364 | Hot Gas Path Inspection (HGPI) | 543564 | 2028-03-01 | 2028-03-16
71EA | NAM North America | 299263 | Gas Turbine | 166366 | Hot Gas Path Inspection (HGPI) | 543565 | 2028-09-18 | 2028-10-02
71EA | NAM North America | 299264 | Gas Turbine | 166369 | Hot Gas Path Inspection (HGPI) | 543566 | 2029-01-24 | 2029-02-07
71EA | NAM North America | 297717 | Gas Turbine | 166418 | Hot Gas Path Inspection (HGPI) | 543592 | 2029-05-08 | 2029-06-05
71EA | NAM North America | 297825 | Gas Turbine | 166444 | Hot Gas Path Inspection (HGPI) | 543615 | 2028-04-20 | 2028-05-06
71EA | NAM North America | 297824 | Gas Turbine | 166445 | Hot Gas Path Inspection (HGPI) | 543616 | 2029-11-07 | 2029-11-21
71EA | NAM North America | 298302 | Gas Turbine | 170531 | Major Inspection (MI) | 546732 | 2026-10-15 | 2026-11-18
71EA | NAM North America | 297147 | Gas Turbine | 182767 | Combustion Inspection (CI) | 558077 | 2028-04-03 | 2028-04-10
71EA | NAM North America | 297147 | Gas Turbine | 182768 | Hot Gas Path Inspection (HGPI) | 553931 | 2029-01-22 | 2029-02-05
71EA | NAM North America | 297147 | Gas Turbine | 182769 | Combustion Inspection (CI) |  | 2030-12-19 | 2030-12-26
71EA | NAM North America | 296594 | Gas Turbine | 182866 | Stand Alone Small Upgrade | 554003 | 2026-04-06 | 2026-04-11
71EA | NAM North America | 296593 | Gas Turbine | 182867 | Stand Alone Small Upgrade | 554004 | 2026-04-06 | 2026-04-11
71EA | NAM North America | 298303 | Gas Turbine | 190586 | Stand Alone Large Upgrade | 559288 | 2027-09-12 | 2027-10-02
71EA | NAM North America | 298301 | Gas Turbine | 190587 | Stand Alone Large Upgrade | 559289 | 2027-10-03 | 2027-10-23
71EA | NAM North America | 298302 | Gas Turbine | 190588 | Stand Alone Large Upgrade | 559290 | 2027-10-23 | 2027-11-13
71EA | MENA | 298490 | Gas Turbine | 191343 | Major Inspection (MI) | 559850 | 2028-04-02 | 2028-04-27
71EA | MENA | 298489 | Gas Turbine | 191360 | Major Inspection (MI) | 559865 | 2029-03-07 | 2029-04-01
71EA | Latin America | 297127 | Gas Turbine | 192322 | Combustion Inspection (CI) | 560479 | 2026-10-01 | 2026-10-19
71EA | Latin America | 297129 | Gas Turbine | 192442 | Combustion Inspection (CI) | 561479 | 2027-02-01 | 2027-03-02
71EA | NAM North America | 297647 | Gas Turbine | 193112 | Combustion Inspection (CI) |  | 2028-04-30 | 2028-05-07
71EA | NAM North America | 297646 | Gas Turbine | 193113 | Combustion Inspection (CI) |  | 2028-12-27 | 2029-01-03
71EA | Latin America | 297127 | Gas Turbine | 193302 | Combustion Inspection (CI) | 561108 | 2026-10-01 | 2026-10-19
71EA | Latin America | 297128 | Gas Turbine | 194956 | Major Inspection (MI) | 562884 | 2027-06-03 | 2027-07-07
71EA | NAM North America | 298682 | Gas Turbine | 194958 | Combustion Inspection (CI) |  | 2026-06-09 | 2026-06-16
71EA | NAM North America | 297673 | Gas Turbine | 196223 | Stand Alone Small Upgrade | 563495 | 2026-07-15 | 2029-07-31
107A-10 | NAM North America | 270T545 | Steam Turbine | 113606 | Minor Inspection |  | 2027-05-10 | 2027-05-15
107A-10 | NAM North America | 270T455 | Steam Turbine | 144333 | Minor Inspection | 556235 | 2027-03-21 | 2027-04-10
107A-10 | NAM North America | 270T506 | Steam Turbine | 144392 | Major Inspection (MI) | 548209 | 2027-08-07 | 2027-10-16
107A-10 | NAM North America | 270T566 | Steam Turbine | 144448 | Major Inspection (MI) | 553408 | 2027-03-13 | 2027-04-12
107A-10 | NAM North America | 270T545 | Steam Turbine | 158479 | Major Inspection (MI) | 537834 | 2026-03-16 | 2026-05-07
107A-10 | NAM North America | 270T546 | Steam Turbine | 165134 | Minor Inspection |  | 2030-05-15 | 2030-05-29
107A-10 | NAM North America | 270T504 | Steam Turbine | 165173 | Major Inspection (MI) | 547697 | 2027-02-04 | 2027-04-13
107A-10 | NAM North America | 270T505 | Steam Turbine | 165177 | Major Inspection (MI) |  | 2030-11-15 | 2030-12-13
107A-10 | NAM North America | 270T431 | Steam Turbine | 165253 | Stand Alone Small Upgrade | 555069 | 2028-11-14 | 2029-01-12
107A-10 | NAM North America | 270T505 | Steam Turbine | 173300 | Major Inspection (MI) | 548226 | 2028-02-05 | 2028-04-15
107A-10 | NAM North America | 270T475 | Steam Turbine | 184401 | Major Inspection (MI) | 555023 | 2027-04-03 | 2027-05-13
107A-10 | NAM North America | 270T476 | Steam Turbine | 184403 | Major Inspection (MI) | 555025 | 2027-04-01 | 2027-04-19
107A-10 | NAM North America | 270T455 | Steam Turbine | 186711 | Minor Inspection | 556599 | 2027-02-11 | 2027-02-25
107A-10 | NAM North America | 270T473 | Steam Turbine | 191048 | Minor Inspection |  | 2026-04-11 | 2026-05-12
107A-10 | NAM North America | 270T504 | Steam Turbine | 195200 | Major Inspection (MI) |  | 2027-03-01 | 2027-03-29
107A-10 | NAM North America | 270T506 | Steam Turbine | 195202 | Major Inspection (MI) |  | 2027-08-07 | 2027-09-04
107A-14 | NAM North America | 270T773 | Steam Turbine | 144407 | Minor Inspection | 547287 | 2026-11-01 | 2026-11-24
107A-14 | Latin America | 270T923 | Steam Turbine | 146323 | Minor Inspection | 559807 | 2028-10-01 | 2028-10-14
107A-14 | NAM North America | 270T920 | Steam Turbine | 146747 | Minor Inspection | 558119 | 2027-03-12 | 2027-03-28
107A-14 | NAM North America | 270T921 | Steam Turbine | 162999 | Minor Inspection |  | 2028-05-10 | 2028-05-15
107A-14 | NAM North America | 270T658 | Steam Turbine | 165247 | Major Inspection (MI) |  | 2027-02-01 | 2027-03-01
107A-14 | NAM North America | 270T737 | Steam Turbine | 165757 | Major Inspection (MI) | 543189 | 2026-01-28 | 2026-04-26
107A-14 | NAM North America | 270T773 | Steam Turbine | 182459 | Minor Inspection |  | 2026-10-01 | 2026-10-06
107A-14 | NAM North America | 270T773 | Steam Turbine | 182461 | Major Inspection (MI) | 562733 | 2030-02-01 | 2030-03-01
107A-14 | NAM North America | 270T762 | Steam Turbine | 186966 | Minor Inspection | 559547 | 2028-04-20 | 2028-05-15
107A-14 | NAM North America | 270T762 | Steam Turbine | 186967 | Major Inspection (MI) |  | 2030-11-01 | 2030-11-29
107A-14 | NAM North America | 270T658 | Steam Turbine | 195186 | Minor Inspection | 562689 | 2027-02-01 | 2027-05-01
107SAC | NAM North America | 270T294 | Steam Turbine | 144181 | Major Inspection (MI) | 528377 | 2026-02-28 | 2026-06-29
107SAC | NAM North America | 270T296 | Steam Turbine | 145499 | Minor Inspection | 547081 | 2026-05-01 | 2026-06-20
107SAC | NAM North America | 155444 | Steam Turbine | 147493 | Minor Inspection | 542424 | 2028-03-25 | 2028-04-08
107SAC | NAM North America | 155423 | Steam Turbine | 166359 | Major Inspection (MI) | 543736 | 2028-09-24 | 2028-10-29
107SAC | NAM North America | 270T294 | Steam Turbine | 177287 | Minor Inspection |  | 2029-08-24 | 2029-08-29
107SC | NAM North America | 270T501 | Steam Turbine | 169452 | Major Inspection (MI) | 552955 | 2028-03-28 | 2028-05-01
107SC | NAM North America | 270T502 | Steam Turbine | 169453 | Major Inspection (MI) | 552953 | 2028-05-03 | 2028-06-12
109A-15 | MENA | 270T726 | Steam Turbine | 144403 | Minor Inspection | 547780 | 2026-05-06 | 2026-05-26
109A-15 | MENA | 270T725 | Steam Turbine | 144404 | Minor Inspection | 546327 | 2028-04-01 | 2028-04-22
109A-15 | Europe | 270T739 | Steam Turbine | 162026 | Major Inspection (MI) |  | 2026-09-18 | 2026-11-17
109A-15 | Europe | 270T767 | Steam Turbine | 167034 | Major Inspection (MI) | 544056 | 2026-02-23 | 2026-05-18
109A-15 | Europe | 270T671 | Steam Turbine | 172084 | Major Inspection (MI) | 547444 | 2026-07-13 | 2026-10-10
109A-15 | MENA | 270T718 | Steam Turbine | 173248 | Minor Inspection | 552084 | 2026-02-08 | 2026-03-01
109A-15 | Europe | 270T739 | Steam Turbine | 177172 | Major Inspection (MI) | 550801 | 2027-03-01 | 2027-06-03
109A-15 | Europe | 270T740 | Steam Turbine | 183377 | Large Call-Out | 554341 | 2027-02-15 | 2027-03-26
109A-15 | Europe | 270T722 | Steam Turbine | 183443 | Major Inspection (MI) | 554387 | 2028-09-14 | 2028-10-23
109A-16 | Europe | 270T800 | Steam Turbine | 106701 | Major Inspection (MI) | 503074 | 2028-09-10 | 2028-10-08
109A-16 | MENA | 270T793 | Steam Turbine | 138889 | Borescope Inspection (BI) | 525399 | 2026-10-20 | 2026-10-24
109A-16 | MENA | 270T794 | Steam Turbine | 138895 | Borescope Inspection (BI) | 525405 | 2027-02-15 | 2027-02-19
109A-16 | MENA | 270T792 | Steam Turbine | 138901 | Borescope Inspection (BI) | 525411 | 2026-12-01 | 2026-12-05
109A-16 | MENA | 270T793 | Steam Turbine | 144409 | Major Inspection (MI) | 532365 | 2027-01-01 | 2027-02-19
109A-16 | MENA | 270T794 | Steam Turbine | 144410 | Major Inspection (MI) | 546215 | 2028-09-01 | 2028-10-25
109A-16 | MENA | 270T794 | Steam Turbine | 145636 | Large Call-Out | 529199 | 2026-01-03 | 2026-01-30
109A-16 | MENA | 270T792 | Steam Turbine | 158886 | Major Inspection (MI) | 538106 | 2029-12-12 | 2030-01-09
109A-16 | Europe | 270T780 | Steam Turbine | 179536 | Minor Inspection | 552083 | 2028-03-01 | 2028-04-30
109A-16 | MENA | 270T793 | Steam Turbine | 191333 | Large Call-Out | 559849 | 2027-01-01 | 2027-02-27
109A-16 | Europe | 270T780 | Steam Turbine | 194116 | Large Call-Out |  | 2026-05-09 | 2026-07-31
109A-16 | Europe | 270T780 | Steam Turbine | 194136 | Large Call-Out | 561836 | 2026-05-21 | 2027-06-30
109A-17 | Europe | 270T886 | Steam Turbine | 148643 | Major Inspection (MI) | 552170 | 2028-03-01 | 2028-03-27
109A-17 | Europe | 270T886 | Steam Turbine | 187568 | Major Inspection (MI) |  | 2028-05-10 | 2028-06-07
109D-10 | Europe | 270T634 | Steam Turbine | 167260 | Major Inspection (MI) | 544264 | 2026-10-20 | 2027-01-16
109D-10 | Europe | 270T633 | Steam Turbine | 167263 | Minor Inspection | 544266 | 2026-01-19 | 2026-02-26
109D-10 | Europe | 270T633 | Steam Turbine | 180214 | Minor Inspection |  | 2026-12-19 | 2026-12-24
109D-10 | Europe | 270T634 | Steam Turbine | 194309 | Minor Inspection | 561959 | 2030-06-03 | 2030-07-20
109D-10 | Europe | 270T633 | Steam Turbine | 194310 | Major Inspection (MI) | 561960 | 2029-09-03 | 2029-11-30
109D-11 | Latin America | 270T365 | Steam Turbine | 168781 | Minor Inspection |  | 2029-08-22 | 2029-08-27
109D-12 | Europe | 270T821 | Steam Turbine | 121243 | Minor Inspection | 503487 | 2026-10-24 | 2026-11-24
109D-12 | Europe | 270T891 | Steam Turbine | 172528 | Minor Inspection |  | 2027-08-22 | 2027-08-27
109D-12 | Europe | 270T891 | Steam Turbine | 172529 | Major Inspection (MI) |  | 2030-12-15 | 2031-01-12
109D-12 | Europe | 270T891 | Steam Turbine | 188820 | Large Call-Out | 547984 | 2027-09-06 | 2027-11-11
109D-14 | Europe | 270T840 | Steam Turbine | 195251 | Large Call-Out | 562745 | 2026-06-22 | 2026-07-31
109SC | Europe | 155401 | Steam Turbine | 155696 | Major Inspection (MI) | 537330 | 2026-01-23 | 2026-04-09
109SC | Europe | 155400 | Steam Turbine | 155698 | Major Inspection (MI) | 537901 | 2027-04-08 | 2027-05-30
109SC | Europe | 155399 | Steam Turbine | 155700 | Minor Inspection | 546440 | 2027-10-01 | 2027-10-20
109SC | Europe | 155401 | Steam Turbine | 155703 | Minor Inspection | 546444 | 2029-01-22 | 2029-02-13
207D-11 | NAM North America | 270T515 | Steam Turbine | 106682 | Major Inspection (MI) | 503055 | 2026-02-07 | 2026-03-30
207D-11 | Latin America | 270T682 | Steam Turbine | 106698 | Major Inspection (MI) | 503071 | 2026-03-04 | 2026-04-07
207D-11 | NAM North America | 270T463 | Steam Turbine | 106740 | Minor Inspection | 503113 | 2026-04-19 | 2026-05-04
207D-11 | NAM North America | 270T597 | Steam Turbine | 114813 | Major Inspection (MI) | 505680 | 2030-02-25 | 2030-03-25
207D-11 | NAM North America | 270T512 | Steam Turbine | 144331 | Major Inspection (MI) | 553739 | 2028-05-08 | 2028-06-27
207D-11 | NAM North America | 270T711 | Steam Turbine | 144343 | Major Inspection (MI) | 555008 | 2027-10-31 | 2027-12-30
207D-11 | NAM North America | 270T519 | Steam Turbine | 144365 | Minor Inspection | 541800 | 2026-02-18 | 2026-03-31
207D-11 | NAM North America | 270T619 | Steam Turbine | 144369 | Major Inspection (MI) | 547232 | 2026-02-01 | 2026-03-24
207D-11 | NAM North America | 270T520 | Steam Turbine | 144373 | Major Inspection (MI) |  | 2028-02-14 | 2028-03-29
207D-11 | NAM North America | 270T489 | Steam Turbine | 144380 | Major Inspection (MI) | 534412 | 2027-08-28 | 2027-11-12
207D-11 | NAM North America | 270T733 | Steam Turbine | 145477 | Major Inspection (MI) | 535923 | 2026-03-27 | 2026-05-19
207D-11 | NAM North America | 270T516 | Steam Turbine | 145480 | Major Inspection (MI) | 535922 | 2027-01-21 | 2027-03-13
207D-11 | NAM North America | 270T796 | Steam Turbine | 145484 | Minor Inspection | 535924 | 2028-02-05 | 2028-03-01
207D-11 | Latin America | 270T599 | Steam Turbine | 146571 | Major Inspection (MI) | 534883 | 2030-06-25 | 2030-07-24
207D-11 | NAM North America | 270T885 | Steam Turbine | 146836 | Major Inspection (MI) | 545342 | 2027-01-19 | 2027-03-04
207D-11 | NAM North America | 270T524 | Steam Turbine | 147498 | Major Inspection (MI) | 542430 | 2027-01-09 | 2027-04-03
207D-11 | NAM North America | 270T498 | Steam Turbine | 147537 | Minor Inspection | 553532 | 2029-03-05 | 2029-03-22
207D-11 | NAM North America | 270T451 | Steam Turbine | 147542 | Minor Inspection | 555047 | 2027-11-09 | 2027-11-28
207D-11 | Latin America | 270T560 | Steam Turbine | 147551 | Minor Inspection | 530602 | 2026-11-04 | 2026-12-18
207D-11 | Latin America | 270T559 | Steam Turbine | 147554 | Major Inspection (MI) | 555073 | 2029-03-03 | 2029-04-08
207D-11 | Latin America | 270T654 | Steam Turbine | 147557 | Minor Inspection | 550003 | 2027-01-16 | 2027-01-30
207D-11 | Latin America | 270T699 | Steam Turbine | 147559 | Minor Inspection | 544067 | 2026-01-06 | 2026-01-26
207D-11 | Latin America | 270T700 | Steam Turbine | 147560 | Minor Inspection | 544071 | 2026-02-05 | 2026-02-20
207D-11 | Latin America | 270T683 | Steam Turbine | 147562 | Minor Inspection |  | 2028-10-11 | 2028-10-31
207D-11 | Latin America | 270T682 | Steam Turbine | 147566 | Minor Inspection |  | 2030-03-03 | 2030-03-23
207D-11 | NAM North America | 270T532 | Steam Turbine | 147572 | Minor Inspection | 543920 | 2028-04-01 | 2028-04-15
207D-11 | NAM North America | 270T491 | Steam Turbine | 147574 | Minor Inspection | 544844 | 2028-09-30 | 2028-10-14
207D-11 | NAM North America | 270T424 | Steam Turbine | 147581 | Minor Inspection | 555019 | 2027-09-16 | 2027-11-04
207D-11 | NAM North America | 270T741 | Steam Turbine | 147583 | Minor Inspection | 542431 | 2027-04-01 | 2027-04-29
207D-11 | NAM North America | 270T443 | Steam Turbine | 147589 | Minor Inspection | 558424 | 2027-04-07 | 2027-04-30
207D-11 | NAM North America | 270T468 | Steam Turbine | 147591 | Major Inspection (MI) | 545028 | 2028-04-01 | 2028-06-14
207D-11 | NAM North America | 270T434 | Steam Turbine | 147596 | Minor Inspection | 555124 | 2028-03-07 | 2028-03-21
207D-11 | NAM North America | 270T631 | Steam Turbine | 157558 | Minor Inspection | 537143 | 2027-02-22 | 2027-04-11
207D-11 | NAM North America | 270T497 | Steam Turbine | 157881 | Major Inspection (MI) | 537416 | 2026-01-29 | 2026-04-20
207D-11 | NAM North America | 270T452 | Steam Turbine | 159199 | Minor Inspection | 544766 | 2029-11-24 | 2029-12-08
207D-11 | Latin America | 270T530 | Steam Turbine | 162651 | Minor Inspection | 545583 | 2028-02-15 | 2028-03-05
207D-11 | NAM North America | 270T462 | Steam Turbine | 163151 | Minor Inspection | 558968 | 2028-10-01 | 2028-11-01
207D-11 | NAM North America | 270T435 | Steam Turbine | 163189 | Minor Inspection | 558123 | 2029-03-17 | 2029-03-31
207D-11 | NAM North America | 270T929 | Steam Turbine | 163248 | Major Inspection (MI) | 541338 | 2026-03-08 | 2026-04-28
207D-11 | NAM North America | 270T606 | Steam Turbine | 165047 | Major Inspection (MI) |  | 2028-03-01 | 2028-03-29
207D-11 | NAM North America | 270T488 | Steam Turbine | 165063 | Major Inspection (MI) |  | 2029-03-15 | 2029-04-12
207D-11 | Latin America | 270T560 | Steam Turbine | 165069 | Major Inspection (MI) |  | 2029-10-01 | 2029-11-10
207D-11 | Latin America | 270T700 | Steam Turbine | 165085 | Major Inspection (MI) | 544130 | 2030-09-20 | 2030-10-18
207D-11 | Latin America | 270T683 | Steam Turbine | 165098 | Minor Inspection |  | 2030-11-03 | 2030-11-08
207D-11 | NAM North America | 270T531 | Steam Turbine | 165138 | Major Inspection (MI) |  | 2028-01-30 | 2028-02-27
207D-11 | NAM North America | 270T493 | Steam Turbine | 165144 | Minor Inspection |  | 2030-03-15 | 2030-03-29
207D-11 | NAM North America | 270T619 | Steam Turbine | 165185 | Minor Inspection |  | 2030-10-01 | 2030-10-06
207D-11 | NAM North America | 270T577 | Steam Turbine | 165287 | Major Inspection (MI) | 543236 | 2027-03-10 | 2027-05-14
207D-11 | NAM North America | 270T578 | Steam Turbine | 165377 | Major Inspection (MI) | 542932 | 2028-03-08 | 2028-05-22
207D-11 | NAM North America | 270T538 | Steam Turbine | 172369 | Minor Inspection | 547688 | 2027-10-05 | 2027-11-15
207D-11 | NAM North America | 270T537 | Steam Turbine | 172374 | Minor Inspection | 547690 | 2028-03-04 | 2028-05-12
207D-11 | NAM North America | 270T885 | Steam Turbine | 175809 | Major Inspection (MI) |  | 2029-06-12 | 2029-07-10
207D-11 | NAM North America | 270T493 | Steam Turbine | 175975 | Minor Inspection | 549952 | 2026-11-01 | 2026-11-18
207D-11 | NAM North America | 270T463 | Steam Turbine | 176105 | Minor Inspection |  | 2030-07-23 | 2030-07-28
207D-11 | NAM North America | 270T733 | Steam Turbine | 176383 | Minor Inspection |  | 2030-07-09 | 2030-07-14
207D-11 | NAM North America | 270T503 | Steam Turbine | 177264 | Major Inspection (MI) | 550914 | 2028-03-12 | 2028-04-09
207D-11 | NAM North America | 270T552 | Steam Turbine | 177400 | Minor Inspection | 554928 | 2029-04-07 | 2029-04-25
207D-11 | NAM North America | 270T490 | Steam Turbine | 177404 | Minor Inspection | 556095 | 2030-04-13 | 2030-05-01
207D-11 | NAM North America | 270T425 | Steam Turbine | 177410 | Minor Inspection |  | 2028-10-01 | 2028-10-06
207D-11 | NAM North America | 270T442 | Steam Turbine | 177417 | Minor Inspection |  | 2028-11-23 | 2028-11-28
207D-11 | NAM North America | 270T531 | Steam Turbine | 181374 | Major Inspection (MI) | 553025 | 2028-03-16 | 2028-05-31
207D-11 | NAM North America | 270T528 | Steam Turbine | 182472 | Major Inspection (MI) |  | 2029-04-30 | 2029-05-28
207D-11 | NAM North America | 270T500 | Steam Turbine | 183678 | Minor Inspection | 554522 | 2026-10-03 | 2026-11-03
207D-11 | NAM North America | 270T260 | Steam Turbine | 184383 | Minor Inspection | 555009 | 2030-10-05 | 2030-11-03
207D-11 | NAM North America | 270T259 | Steam Turbine | 184387 | Minor Inspection | 555011 | 2029-10-13 | 2029-10-31
207D-11 | Latin America | 270T683 | Steam Turbine | 184502 | Minor Inspection | 555070 | 2029-01-16 | 2029-02-05
207D-11 | NAM North America | 270T492 | Steam Turbine | 184904 | Minor Inspection | 555364 | 2026-02-02 | 2026-02-28
207D-11 | NAM North America | 270T680 | Steam Turbine | 184945 | Minor Inspection | 555389 | 2026-03-10 | 2026-03-26
207D-11 | NAM North America | 270T769 | Steam Turbine | 185184 | Minor Inspection | 555540 | 2026-09-28 | 2026-10-19
207D-11 | NAM North America | 270T454 | Steam Turbine | 186303 | Minor Inspection |  | 2028-09-01 | 2028-09-06
207D-11 | NAM North America | 270T453 | Steam Turbine | 187627 | Minor Inspection |  | 2030-05-23 | 2030-05-28
207D-11 | NAM North America | 270T512 | Steam Turbine | 187723 | Major Inspection (MI) |  | 2028-09-01 | 2028-09-29
207D-11 | NAM North America | 270T711 | Steam Turbine | 187782 | Major Inspection (MI) |  | 2027-02-24 | 2027-03-24
207D-11 | NAM North America | 270T597 | Steam Turbine | 187789 | Major Inspection (MI) |  | 2028-09-22 | 2028-10-20
207D-11 | NAM North America | 270T489 | Steam Turbine | 187832 | Major Inspection (MI) |  | 2027-09-01 | 2027-09-29
207D-11 | NAM North America | 270T500 | Steam Turbine | 188756 | Major Inspection (MI) | 557941 | 2030-03-01 | 2030-05-31
207D-11 | NAM North America | 270T500 | Steam Turbine | 189434 | Minor Inspection |  | 2026-06-27 | 2026-07-02
207D-11 | NAM North America | 270T435 | Steam Turbine | 192342 | Large Call-Out | 560500 | 2027-10-23 | 2027-11-19
207D-11 | NAM North America | 270T495 | Steam Turbine | 194285 | Stand Alone Large Upgrade | 561935 | 2028-10-09 | 2028-12-01
207D-11 | NAM North America | 270T912 | Steam Turbine | 195746 | Minor Inspection | 563120 | 2027-05-03 | 2027-05-20
207SC-5 | NAM North America | 270T529 | Steam Turbine | 166446 | Major Inspection (MI) | 557259 | 2029-07-03 | 2029-07-31
207SCSF | NAM North America | 270T321 | Steam Turbine | 150900 | Minor Inspection |  | 2028-03-02 | 2028-03-07
209C-7 | MENA | 270T810 | Steam Turbine | 190384 | Minor Inspection | 559133 | 2026-11-09 | 2026-11-25
209D-11 | Latin America | 270T409 | Steam Turbine | 136857 | Major Inspection (MI) | 543468 | 2028-03-21 | 2028-04-18
209D-11 | Europe | 270T890 | Steam Turbine | 144427 | Major Inspection (MI) | 533081 | 2027-05-17 | 2027-07-16
209D-11 | Europe | 270T724 | Steam Turbine | 151848 | Major Inspection (MI) | 532957 | 2027-09-20 | 2027-11-20
209D-11 | Europe | 270T727 | Steam Turbine | 151972 | Major Inspection (MI) | 533061 | 2026-01-26 | 2026-04-25
209D-11 | Europe | 270T517 | Steam Turbine | 152116 | Minor Inspection | 533186 | 2028-04-03 | 2028-04-24
209D-11 | Latin America | 270T887 | Steam Turbine | 154382 | Minor Inspection | 554020 | 2028-01-25 | 2028-01-30
209D-11 | Europe | 270T797 | Steam Turbine | 164431 | Minor Inspection | 556465 | 2027-04-01 | 2027-05-31
209D-11 | Europe | 270T708 | Steam Turbine | 166722 | Major Inspection (MI) | 543832 | 2027-02-01 | 2027-04-22
209D-11 | Latin America | 270T409 | Steam Turbine | 169443 | Minor Inspection |  | 2029-05-11 | 2029-05-16
209D-11 | MENA | 270T760 | Steam Turbine | 170092 | Minor Inspection | 546398 | 2026-01-18 | 2026-02-04
209D-11 | Europe | 270T727 | Steam Turbine | 177259 | Major Inspection (MI) |  | 2027-10-09 | 2027-11-06
307D-11 | Latin America | 270T459 | Steam Turbine | 144376 | Minor Inspection | 562183 | 2028-11-18 | 2028-11-23
307D-11 | NAM North America | 270T513 | Steam Turbine | 144401 | Major Inspection (MI) | 538324 | 2027-10-01 | 2027-11-29
307D-11 | NAM North America | 270T632 | Steam Turbine | 154817 | Major Inspection (MI) | 535060 | 2026-02-16 | 2026-04-27
307D-11 | NAM North America | 270T485 | Steam Turbine | 161029 | Minor Inspection | 539601 | 2026-03-02 | 2026-04-05
307D-11 | NAM North America | 270T543 | Steam Turbine | 163009 | Minor Inspection |  | 2029-05-23 | 2029-05-28
307D-11 | NAM North America | 270T635 | Steam Turbine | 163036 | Major Inspection (MI) | 545835 | 2027-03-04 | 2027-04-29
307D-11 | NAM North America | 270T485 | Steam Turbine | 165149 | Minor Inspection |  | 2026-04-24 | 2026-04-29
307D-11 | NAM North America | 270T485 | Steam Turbine | 165150 | Major Inspection (MI) |  | 2029-01-29 | 2029-02-26
307D-11 | NAM North America | 270T551 | Steam Turbine | 167540 | Minor Inspection | 544521 | 2026-11-04 | 2026-12-08
307D-11 | NAM North America | 270T426 | Steam Turbine | 177274 | Minor Inspection | 563522 | 2028-10-17 | 2028-11-05
307D-11 | Asia | 270T444 | Steam Turbine | 179926 | Minor Inspection | 552286 | 2027-02-04 | 2027-02-13
307D-11 | NAM North America | 270T527 | Steam Turbine | 181354 | Minor Inspection | 553010 | 2028-03-31 | 2028-04-18
307D-11 | NAM North America | 270T632 | Steam Turbine | 184858 | Minor Inspection | 555324 | 2030-02-19 | 2030-03-09
307D-11 | NAM North America | 270T543 | Steam Turbine | 191265 | Large Call-Out | 560102 | 2026-09-01 | 2026-10-15
307D-11 | NAM North America | 270T543 | Steam Turbine | 195504 | Large Call-Out | 562941 | 2027-10-04 | 2027-10-31
309C-7 | MENA | 270T357 | Steam Turbine | 182561 | Major Inspection (MI) | 553791 | 2027-10-01 | 2027-10-30
324 | MENA | 337X881 | Generator | 102663 | Major Inspection (Robotic) | 502141 | 2028-10-03 | 2028-10-30
324 | MENA | SG10185 | Generator | 104603 | Major Inspection (Robotic) | 500501 | 2028-05-01 | 2028-05-15
324 | MENA | SG10186 | Generator | 105429 | Major Inspection (Robotic) | 500500 | 2028-06-01 | 2028-06-15
324 | MENA | 337X576 | Generator | 106232 | Minor Inspection | 502331 | 2027-03-01 | 2027-04-01
324 | Europe | 337X530 | Generator | 112502 | Major Inspection (Robotic) | 504793 | 2027-10-01 | 2027-10-30
324 | Latin America | 337X542 | Generator | 112925 | Minor Inspection | 512412 | 2028-08-14 | 2028-08-28
324 | Europe | 339X202 | Generator | 118626 | Major Inspection (Robotic) | 516230 | 2028-04-01 | 2028-05-03
324 | Europe | 337X531 | Generator | 120186 | Major Inspection (Robotic) | 504813 | 2029-04-01 | 2029-04-30
324 | Europe | 337X532 | Generator | 123465 | Major Inspection (Robotic) | 504790 | 2029-04-01 | 2029-04-30
324 | Latin America | 290T682 | Generator | 126062 | Major Inspection (Rotor Out) | 503071 | 2026-03-04 | 2026-04-07
324 | MENA | GG10422 | Generator | 139807 | Minor Inspection | 502337 | 2026-02-09 | 2026-03-14
324 | MENA | 324X047 | Generator | 139815 | Minor Inspection | 500035 | 2028-04-06 | 2028-05-20
324 | MENA | 324X045 | Generator | 139928 | Minor Inspection | 500034 | 2027-10-06 | 2027-10-29
324 | MENA | 324X046 | Generator | 139932 | Minor Inspection | 502310 | 2030-04-01 | 2030-05-15
324 | MENA | 339X215 | Generator | 140000 | Minor Inspection | 523641 | 2026-11-09 | 2026-11-17
324 | NAM North America | 290T463 | Generator | 142477 | Minor Inspection | 503113 | 2026-04-19 | 2026-05-04
324 | Europe | 337X552 | Generator | 142613 | Major Inspection (Rotor Out) | 513583 | 2026-09-21 | 2026-11-27
324 | Europe | 337X557 | Generator | 142864 | Major Inspection (Robotic) | 503012 | 2026-04-16 | 2026-05-18
324 | NAM North America | 290T542 | Generator | 144977 | Minor Inspection | 528746 | 2026-03-16 | 2026-04-07
324 | Europe | 337X529 | Generator | 146965 | Major Inspection (Robotic) | 504791 | 2027-10-01 | 2027-10-30
324 | Europe | 290T797 | Generator | 148058 | Major Inspection (Stator Rewind) | 530525 | 2030-04-01 | 2030-07-15
324 | Latin America | 290T560 | Generator | 148191 | Minor Inspection | 530602 | 2026-11-04 | 2026-12-18
324 | Europe | 337X564 | Generator | 149279 | Major Inspection (Robotic) | 531305 | 2029-04-23 | 2029-06-24
324 | Europe | 337X565 | Generator | 149282 | Major Inspection (Robotic) | 531308 | 2028-04-16 | 2028-06-30
324 | MENA | 337X575 | Generator | 149752 | Minor Inspection | 502231 | 2027-01-15 | 2027-02-15
324 | Europe | 337X562A | Generator | 152034 | Minor Inspection | 502838 | 2026-09-07 | 2026-09-21
324 | Europe | 337X533 | Generator | 152109 | Major Inspection (Rotor Out) | 533181 | 2028-04-03 | 2028-04-30
324 | Europe | 337X534 | Generator | 152115 | Major Inspection (Rotor Out) | 533185 | 2028-04-03 | 2028-04-30
324 | Europe | 290T517 | Generator | 152117 | Major Inspection (Robotic) | 533186 | 2028-04-03 | 2028-04-24
324 | Europe | 337X540 | Generator | 155451 | Minor Inspection | 529938 | 2026-07-10 | 2026-08-10
324 | MENA | 337X882 | Generator | 155686 | Major Inspection (Rotor Out) | 535713 | 2026-03-17 | 2026-06-24
324 | NAM North America | 290T733 | Generator | 157548 | Major Inspection (Stator Rewind) | 535923 | 2026-03-27 | 2026-05-10
324 | NAM North America | 290T515 | Generator | 157553 | Major Inspection (Stator Rewind) | 503055 | 2026-02-07 | 2026-03-30
324 | NAM North America | 290T516 | Generator | 157556 | Major Inspection (Stator Rewind) | 535922 | 2027-01-21 | 2027-03-13
324 | NAM North America | 290T796 | Generator | 157557 | Major Inspection (Stator Rewind) | 535924 | 2027-10-01 | 2027-11-25
324 | NAM North America | 290T631 | Generator | 157559 | Major Inspection (Stator Rewind) | 537143 | 2027-02-22 | 2027-04-11
324 | Latin America | 290T917 | Generator | 157606 | Minor Inspection | 537178 | 2026-10-19 | 2026-11-04
324 | NAM North America | 290T497 | Generator | 157882 | Major Inspection (Robotic) | 537416 | 2026-01-29 | 2026-04-20
324 | Europe | 337X544 | Generator | 157978 | Major Inspection (Rotor Out) | 537490 | 2026-03-13 | 2026-06-13
324 | MENA | 339X231 | Generator | 158712 | Major Inspection (Robotic) | 534044 | 2026-11-25 | 2026-12-15
324 | MENA | 324X032 | Generator | 158713 | Major Inspection (Robotic) | 534194 | 2026-11-05 | 2026-11-25
324 | MENA | 339X232 | Generator | 158714 | Major Inspection (Robotic) | 534688 | 2026-12-15 | 2027-01-04
324 | MENA | 324X056 | Generator | 158715 | Major Inspection (Robotic) | 534689 | 2027-11-03 | 2027-11-22
324 | MENA | 324X057 | Generator | 158716 | Major Inspection (Robotic) | 534690 | 2027-12-20 | 2028-01-03
324 | MENA | 339X231 | Generator | 158718 | Major Inspection (Robotic) | 538010 | 2030-03-31 | 2030-04-28
324 | MENA | 324X032 | Generator | 158720 | Major Inspection (Robotic) | 538011 | 2030-11-01 | 2030-11-29
324 | MENA | 339X218 | Generator | 158942 | Minor Inspection | 538132 | 2027-11-10 | 2027-11-20
324 | MENA | 339X217 | Generator | 158943 | Major Inspection (Robotic) | 538133 | 2028-11-09 | 2028-11-20
324 | MENA | GG10545 | Generator | 158958 | Major Inspection (Robotic) | 538140 | 2027-03-18 | 2027-04-14
324 | MENA | 324X024 | Generator | 158959 | Major Inspection (Rotor Out) | 538141 | 2026-11-07 | 2026-12-04
324 | MENA | 337X879 | Generator | 158960 | Minor Inspection | 538142 | 2027-11-15 | 2027-12-10
324 | MENA | 324X023 | Generator | 158961 | Major Inspection (Rotor Out) | 538143 | 2027-05-10 | 2027-07-13
324 | MENA | 324X025 | Generator | 158962 | Major Inspection (Rotor Out) | 538144 | 2027-10-21 | 2027-11-17
324 | MENA | 337X882 | Generator | 158963 | Minor Inspection | 538145 | 2028-03-31 | 2028-04-28
324 | MENA | 337X877 | Generator | 158964 | Major Inspection (Robotic) | 538146 | 2028-11-25 | 2028-12-23
324 | MENA | GG10545 | Generator | 158966 | Minor Inspection | 538147 | 2030-01-01 | 2030-01-29
324 | MENA | 337X879 | Generator | 158968 | Major Inspection (Robotic) | 538148 | 2030-03-31 | 2030-04-28
324 | MENA | 324X023 | Generator | 158972 | Minor Inspection | 538149 | 2030-03-27 | 2030-04-24
324 | MENA | 324X024 | Generator | 158973 | Minor Inspection | 538150 | 2029-03-31 | 2029-04-28
324 | MENA | 324X025 | Generator | 158975 | Minor Inspection | 538151 | 2030-03-31 | 2030-04-28
324 | MENA | GG10403 | Generator | 158979 | Minor Inspection | 538153 | 2027-12-27 | 2028-01-25
324 | MENA | GG10404 | Generator | 158981 | Minor Inspection | 538154 | 2028-03-01 | 2028-03-30
324 | MENA | GG10413 | Generator | 158998 | Minor Inspection | 538161 | 2029-10-01 | 2029-10-15
324 | MENA | GG10416 | Generator | 158999 | Minor Inspection | 538162 | 2030-11-02 | 2030-11-16
324 | MENA | GG10424 | Generator | 159013 | Minor Inspection | 500416 | 2027-03-03 | 2027-04-01
324 | MENA | GG10405 | Generator | 159018 | Minor Inspection | 500120 | 2030-10-01 | 2030-10-30
324 | MENA | 324X048 | Generator | 159081 | Major Inspection (Rotor Out) | 538195 | 2027-12-01 | 2028-01-14
324 | MENA | 324X050 | Generator | 159082 | Major Inspection (Robotic) | 538196 | 2029-02-25 | 2029-03-29
324 | MENA | 324X049 | Generator | 159083 | Major Inspection (Rotor Out) | 538197 | 2028-09-15 | 2028-10-13
324 | MENA | 324X047 | Generator | 159088 | Major Inspection (Robotic) | 538200 | 2027-09-21 | 2027-10-19
324 | MENA | 324X046 | Generator | 159090 | Major Inspection (Robotic) | 538201 | 2026-11-05 | 2026-12-03
324 | MENA | GG10412 | Generator | 159092 | Minor Inspection | 538202 | 2028-06-30 | 2028-07-28
324 | Europe | 337X541 | Generator | 159120 | Major Inspection (Robotic) | 515514 | 2028-05-12 | 2028-06-22
324 | NAM North America | 290T769 | Generator | 159650 | Minor Inspection | 538635 | 2026-09-28 | 2026-10-16
324 | NAM North America | 290T294 | Generator | 160505 | Major Inspection (Robotic) | 528377 | 2026-02-28 | 2026-07-01
324 | Asia | 324X015 | Generator | 160844 | Minor Inspection | 539424 | 2026-10-01 | 2026-10-07
324 | Asia | 324X016 | Generator | 160845 | Minor Inspection | 539425 | 2026-10-06 | 2026-10-12
324 | Asia | 290T831 | Generator | 160846 | Minor Inspection | 539426 | 2026-10-08 | 2026-10-15
324 | NAM North America | 324X066 | Generator | 162699 | Minor Inspection | 540972 | 2028-10-14 | 2028-11-12
324 | MENA | 337X878 | Generator | 162785 | Minor Inspection | 537976 | 2026-06-23 | 2026-07-27
324 | Europe | 337X538 | Generator | 163067 | Major Inspection (Robotic) | 541186 | 2029-06-01 | 2029-06-30
324 | Europe | 337X539 | Generator | 163069 | Major Inspection (Robotic) | 541187 | 2029-06-15 | 2029-07-14
324 | MENA | 337X586 | Generator | 163221 | Minor Inspection | 541317 | 2029-01-15 | 2029-02-07
324 | MENA | 337X585 | Generator | 163223 | Minor Inspection | 541318 | 2029-10-01 | 2029-10-24
324 | Europe | 324X037 | Generator | 163295 | Major Inspection (Robotic) | 541375 | 2028-08-01 | 2028-08-31
324 | Europe | 337X548 | Generator | 163389 | Major Inspection (Robotic) | 541461 | 2027-10-04 | 2027-11-12
324 | Asia | 324X044 | Generator | 163474 | Major Inspection (Rotor Out) | 540973 | 2028-08-01 | 2028-08-31
324 | NAM North America | 290T929 | Generator | 164381 | Major Inspection (Robotic) | 541338 | 2026-03-08 | 2026-04-28
324 | NAM North America | 290T578 | Generator | 165378 | Major Inspection (Robotic) | 542932 | 2028-03-08 | 2028-05-22
324 | NAM North America | 290T577 | Generator | 165841 | Major Inspection (Rotor Out) | 543236 | 2027-03-10 | 2027-05-24
324 | NAM North America | 290T741 | Generator | 166411 | Minor Inspection | 542431 | 2027-04-01 | 2027-04-29
324 | NAM North America | 290T532 | Generator | 166817 | Minor Inspection | 543920 | 2028-04-01 | 2028-04-15
324 | Latin America | 290T699 | Generator | 167046 | Minor Inspection | 544067 | 2026-01-06 | 2026-01-26
324 | Latin America | 290T700 | Generator | 167049 | Minor Inspection | 544071 | 2026-02-05 | 2026-02-20
324 | MENA | GG10406 | Generator | 167106 | Minor Inspection | 502346 | 2028-03-15 | 2028-04-13
324 | MENA | GG10407 | Generator | 167107 | Minor Inspection | 500123 | 2029-02-01 | 2029-02-28
324 | MENA | GG10408 | Generator | 167108 | Major Inspection (Robotic) | 500122 | 2028-02-01 | 2028-03-01
324 | Latin America | 290T700 | Generator | 167119 | Major Inspection (Rotor Out) | 544130 | 2030-09-20 | 2030-10-18
324 | MENA | GG10401 | Generator | 167138 | Minor Inspection | 544147 | 2027-11-07 | 2027-12-06
324 | NAM North America | 290T491 | Generator | 167921 | Minor Inspection | 544844 | 2028-09-30 | 2028-10-14
324 | MENA | 337X592 | Generator | 168097 | Major Inspection (Rotor Out) | 544997 | 2028-02-14 | 2028-03-17
324 | MENA | 337X593 | Generator | 168098 | Major Inspection (Rotor Out) | 544998 | 2027-02-01 | 2027-03-05
324 | MENA | 337X594 | Generator | 168100 | Major Inspection (Robotic) | 544999 | 2030-09-01 | 2030-09-29
324 | MENA | 339X225 | Generator | 168103 | Minor Inspection | 545001 | 2029-06-20 | 2029-07-19
324 | MENA | GG10449 | Generator | 168104 | Minor Inspection | 545002 | 2028-07-28 | 2028-08-25
324 | MENA | GG10448 | Generator | 168105 | Minor Inspection | 545003 | 2028-07-28 | 2028-08-25
324 | MENA | GG10447 | Generator | 168106 | Minor Inspection | 545004 | 2028-04-14 | 2028-05-12
324 | MENA | GG10446 | Generator | 168107 | Minor Inspection | 545005 | 2028-04-14 | 2028-05-12
324 | MENA | GG10460 | Generator | 168108 | Minor Inspection | 545006 | 2028-10-10 | 2028-11-07
324 | MENA | GG10459 | Generator | 168109 | Minor Inspection | 545007 | 2029-12-05 | 2030-01-02
324 | MENA | GG10461 | Generator | 168111 | Minor Inspection | 545008 | 2029-03-15 | 2029-03-29
324 | MENA | GG10462 | Generator | 168112 | Minor Inspection | 545009 | 2029-07-04 | 2029-08-01
324 | MENA | GG10414 | Generator | 168113 | Minor Inspection | 538484 | 2029-11-01 | 2029-11-15
324 | MENA | GG10415 | Generator | 168114 | Minor Inspection | 545010 | 2030-10-01 | 2030-10-15
324 | MENA | SG10192 | Generator | 168231 | Minor Inspection |  | 2026-11-01 | 2026-11-30
324 | MENA | SG10192 | Generator | 168232 | Minor Inspection | 543011 | 2027-02-01 | 2027-03-02
324 | MENA | 290T905 | Generator | 168233 | Minor Inspection | 542941 | 2026-02-15 | 2026-05-15
324 | NAM North America | 290T885 | Generator | 168519 | Major Inspection (Robotic) | 545342 | 2027-01-19 | 2027-03-04
324 | China | 337X568 | Generator | 168667 | Minor Inspection | 540332 | 2028-03-20 | 2028-04-13
324 | China | 337X569 | Generator | 168668 | Minor Inspection | 540333 | 2029-03-20 | 2029-04-13
324 | China | 339X207 | Generator | 168676 | Major Inspection (Robotic) | 545467 | 2028-12-12 | 2029-01-09
324 | China | 337X595 | Generator | 168678 | Major Inspection (Robotic) | 545468 | 2029-12-15 | 2030-01-12
324 | Asia | GG10606 | Generator | 168730 | Minor Inspection | 545503 | 2028-08-27 | 2028-09-24
324 | Latin America | 337X502 | Generator | 168783 | Minor Inspection | 545549 | 2029-08-22 | 2029-09-19
324 | NAM North America | 290T537 | Generator | 168902 | Major Inspection (Stator Rewind) | 545649 | 2028-03-04 | 2028-05-12
324 | Latin America | 324X042 | Generator | 169083 | Minor Inspection | 545807 | 2028-01-25 | 2028-02-26
324 | Latin America | 324X074 | Generator | 169106 | Major Inspection (Robotic) | 545829 | 2028-03-07 | 2028-04-04
324 | MENA | 337X594 | Generator | 169165 | Minor Inspection | 545877 | 2027-03-08 | 2027-03-29
324 | MENA | 324X035 | Generator | 169181 | Minor Inspection | 537817 | 2027-03-13 | 2027-03-27
324 | MENA | 324X021 | Generator | 169182 | Minor Inspection | 537815 | 2027-04-30 | 2027-05-14
324 | MENA | 324X022 | Generator | 169183 | Minor Inspection | 537816 | 2027-05-27 | 2027-06-10
324 | MENA | 324X036 | Generator | 169187 | Minor Inspection | 537818 | 2028-07-14 | 2028-07-28
324 | MENA | 324X035 | Generator | 169189 | Major Inspection (Robotic) | 545888 | 2030-10-17 | 2030-11-14
324 | MENA | 324X022 | Generator | 169191 | Major Inspection (Robotic) | 545889 | 2030-07-05 | 2030-08-02
324 | MENA | 324X021 | Generator | 169193 | Major Inspection (Robotic) | 545890 | 2030-02-09 | 2030-03-09
324 | MENA | 337X580 | Generator | 169280 | Major Inspection (Robotic) | 545934 | 2028-11-30 | 2028-12-28
324 | MENA | 337X581 | Generator | 169281 | Major Inspection (Robotic) | 545935 | 2028-04-01 | 2028-04-29
324 | Latin America | 337X510 | Generator | 169444 | Major Inspection (Robotic) | 543466 | 2028-03-21 | 2028-04-07
324 | MENA | 339X232 | Generator | 169457 | Major Inspection (Robotic) | 546040 | 2030-03-31 | 2030-04-28
324 | MENA | SG10181 | Generator | 169861 | Minor Inspection | 546242 | 2027-10-15 | 2027-11-13
324 | MENA | SG10182 | Generator | 169868 | Minor Inspection | 546246 | 2028-02-17 | 2028-03-17
324 | MENA | GG10412 | Generator | 169967 | Minor Inspection | 546348 | 2028-04-01 | 2028-04-24
324 | MENA | GG10412 | Generator | 169968 | Minor Inspection | 500076 | 2028-04-01 | 2028-04-24
324 | MENA | GG10411 | Generator | 169969 | Minor Inspection | 500077 | 2028-03-01 | 2028-03-24
324 | MENA | GG10410 | Generator | 169970 | Minor Inspection | 500074 | 2028-02-01 | 2028-02-24
324 | MENA | GG10409 | Generator | 169971 | Minor Inspection | 500075 | 2028-01-01 | 2028-01-24
324 | MENA | SG10187 | Generator | 170007 | Minor Inspection | 500240 | 2029-10-01 | 2029-10-15
324 | MENA | SG10188 | Generator | 170008 | Minor Inspection | 500241 | 2030-10-01 | 2030-10-15
324 | NAM North America | 290T489 | Generator | 170278 | Major Inspection (Robotic) | 534412 | 2027-08-28 | 2027-11-12
324 | MENA | 339X211 | Generator | 170457 | Minor Inspection | 546667 | 2027-02-26 | 2027-03-29
324 | Europe | 337X574 | Generator | 170479 | Major Inspection (Rotor Out) | 546682 | 2026-09-15 | 2026-12-15
324 | Europe | 337X553 | Generator | 170878 | Major Inspection (Rotor Out) | 546820 | 2027-02-20 | 2027-04-17
324 | NAM North America | 290T619 | Generator | 171823 | Major Inspection (Robotic) | 547232 | 2026-02-03 | 2026-03-19
324 | MENA | 324X023 | Generator | 172203 | Major Inspection (Stator Rewind) | 547607 | 2027-04-17 | 2027-06-20
324 | NAM North America | 290T538 | Generator | 172370 | Minor Inspection | 547688 | 2027-10-05 | 2027-11-15
324 | NAM North America | 290T537 | Generator | 172375 | Minor Inspection | 547690 | 2028-03-04 | 2028-05-12
324 | Europe | 324X100 | Generator | 172524 | Minor Inspection | 547806 | 2028-09-06 | 2028-09-13
324 | Europe | 324X100 | Generator | 172525 | Major Inspection (Robotic) | 547807 | 2030-12-15 | 2031-01-12
324 | Europe | 324X038 | Generator | 175265 | Major Inspection (Robotic) | 541471 | 2028-12-01 | 2028-12-31
324 | Europe | 290T845 | Generator | 175266 | Major Inspection (Robotic) | 544100 | 2028-08-01 | 2028-08-31
324 | NAM North America | 290T635 | Generator | 175658 | Minor Inspection | 545835 | 2027-03-04 | 2027-04-29
324 | NAM North America | 324X067 | Generator | 175668 | Minor Inspection | 549774 | 2029-04-14 | 2029-05-09
324 | Europe | 337X583 | Generator | 175946 | Major Inspection (Robotic) |  | 2026-03-23 | 2026-06-09
324 | MENA | GG10409 | Generator | 176701 | Stand Alone Small Upgrade | 550457 | 2028-09-01 | 2028-10-03
324 | MENA | GG10410 | Generator | 176703 | Stand Alone Small Upgrade | 550458 | 2028-10-01 | 2028-11-02
324 | MENA | GG10411 | Generator | 176705 | Stand Alone Small Upgrade | 550459 | 2028-11-01 | 2028-12-03
324 | MENA | GG10412 | Generator | 176707 | Stand Alone Small Upgrade | 550460 | 2028-12-01 | 2029-01-02
324 | NAM North America | 290T657 | Generator | 176988 | Major Inspection (Robotic) | 556248 | 2027-03-15 | 2027-04-13
324 | NAM North America | 290T294 | Generator | 177289 | Minor Inspection | 550872 | 2029-08-24 | 2029-09-21
324 | NAM North America | 290T503 | Generator | 177444 | Major Inspection (Robotic) | 550914 | 2028-03-26 | 2028-04-23
324 | MENA | SG10183 | Generator | 179422 | Minor Inspection | 500323 | 2028-03-01 | 2028-03-30
324 | Europe | 337X528 | Generator | 179529 | Major Inspection (Robotic) | 507313 | 2030-10-01 | 2030-10-31
324 | Europe | 337X527 | Generator | 179530 | Major Inspection (Robotic) | 503014 | 2030-10-01 | 2030-10-30
324 | Europe | 337X525 | Generator | 179705 | Major Inspection (Robotic) | 552155 | 2028-10-05 | 2028-10-30
324 | Europe | 339X206 | Generator | 179843 | Major Inspection (Stator Rewind) | 552230 | 2027-07-12 | 2027-12-07
324 | MENA | SG10184 | Generator | 180650 | Major Inspection (Robotic) | 500324 | 2028-02-01 | 2028-03-01
324 | Asia | 339X229 | Generator | 180727 | Major Inspection (Rotor Out) | 552750 | 2028-03-15 | 2028-06-19
324 | MENA | 339X213 | Generator | 180849 | Minor Inspection | 552829 | 2028-03-06 | 2028-04-05
324 | MENA | 339X214 | Generator | 180851 | Minor Inspection | 552831 | 2029-03-05 | 2029-04-05
324 | MENA | 290T919 | Generator | 181430 | Minor Inspection | 553075 | 2028-07-24 | 2028-07-29
324 | MENA | 324X018 | Generator | 181796 | Major Inspection (Robotic) | 553335 | 2028-02-14 | 2028-03-13
324 | MENA | 324X017 | Generator | 181798 | Major Inspection (Robotic) | 553336 | 2028-09-28 | 2028-10-26
324 | Europe | 337X545 | Generator | 182041 | Major Inspection (Robotic) | 553513 | 2030-09-08 | 2030-10-30
324 | MENA | 290T357 | Generator | 182562 | Major Inspection (Rotor Out) | 553791 | 2027-10-01 | 2027-10-30
324 | Asia | 324X015 | Generator | 182761 | Minor Inspection | 552617 | 2029-06-27 | 2029-07-11
324 | Latin America | 324X043 | Generator | 182889 | Major Inspection (Robotic) | 554019 | 2028-03-02 | 2028-04-03
324 | Latin America | 290T887 | Generator | 182890 | Major Inspection (Robotic) | 554020 | 2028-01-25 | 2028-01-30
324 | MENA | 339X224 | Generator | 182993 | Minor Inspection | 554095 | 2029-05-25 | 2029-06-22
324 | MENA | 337X593 | Generator | 183164 | Minor Inspection | 554210 | 2030-03-06 | 2030-04-03
324 | MENA | GG10421 | Generator | 183632 | Major Inspection (Robotic) | 554498 | 2028-11-01 | 2028-11-28
324 | MENA | GG10422 | Generator | 183635 | Major Inspection (Robotic) | 554499 | 2030-03-01 | 2030-03-28
324 | MENA | 324X029 | Generator | 183665 | Major Inspection (Robotic) | 554515 | 2030-11-20 | 2030-12-18
324 | Europe | 337X560 | Generator | 183668 | Minor Inspection | 554516 | 2026-07-24 | 2026-08-07
324 | NAM North America | 290T500 | Generator | 183679 | Minor Inspection | 554522 | 2026-10-03 | 2026-11-03
324 | Europe | 337X574 | Generator | 183710 | Major Inspection (Robotic) | 554536 | 2026-04-22 | 2026-05-20
324 | Europe | 337X574 | Generator | 183712 | Minor Inspection | 554537 | 2030-11-30 | 2030-12-14
324 | Europe | 337X548 | Generator | 183716 | Major Inspection (Robotic) | 554538 | 2027-03-12 | 2027-04-09
324 | Europe | 337X549 | Generator | 183717 | Major Inspection (Robotic) | 554539 | 2027-03-12 | 2027-04-09
324 | Europe | 337X554 | Generator | 183733 | Major Inspection (Rotor Out) | 554548 | 2028-03-01 | 2028-04-14
324 | MENA | 337X578 | Generator | 183801 | Major Inspection (Stator Rewind) | 553564 | 2026-01-26 | 2026-04-28
324 | MENA | 290T918 | Generator | 183861 | Major Inspection (Stator Rewind) | 554973 | 2027-06-01 | 2027-07-30
324 | MENA | GG10692 | Generator | 183895 | Minor Inspection | 554660 | 2030-03-31 | 2030-04-14
324 | MENA | GG10693 | Generator | 183897 | Minor Inspection | 554662 | 2030-09-30 | 2030-10-14
324 | Europe | 324X108 | Generator | 183954 | Major Inspection (Rotor Out) | 554692 | 2029-06-18 | 2029-07-27
324 | MENA | 324X019 | Generator | 184249 | Major Inspection (Robotic) | 537813 | 2028-06-09 | 2028-06-23
324 | MENA | 324X020 | Generator | 184250 | Major Inspection (Robotic) | 537814 | 2028-07-09 | 2028-08-08
324 | NAM North America | 290T552 | Generator | 184302 | Minor Inspection | 554928 | 2029-04-07 | 2029-04-25
324 | NAM North America | SG10205 | Generator | 184325 | Major Inspection (Robotic) | 544680 | 2028-03-06 | 2028-04-15
324 | Latin America | 290T683 | Generator | 184501 | Minor Inspection | 555070 | 2029-01-16 | 2029-02-05
324 | NAM North America | 290T711 | Generator | 184624 | Major Inspection (Robotic) | 555008 | 2027-10-31 | 2027-12-30
324 | Latin America | 290T599 | Generator | 184630 | Major Inspection (Robotic) | 534883 | 2030-06-25 | 2030-07-24
324 | Latin America | 290T559 | Generator | 184647 | Major Inspection (Rotor Out) | 555073 | 2029-03-03 | 2029-04-08
324 | NAM North America | 290T492 | Generator | 184905 | Major Inspection (Robotic) | 555364 | 2026-02-02 | 2026-02-28
324 | NAM North America | 290T680 | Generator | 184946 | Minor Inspection | 555389 | 2026-03-10 | 2026-03-26
324 | NAM North America | 290T531 | Generator | 185581 | Major Inspection (Rotor Out) | 553025 | 2028-03-16 | 2028-05-31
324 | NAM North America | 290T610 | Generator | 185727 | Minor Inspection | 555957 | 2027-10-25 | 2027-11-05
324 | MENA | 324X040 | Generator | 185923 | Stand Alone Small Upgrade | 550461 | 2027-10-15 | 2027-11-05
324 | NAM North America | 290T490 | Generator | 185927 | Minor Inspection | 556095 | 2030-04-13 | 2030-05-01
324 | Europe | 290T797 | Generator | 186429 | Minor Inspection | 556465 | 2027-04-01 | 2027-05-31
324 | Asia | 324X016 | Generator | 187125 | Minor Inspection | 552618 | 2029-06-27 | 2029-07-11
324 | Asia | 290T831 | Generator | 187126 | Minor Inspection | 552619 | 2029-06-27 | 2029-07-02
324 | Europe | 337X524 | Generator | 188345 | Large Call-Out |  | 2026-11-15 | 2026-12-05
324 | NAM North America | 290T500 | Generator | 188757 | Major Inspection (Robotic) | 557942 | 2030-03-01 | 2030-05-31
324 | Europe | 337X540 | Generator | 189145 | Stand Alone Large Upgrade | 558237 | 2029-06-01 | 2029-08-30
324 | Europe | 337X541 | Generator | 189146 | Stand Alone Large Upgrade | 558238 | 2030-06-01 | 2030-08-30
324 | MENA | GG10447 | Generator | 190018 | Major Inspection (Stator Rewind) | 558843 | 2026-01-31 | 2026-05-25
324 | Europe | 337X560 | Generator | 190263 | Major Inspection (Rotor Out) | 559039 | 2028-04-10 | 2028-06-16
324 | Europe | 337X560 | Generator | 190264 | Major Inspection (Field Rewind) | 559038 | 2028-06-19 | 2028-11-06
324 | MENA | GG10448 | Generator | 190325 | Major Inspection (Stator Rewind) | 561001 | 2026-10-13 | 2026-12-31
324 | MENA | GG10449 | Generator | 190326 | Major Inspection (Stator Rewind) | 561000 | 2027-01-01 | 2027-03-21
324 | MENA | GG10461 | Generator | 190327 | Major Inspection (Stator Rewind) | 559084 | 2027-03-22 | 2027-06-09
324 | MENA | 290T810 | Generator | 190385 | Minor Inspection | 559133 | 2026-11-09 | 2026-11-25
324 | MENA | 337X578 | Generator | 191168 | Minor Inspection | 559719 | 2028-03-01 | 2028-03-21
324 | MENA | 324X041 | Generator | 191442 | Stand Alone Small Upgrade | 550462 | 2027-11-15 | 2027-12-05
324 | MENA | 324X002 | Generator | 193145 | Major Inspection (Rotor Out) | 560951 | 2027-02-02 | 2027-03-03
324 | MENA | 324X003 | Generator | 193148 | Major Inspection (Rotor Out) | 560953 | 2027-01-02 | 2027-01-31
324 | MENA | GG10460 | Generator | 193564 | Major Inspection (Stator Rewind) | 561317 | 2027-10-11 | 2027-12-31
324 | MENA | GG10462 | Generator | 193565 | Major Inspection (Stator Rewind) | 561318 | 2028-01-16 | 2028-04-15
324 | NAM North America | 290T462 | Generator | 193640 | Minor Inspection | 558968 | 2028-10-01 | 2028-11-01
324 | MENA | 324X029 | Generator | 194283 | Large Call-Out | 562432 | 2026-10-25 | 2026-11-10
324 | MENA | 324X028 | Generator | 194284 | Large Call-Out | 561934 | 2026-12-25 | 2027-01-10
324 | MENA | 324X017 | Generator | 194316 | Large Call-Out | 562034 | 2026-09-01 | 2026-10-30
324 | MENA | 324X036 | Generator | 194558 | Minor Inspection | 562367 | 2026-11-01 | 2026-11-08
324 | MENA | 324X036 | Generator | 194901 | Minor Inspection | 500834 | 2027-04-01 | 2027-04-14
324 | NAM North America | 290T733 | Generator | 195342 | Large Call-Out | 562805 | 2027-03-22 | 2027-04-05
324 | MENA | GG10414 | Generator | 195656 | Minor Inspection | 563039 | 2028-07-25 | 2028-08-08
324 | MENA | GG10413 | Generator | 195661 | Minor Inspection | 563040 | 2028-10-03 | 2028-10-17
324 | MENA | GG10415 | Generator | 195665 | Minor Inspection | 563041 | 2030-01-08 | 2030-01-22
324 | NAM North America | 290T912 | Generator | 195747 | Minor Inspection |  | 2027-05-03 | 2027-05-20
324 | NAM North America | 290T912 | Generator | 195776 | Minor Inspection | 563120 | 2027-05-03 | 2027-05-20
324 | Europe | 337X547 | Generator | 195861 | Major Inspection (Robotic) | 563194 | 2026-09-01 | 2026-09-29
324 | Europe | 337X552 | Generator | 195862 | Major Inspection (Robotic) | 563195 | 2026-09-01 | 2026-09-29
324 | Europe | 337X564 | Generator | 195883 | Minor Inspection | 563210 | 2027-02-01 | 2027-02-15
330H | Europe | 290T708 | Generator | 137369 | Major Inspection (Stator Rewind) | 524613 | 2030-07-01 | 2030-10-08
330H | Europe | 962X028 | Generator | 144570 | Minor Inspection | 528498 | 2026-03-30 | 2026-06-07
330H | Europe | 962X007 | Generator | 145207 | Major Inspection (Rotor Out) | 528929 | 2028-04-24 | 2028-05-31
330H | Europe | 962X008 | Generator | 145677 | Major Inspection (Stator Rewind) | 529205 | 2027-03-01 | 2027-06-10
330H | Europe | 962X031 | Generator | 148950 | Major Inspection (Stator Rewind) | 531068 | 2030-04-01 | 2030-07-15
330H | Europe | 962X022 | Generator | 151969 | Minor Inspection | 533059 | 2028-02-06 | 2028-02-27
330H | Europe | 962X023 | Generator | 151971 | Major Inspection (Robotic) | 533060 | 2028-02-14 | 2028-03-05
330H | Europe | 290T727 | Generator | 151973 | Major Inspection (Stator Rewind) | 533061 | 2026-01-19 | 2026-04-24
330H | Europe | 290T890 | Generator | 151993 | Major Inspection (Stator Rewind) | 533081 | 2027-05-17 | 2027-07-02
330H | Europe | 962X045 | Generator | 151995 | Major Inspection (Robotic) | 533082 | 2027-05-17 | 2027-07-02
330H | MENA | 962X014 | Generator | 157689 | Minor Inspection | 537245 | 2026-01-16 | 2026-02-04
330H | Europe | 962X039 | Generator | 157797 | Major Inspection (Robotic) | 503483 | 2026-04-05 | 2026-10-01
330H | Europe | 290T873 | Generator | 157800 | Major Inspection (Robotic) | 537340 | 2026-04-12 | 2026-10-01
330H | Europe | 962X046 | Generator | 159045 | Major Inspection (Robotic) | 503652 | 2029-04-01 | 2029-04-30
330H | MENA | 962X016 | Generator | 163296 | Minor Inspection | 538807 | 2026-02-01 | 2026-02-18
330H | Europe | 962X043 | Generator | 164131 | Major Inspection (Rotor Out) | 542045 | 2028-04-17 | 2028-05-21
330H | Europe | 962X031 | Generator | 164430 | Minor Inspection | 542315 | 2027-04-01 | 2027-04-30
330H | Europe | 962X030 | Generator | 164433 | Minor Inspection | 542316 | 2029-04-01 | 2029-04-30
330H | Europe | 962X005 | Generator | 166719 | Major Inspection (Robotic) | 543830 | 2026-11-02 | 2027-01-20
330H | Europe | 962X006 | Generator | 166721 | Major Inspection (Robotic) | 543831 | 2027-02-04 | 2027-03-01
330H | Europe | 290T708 | Generator | 166723 | Major Inspection (Robotic) | 543832 | 2027-02-01 | 2027-04-22
330H | Europe | 962X030 | Generator | 167281 | Major Inspection (Stator Rewind) | 544287 | 2026-04-01 | 2026-07-19
330H | MENA | 962X013 | Generator | 168367 | Major Inspection (Rotor Out) | 545225 | 2028-02-29 | 2028-03-21
330H | MENA | 962X012 | Generator | 168369 | Major Inspection (Robotic) | 545201 | 2028-02-07 | 2028-02-28
330H | MENA | 962X017 | Generator | 168371 | Major Inspection (Robotic) | 545226 | 2029-01-16 | 2029-02-06
330H | MENA | 962X015 | Generator | 168372 | Major Inspection (Robotic) | 545227 | 2029-02-07 | 2029-02-28
330H | MENA | 962X016 | Generator | 168375 | Major Inspection (Robotic) | 545228 | 2029-10-01 | 2029-10-29
330H | MENA | 962X014 | Generator | 168376 | Major Inspection (Robotic) | 545229 | 2029-10-01 | 2029-10-29
330H | MENA | 290T760 | Generator | 170093 | Minor Inspection | 546399 | 2026-01-15 | 2026-02-04
330H | Europe | 962X022 | Generator | 172768 | Large Call-Out | 547956 | 2026-01-28 | 2026-04-06
330H | Europe | 962X027 | Generator | 175649 | Major Inspection (Robotic) | 549755 | 2029-04-02 | 2029-06-08
330H | Europe | 962X026 | Generator | 175650 | Major Inspection (Robotic) | 549756 | 2028-04-03 | 2028-06-09
330H | Europe | 962X028 | Generator | 175653 | Major Inspection (Robotic) | 549757 | 2030-04-01 | 2030-06-07
330H | Europe | 290T890 | Generator | 177589 | Major Inspection (Stator Rewind) | 551021 | 2026-11-01 | 2026-12-31
330H | Europe | 962X038 | Generator | 180340 | Major Inspection (Robotic) | 552475 | 2028-09-04 | 2028-10-13
330H | Europe | 962X022 | Generator | 187666 | Minor Inspection | 557289 | 2026-12-06 | 2026-12-20
330H | Europe | 962X023 | Generator | 187668 | Minor Inspection | 557290 | 2027-02-24 | 2027-03-10
330H | Europe | 962X019 | Generator | 189147 | Stand Alone Large Upgrade | 558239 | 2029-01-01 | 2029-04-30
330H | Europe | 962X045 | Generator | 190247 | Major Inspection (Robotic) | 560122 | 2026-05-22 | 2026-05-31
330H | Europe | 962X046 | Generator | 191816 | Major Inspection (Stator Rewind) | 560135 | 2029-05-31 | 2029-07-30
330H | Europe | 962X039 | Generator | 194534 | Major Inspection (Stator Rewind) |  | 2026-06-15 | 2026-08-30
390H | Europe | 290T634 | Generator | 124891 | Major Inspection (Robotic) | 513539 | 2026-10-20 | 2027-01-16
390H | NAM North America | 290T556 | Generator | 148683 | Major Inspection (Rotor Out) |  | 2026-10-19 | 2026-11-15
390H | NAM North America | 290T632 | Generator | 154818 | Major Inspection (Rotor Out) | 535060 | 2026-02-16 | 2026-04-27
390H | NAM North America | 290T513 | Generator | 159273 | Major Inspection (Rotor Out) | 538324 | 2027-10-01 | 2027-11-29
390H | NAM North America | 290T485 | Generator | 161030 | Major Inspection (Robotic) | 539601 | 2026-03-02 | 2026-03-23
390H | Europe | 290T633 | Generator | 167262 | Major Inspection (Robotic) | 544265 | 2026-01-19 | 2026-02-26
390H | NAM North America | 290T551 | Generator | 167541 | Major Inspection (Stator Rewind) | 544521 | 2026-11-04 | 2026-12-08
390H | Latin America | 290T654 | Generator | 176036 | Minor Inspection | 550003 | 2027-01-16 | 2027-01-30
390H | NAM North America | 290T527 | Generator | 181355 | Minor Inspection | 553010 | 2028-03-31 | 2028-04-18
390H | NAM North America | 290T632 | Generator | 184859 | Minor Inspection | 555324 | 2030-02-19 | 2030-03-09
390H | Europe | 290T511 | Generator | 189666 | Minor Inspection | 558556 | 2029-09-04 | 2029-09-18
390H | Europe | 290T633 | Generator | 194306 | Major Inspection (Rotor Out) | 561957 | 2029-09-03 | 2029-11-30
390H | Europe | 290T634 | Generator | 194308 | Minor Inspection | 561958 | 2030-06-03 | 2030-07-20
390H | NAM North America | 290T426 | Generator | 196261 | Minor Inspection | 563522 | 2028-10-17 | 2028-11-05
450H | Europe | 290T706 | Generator | 108922 | Major Inspection (Stator Rewind) | 515466 | 2026-01-12 | 2026-02-15
450H | Europe | 290T706 | Generator | 119418 | Major Inspection (Stator Rewind) | 509193 | 2027-04-10 | 2027-07-12
450H | MENA | 290T726 | Generator | 139805 | Minor Inspection | 502670 | 2026-05-06 | 2026-05-25
450H | MENA | 290T718 | Generator | 139811 | Minor Inspection | 502671 | 2026-02-04 | 2026-03-10
450H | Europe | 290T800 | Generator | 141438 | Major Inspection (Stator Rewind) | 526763 | 2029-02-05 | 2029-03-02
450H | MENA | 290T793 | Generator | 158882 | Major Inspection (Robotic) | 528979 | 2027-01-01 | 2027-01-29
450H | MENA | 290T794 | Generator | 158883 | Major Inspection (Robotic) | 528980 | 2028-09-01 | 2028-10-20
450H | MENA | 290T792 | Generator | 158885 | Major Inspection (Robotic) | 538106 | 2029-12-12 | 2030-01-09
450H | Europe | 290T780 | Generator | 159037 | Major Inspection (Stator Rewind) | 538174 | 2029-08-04 | 2029-09-01
450H | Europe | 290T886 | Generator | 159118 | Minor Inspection | 538216 | 2028-03-01 | 2028-03-27
450H | Europe | 290T739 | Generator | 162028 | Minor Inspection | 540436 | 2027-03-01 | 2027-04-30
450H | Europe | 290T767 | Generator | 167033 | Major Inspection (Robotic) | 544055 | 2026-02-23 | 2026-05-18
450H | MENA | 290T725 | Generator | 179423 | Minor Inspection | 536780 | 2028-04-01 | 2028-04-22
450H | MENA | 290T794 | Generator | 181292 | Large Call-Out | 552969 | 2027-02-15 | 2027-03-17
450H | Europe | 290T706 | Generator | 182333 | Major Inspection (Stator Rewind) | 553694 | 2027-05-03 | 2027-07-03
450H | Europe | 290T722 | Generator | 183442 | Major Inspection (Rotor Out) | 554386 | 2028-09-14 | 2028-10-23
450H | Europe | 290T719 | Generator | 187655 | Minor Inspection | 557285 | 2028-04-19 | 2028-05-26
450H | Europe | 290T740 | Generator | 188249 | Minor Inspection | 557004 | 2026-03-21 | 2026-03-23
450H | Europe | 290T800 | Generator | 190798 | Major Inspection (Stator Rewind) | 503007 | 2028-09-10 | 2028-10-08
450H | MENA | 290T793 | Generator | 191991 | Large Call-Out | 560828 | 2027-01-10 | 2027-02-06
450H | MENA | 290T792 | Generator | 193420 | Large Call-Out | 561366 | 2027-02-14 | 2027-03-05
450H | Europe | 290T778 | Generator | 194266 | Major Inspection (Stator Rewind) | 561922 | 2028-04-14 | 2028-05-31
2316RT2 | NAM North America | 813840 | Steam Turbine | 191096 | Minor Inspection | 559659 | 2028-04-03 | 2028-05-16
137960 | Asia | G26103-HRSG | HRSG | 175440 | Minor Inspection | 549608 | 2026-02-20 | 2026-04-05
14130022H | MENA | 299281-HRSG | HRSG | 155292 | Minor Inspection |  | 2030-06-30 | 2030-07-05
14130022H | MENA | 299311-HRSG | HRSG | 155293 | Minor Inspection |  | 2030-09-30 | 2030-10-05
14130022H | MENA | 299310-HRSG | HRSG | 155299 | Minor Inspection |  | 2030-08-31 | 2030-09-05
14130022H | MENA | 299282-HRSG | HRSG | 155301 | Minor Inspection |  | 2030-07-31 | 2030-08-05
A10 | MENA | 270T903 | Steam Turbine | 103621 | Minor Inspection | 500323 | 2028-03-01 | 2028-03-30
A10 | MENA | 270T900 | Steam Turbine | 104043 | Minor Inspection | 500241 | 2030-10-01 | 2030-10-15
A10 | MENA | 270T904 | Steam Turbine | 104654 | Minor Inspection | 500324 | 2028-02-01 | 2028-03-01
A10 | MENA | 270T899 | Steam Turbine | 104739 | Minor Inspection | 500240 | 2029-10-01 | 2029-10-15
A10 | MENA | 270T900 | Steam Turbine | 105974 | Minor Inspection | 502418 | 2026-03-08 | 2026-03-15
A10 | MENA | 270T899 | Steam Turbine | 105975 | Minor Inspection | 502419 | 2026-08-08 | 2026-08-15
A10 | MENA | 270T902 | Steam Turbine | 155297 | Minor Inspection |  | 2030-08-31 | 2030-09-05
A10 | MENA | 270T901 | Steam Turbine | 155298 | Minor Inspection |  | 2030-06-30 | 2030-07-05
A10 | MENA | 270T905 | Steam Turbine | 155345 | Minor Inspection | 542941 | 2026-02-15 | 2026-05-15
A10 | MENA | 270T906 | Steam Turbine | 155348 | Minor Inspection | 543011 | 2027-02-01 | 2027-03-02
A10 | MENA | 270T904 | Steam Turbine | 159021 | Major Inspection (MI) |  | 2030-03-29 | 2030-04-26
A10 | MENA | 270T907 | Steam Turbine | 169860 | Minor Inspection | 546242 | 2027-10-15 | 2027-11-13
A10 | MENA | 270T908 | Steam Turbine | 169867 | Minor Inspection | 546246 | 2028-02-17 | 2028-03-17
A10 | MENA | 370T042 | Steam Turbine | 183899 | Minor Inspection |  | 2030-09-30 | 2030-10-05
A10 | MENA | 270T900 | Steam Turbine | 195659 | Minor Inspection |  | 2028-07-25 | 2028-07-30
A10 | MENA | 270T899 | Steam Turbine | 195660 | Minor Inspection |  | 2028-10-03 | 2028-10-08
A10 | MENA | 270T903 | Steam Turbine | 195730 | Minor Inspection |  | 2028-11-10 | 2028-11-15
A22 | Asia | 937294 | Generator | 156940 | Minor Inspection | 536612 | 2029-02-17 | 2029-02-26
A22 | Asia | 937289 | Generator | 166076 | Minor Inspection | 543392 | 2028-07-22 | 2028-07-31
A30 | Latin America | A3016001 | Generator | 165823 | Minor Inspection | 543229 | 2030-04-21 | 2030-05-19
A30 | Latin America | A3016002 | Generator | 165825 | Minor Inspection | 543230 | 2030-10-16 | 2030-10-30
A30 | Latin America | A3016001 | Generator | 176895 | Major Inspection (Rotor Out) |  | 2027-04-17 | 2027-05-06
A30 | Latin America | A3016001 | Generator | 176896 | Major Inspection (Rotor Out) | 539929 | 2027-01-11 | 2027-02-14
A30 | Latin America | A3016002 | Generator | 180665 | Major Inspection (Robotic) | 552686 | 2027-09-06 | 2027-10-08
A30 | Latin America | A3016003 | Generator | 180828 | Major Inspection (Robotic) | 552815 | 2028-02-02 | 2028-03-01
A33 | Asia | GG10714 | Generator | 153836 | Minor Inspection | 534517 | 2026-08-22 | 2026-09-04
A33 | Asia | GG10715 | Generator | 155229 | Minor Inspection | 535382 | 2027-01-01 | 2027-01-20
A33 | Asia | GG10524 | Generator | 156833 | Major Inspection (Robotic) | 536527 | 2027-10-01 | 2027-10-14
A33 | Asia | GG10525 | Generator | 156835 | Major Inspection (Robotic) | 536529 | 2027-10-18 | 2027-11-01
A33 | Latin America | GG10539 | Generator | 165417 | Major Inspection (Robotic) | 532097 | 2027-06-01 | 2027-06-29
A33 | Asia | GG10593 | Generator | 165650 | Major Inspection (Robotic) | 543123 | 2028-01-01 | 2028-01-14
A33 | Asia | GG10714 | Generator | 165708 | Minor Inspection | 543158 | 2026-06-26 | 2026-07-10
A33 | Asia | GG10715 | Generator | 165709 | Minor Inspection | 543159 | 2026-12-27 | 2027-01-10
A33 | Asia | GG10714 | Generator | 165710 | Major Inspection (Robotic) | 543160 | 2030-03-19 | 2030-04-16
A33 | Asia | GG10715 | Generator | 179302 | Major Inspection (Robotic) | 551902 | 2030-08-29 | 2030-09-26
A33 | Asia | GG10524 | Generator | 179449 | Major Inspection (Robotic) | 552017 | 2030-07-01 | 2030-07-26
A33 | Asia | GG10525 | Generator | 179450 | Major Inspection (Robotic) | 552018 | 2030-08-01 | 2030-08-26
A34 | Asia | GG10641 | Generator | 170844 | Major Inspection (Robotic) | 535000 | 2026-10-15 | 2026-11-10
A34 | Asia | GG10642 | Generator | 170845 | Major Inspection (Robotic) | 534999 | 2027-11-05 | 2027-12-03
A34 | Latin America | GG10687 | Generator | 185122 | Major Inspection (Robotic) | 547794 | 2028-07-18 | 2028-08-15
A34 | Latin America | A3416003 | Generator | 188808 | Major Inspection (Rotor Out) | 554347 | 2028-06-03 | 2028-07-07
A35 | Latin America | GG10574 | Generator | 131795 | Major Inspection (Robotic) | 502952 | 2027-05-03 | 2027-06-01
A35 | Latin America | GG10576 | Generator | 143481 | Major Inspection (Robotic) | 503020 | 2029-08-06 | 2029-09-04
A35 | Latin America | GG10576 | Generator | 165567 | Major Inspection (Robotic) | 543060 | 2027-10-09 | 2027-11-07
A35 | Latin America | GG10575 | Generator | 165568 | Minor Inspection | 543061 | 2030-08-05 | 2030-08-24
A35 | Europe | GG10805 | Generator | 166199 | Minor Inspection | 543469 | 2029-05-06 | 2029-06-03
A35 | Europe | GG10743 | Generator | 166468 | Minor Inspection | 543629 | 2028-08-24 | 2028-09-07
A35 | Europe | GG10744 | Generator | 166470 | Minor Inspection | 543630 | 2028-09-09 | 2028-09-28
A35 | NAM North America | GG10534 | Generator | 185930 | Major Inspection (Robotic) | 556099 | 2027-03-01 | 2027-03-29
A35 | NAM North America | GG10534 | Generator | 185932 | Major Inspection (Robotic) | 554281 | 2027-03-01 | 2027-03-29
A35 | Europe | GG10847 | Generator | 195784 | Minor Inspection | 558358 | 2030-03-03 | 2030-03-22
A35 | Europe | GG10846 | Generator | 195785 | Minor Inspection | 563072 | 2030-09-01 | 2030-09-20
A36 | Asia | A3618001 | Generator | 165719 | Major Inspection (Robotic) | 543164 | 2030-03-06 | 2030-04-03
A36 | Asia | A3618002 | Generator | 165722 | Major Inspection (Robotic) | 543165 | 2030-01-27 | 2030-02-24
A40 | Europe | BH1395907 | Generator | 173878 | Minor Inspection | 548587 | 2026-05-01 | 2026-06-16
A40 | Europe | BH1395907 | Generator | 190375 | Minor Inspection | 552691 | 2026-05-01 | 2026-06-16
A63 | MENA | GG10562 | Generator | 162687 | Major Inspection (Robotic) | 540965 | 2027-02-01 | 2027-02-28
A63 | MENA | GG10563 | Generator | 162688 | Major Inspection (Robotic) | 540966 | 2027-01-03 | 2027-01-30
A63 | MENA | GG10564 | Generator | 162690 | Major Inspection (Robotic) | 540967 | 2028-01-01 | 2028-01-26
A63 | MENA | GG10565 | Generator | 162693 | Major Inspection (Robotic) | 540968 | 2028-03-01 | 2028-03-26
A63 | Latin America | GG10813 | Generator | 176097 | Minor Inspection | 550044 | 2029-10-01 | 2029-10-20
A63 | Latin America | GG10814 | Generator | 176100 | Minor Inspection | 550045 | 2028-10-02 | 2028-10-21
A70 | NAM North America | SG10236 | Generator | 186978 | Major Inspection (Robotic) | 556779 | 2027-09-11 | 2027-10-14
A72 | Asia | 390T019 | Generator | 137694 | Minor Inspection | 524086 | 2026-06-05 | 2026-07-23
A72 | Asia | PL100203 | Generator | 175439 | Minor Inspection | 549607 | 2026-02-20 | 2026-04-05
A74 | Europe | PL100204 | Generator | 173876 | Minor Inspection | 548586 | 2026-05-01 | 2026-06-16
A74 | MENA | SG10254 | Generator | 179424 | Minor Inspection | 551992 | 2027-11-16 | 2027-12-10
A74 | MENA | SG10255 | Generator | 179425 | Minor Inspection | 551993 | 2028-11-15 | 2028-12-09
A74 | MENA | SG10253 | Generator | 179426 | Major Inspection (Robotic) | 551994 | 2028-12-19 | 2029-01-16
A74 | MENA | SG10253 | Generator | 180740 | Minor Inspection | 552762 | 2026-11-17 | 2026-12-11
A74 | MENA | SG10253 | Generator | 180741 | Minor Inspection | 552760 | 2026-11-17 | 2026-12-11
A74 | Latin America | SG10251 | Generator | 182007 | Major Inspection (Robotic) | 553480 | 2028-03-07 | 2028-04-04
A74 | Europe | PL100204 | Generator | 183315 | Minor Inspection | 548438 | 2026-05-01 | 2026-06-16
A74 | Europe | PL100204 | Generator | 183316 | Major Inspection (Robotic) | 554313 | 2029-12-29 | 2030-01-23
A74 | Europe | PM100202 | Generator | 183317 | Major Inspection (Robotic) | 554312 | 2029-05-03 | 2029-05-28
A78 | Asia | PL100182 | Generator | 136658 | Minor Inspection | 524084 | 2026-06-05 | 2026-07-10
A78 | Asia | GG10768 | Generator | 162263 | Minor Inspection | 540657 | 2029-09-01 | 2029-09-24
A78 | Asia | PL100202 | Generator | 176379 | Minor Inspection | 550221 | 2026-02-20 | 2026-04-05
A78 | MENA | SG10284 | Generator | 181323 | Minor Inspection | 552990 | 2027-12-02 | 2027-12-31
A201 | Europe | 942369 | Steam Turbine | 173241 | Major Inspection (MI) |  | 2029-05-03 | 2029-05-31
A201 | Europe | 942370 | Steam Turbine | 173877 | Minor Inspection | 548587 | 2026-05-01 | 2026-06-16
A201 | Europe | 942369 | Steam Turbine | 180167 | Large Call-Out | 552400 | 2026-09-20 | 2026-09-30
A201 | Europe | 942370 | Steam Turbine | 180675 | Minor Inspection | 552691 | 2026-05-01 | 2026-06-24
A201 | Latin America | 370T017 | Steam Turbine | 180830 | Major Inspection (MI) | 554347 | 2028-06-03 | 2028-07-07
A201 | Europe | 942370 | Steam Turbine | 183314 | Major Inspection (MI) |  | 2029-12-29 | 2030-01-26
A451 | NAM North America | 270T981 | Steam Turbine | 145251 | Major Inspection (MI) | 556779 | 2027-09-11 | 2027-10-14
A451 | NAM North America | 270T980 | Steam Turbine | 145253 | Major Inspection (MI) |  | 2028-04-25 | 2028-05-23
A451 | NAM North America | 270T982 | Steam Turbine | 146742 | Major Inspection (MI) |  | 2026-10-01 | 2026-10-29
A650 | NAM North America | 270T951 | Steam Turbine | 106687 | Major Inspection (MI) | 503060 | 2026-09-12 | 2026-12-08
A650 | Asia | 370T019 | Steam Turbine | 136660 | Minor Inspection | 524086 | 2026-06-05 | 2026-08-17
A650 | NAM North America | 270T952 | Steam Turbine | 144965 | Major Inspection (MI) | 556796 | 2027-03-01 | 2027-03-30
A650 | NAM North America | 270T960 | Steam Turbine | 146758 | Major Inspection (MI) | 535740 | 2026-03-16 | 2026-05-28
A650 | NAM North America | 270T959 | Steam Turbine | 146762 | Minor Inspection | 550718 | 2028-03-06 | 2028-03-31
A650 | NAM North America | 270T960 | Steam Turbine | 146765 | Minor Inspection | 550720 | 2029-03-19 | 2029-04-13
A650 | NAM North America | 270T994 | Steam Turbine | 146812 | Minor Inspection | 552796 | 2027-10-01 | 2027-10-31
A650 | NAM North America | 270T995 | Steam Turbine | 146815 | Minor Inspection | 559294 | 2026-10-01 | 2026-10-30
A650 | NAM North America | 270T996 | Steam Turbine | 146816 | Minor Inspection | 561808 | 2027-04-01 | 2027-05-01
A650 | NAM North America | 370T095 | Steam Turbine | 151266 | Minor Inspection | 559446 | 2030-02-18 | 2030-03-17
A650 | Latin America | 370T105 | Steam Turbine | 154756 | Minor Inspection | 538394 | 2030-05-14 | 2030-05-19
A650 | NAM North America | 270T971 | Steam Turbine | 169081 | Major Inspection (MI) | 545806 | 2027-03-20 | 2027-05-18
A650 | Asia | 370T019 | Steam Turbine | 169214 | Major Inspection (MI) |  | 2030-01-11 | 2030-02-08
A650 | Asia | 370T040 | Steam Turbine | 175438 | Minor Inspection | 549607 | 2026-02-21 | 2026-04-18
A650 | NAM North America | 270T961 | Steam Turbine | 176141 | Minor Inspection | 555753 | 2028-09-11 | 2028-10-06
A650 | NAM North America | 270T959 | Steam Turbine | 176142 | Major Inspection (MI) |  | 2030-09-02 | 2030-11-27
A650 | Asia | 370T040 | Steam Turbine | 183293 | Major Inspection (MI) |  | 2030-03-04 | 2030-04-01
A650 | NAM North America | 270T956 | Steam Turbine | 183467 | Major Inspection (MI) | 554406 | 2026-03-03 | 2026-05-08
A650 | NAM North America | 370T067 | Steam Turbine | 195748 | Minor Inspection | 563102 | 2027-09-25 | 2027-10-24
A650 | NAM North America | 370T068 | Steam Turbine | 195749 | Minor Inspection | 563103 | 2027-10-23 | 2027-11-21
AIR-COOLED | Asia | 821601 | Generator | 168352 | Minor Inspection | 525142 | 2026-01-15 | 2026-02-04
AIR-COOLED | Europe | 43561 | Generator | 177457 | Major Inspection (Stator Rewind) | 550917 | 2028-06-19 | 2028-11-06
AIR-COOLED | Asia | 821601 | Generator | 179244 | Major Inspection (Robotic) | 551860 | 2030-03-19 | 2030-04-16
BDAX 7 | Europe | 341X926 | Generator | 137391 | Major Inspection (Robotic) | 524633 | 2026-10-01 | 2026-10-30
BDAX 7 | Asia | 341X943 | Generator | 138985 | Major Inspection (Rotor Out) | 525477 | 2027-03-22 | 2027-04-20
BDAX 7 | NAM North America | 341X962 | Generator | 148004 | Major Inspection (Rotor Out) | 530495 | 2028-09-06 | 2028-10-04
BDAX 7 | Asia | 341X944 | Generator | 155979 | Major Inspection (Rotor Out) | 535869 | 2026-07-18 | 2026-08-17
BDAX 7 | Europe | 341X969 | Generator | 166476 | Major Inspection (Rotor Out) | 536896 | 2027-02-28 | 2027-03-31
BDAX 7 | Europe | 341X968 | Generator | 166477 | Major Inspection (Robotic) | 536894 | 2027-04-01 | 2027-04-30
BDAX 7 | Latin America | 341X901 | Generator | 178704 | Major Inspection (Rotor Out) | 551496 | 2026-03-05 | 2026-04-09
BDAX 7 | Europe | 341X911 | Generator | 179434 | Major Inspection (Robotic) | 552001 | 2027-10-27 | 2027-11-24
BDAX 7 | Latin America | 341X900 | Generator | 181467 | Major Inspection (Rotor Out) | 553093 | 2027-02-01 | 2027-03-08
BDAX 7 | Europe | 341X911 | Generator | 186797 | Major Inspection (Robotic) | 556674 | 2028-05-15 | 2028-06-14
BDAX 7 | Europe | 341X911 | Generator | 188025 | Major Inspection (Robotic) | 557468 | 2027-05-18 | 2027-06-17
BDAX 7 | Latin America | 341X910 | Generator | 192933 | Major Inspection (Robotic) | 508232 | 2028-02-01 | 2028-03-10
BDAX 7 | Latin America | 341X964 | Generator | 194954 | Major Inspection (Rotor Out) | 562541 | 2028-01-19 | 2028-02-02
BDAX 7 | Latin America | 341X963 | Generator | 194955 | Major Inspection (Rotor Out) | 562542 | 2028-10-15 | 2028-10-29
BDAX 8 | NAM North America | 338X963 | Generator | 121930 | Major Inspection (Rotor Out) | 505716 | 2026-02-17 | 2026-03-20
BDAX 8 | NAM North America | 339X938 | Generator | 170532 | Major Inspection (Rotor Out) | 546732 | 2026-03-25 | 2026-04-28
BDAX 8 | NAM North America | 290T920 | Generator | 190846 | Minor Inspection | 559477 | 2027-05-01 | 2027-05-15
BDAX 8 | NAM North America | 290T920 | Generator | 190847 | Minor Inspection | 558119 | 2027-03-12 | 2027-03-28
BDAX 9 | MENA | 340X950 | Generator | 106233 | Major Inspection (Rotor Out) | 502392 | 2027-01-21 | 2027-03-06
BDAX 9 | SSA | 340X930 | Generator | 139100 | Minor Inspection | 501143 | 2026-09-01 | 2026-10-31
BDAX 9 | SSA | 340X922 | Generator | 139107 | Minor Inspection | 501135 | 2027-06-01 | 2027-06-24
BDAX 9 | SSA | 340X921 | Generator | 139110 | Minor Inspection | 501138 | 2027-03-01 | 2027-03-31
BDAX 9 | SSA | 340X923 | Generator | 141609 | Major Inspection (Rotor Out) | 526897 | 2029-12-01 | 2029-12-30
BDAX 9 | MENA | 811185 | Generator | 149751 | Major Inspection (Rotor Out) | 531663 | 2027-11-05 | 2027-12-04
BDAX 9 | MENA | 340X951 | Generator | 165040 | Minor Inspection | 542781 | 2028-11-03 | 2028-11-19
BDAX 9 | Latin America | 340X975 | Generator | 166380 | Major Inspection (Robotic) | 543572 | 2026-08-04 | 2026-09-11
BDAX 9 | Latin America | 340X975 | Generator | 166386 | Minor Inspection | 543573 | 2030-01-26 | 2030-02-09
BDAX 9 | MENA | 811187 | Generator | 170438 | Major Inspection (Rotor Out) | 546652 | 2029-03-01 | 2029-03-31
BDAX 9 | MENA | 340X950 | Generator | 192784 | Major Inspection (Robotic) | 560748 | 2026-03-31 | 2026-04-28
C7 | MENA | 270T919 | Steam Turbine | 141863 | Minor Inspection | 553075 | 2028-07-24 | 2028-07-29
C7 | MENA | 270T918 | Steam Turbine | 141867 | Minor Inspection | 552672 | 2028-10-29 | 2028-11-03
C7 | MENA | 270T989 | Steam Turbine | 141870 | Minor Inspection | 552827 | 2028-11-29 | 2028-12-04
C7 | MENA | 270T990 | Steam Turbine | 168110 | Minor Inspection | 552828 | 2029-03-24 | 2029-03-29
CC2P2C2F32 | Latin America | 818613 | Steam Turbine | 159700 | Major Inspection (MI) | 539739 | 2027-06-15 | 2027-08-12
CC2P2C2F32 | Latin America | 818615 | Steam Turbine | 165261 | Major Inspection (MI) | 542907 | 2027-10-27 | 2027-11-24
CC2P2C2F32 | Latin America | 818615 | Steam Turbine | 191107 | Large Call-Out | 559668 | 2026-02-23 | 2026-04-09
D11 | Latin America | 270T870 | Steam Turbine | 136120 | Major Inspection (MI) | 523664 | 2026-04-22 | 2026-06-06
D11 | Europe | 270T845 | Steam Turbine | 145248 | Major Inspection (MI) | 544100 | 2028-08-01 | 2028-09-30
D11 | Latin America | 270T917 | Steam Turbine | 146638 | Minor Inspection | 537178 | 2026-10-19 | 2026-11-04
D11 | Latin America | 270T917 | Steam Turbine | 146642 | Major Inspection (MI) |  | 2029-10-06 | 2029-11-06
D11 | Asia | 270T831 | Steam Turbine | 155160 | Minor Inspection | 552619 | 2029-06-27 | 2029-07-02
D202 | MENA | 370T061 | Steam Turbine | 170815 | Minor Inspection | 546782 | 2026-10-03 | 2026-10-18
D202 | MENA | 370T062 | Steam Turbine | 172588 | Minor Inspection |  | 2026-07-01 | 2026-07-06
D202 | MENA | 370T086 | Steam Turbine | 181312 | Minor Inspection | 552990 | 2027-12-02 | 2027-12-31
D602 | NAM North America | 270T943 | Steam Turbine | 106730 | Minor Inspection | 503103 | 2028-07-13 | 2028-07-18
D602 | NAM North America | 370T055 | Steam Turbine | 146850 | Minor Inspection | 552378 | 2027-03-08 | 2027-04-08
D602 | NAM North America | 270T932 | Steam Turbine | 162210 | Major Inspection (MI) | 540605 | 2028-01-30 | 2028-03-29
D602 | NAM North America | 270T933 | Steam Turbine | 162211 | Major Inspection (MI) | 540607 | 2027-11-27 | 2028-01-02
D602 | NAM North America | 270T941 | Steam Turbine | 167737 | Major Inspection (MI) | 544680 | 2028-03-06 | 2028-04-15
D602 | NAM North America | 270T983 | Steam Turbine | 167895 | Major Inspection (MI) | 544877 | 2028-04-03 | 2028-05-30
D602 | Latin America | 370T089 | Steam Turbine | 176099 | Minor Inspection |  | 2029-06-08 | 2029-06-30
D602 | NAM North America | 370T110 | Steam Turbine | 194906 | Minor Inspection |  | 2030-09-02 | 2030-09-07
D650 | Europe | 370T097 | Steam Turbine | 159116 | Minor Inspection | 538215 | 2030-09-04 | 2030-09-18
D650 | Asia | 370T094 | Steam Turbine | 175559 | Minor Inspection | 549691 | 2029-08-07 | 2029-09-09
D650 | Asia | 370T093 | Steam Turbine | 176996 | Minor Inspection | 550626 | 2029-06-26 | 2029-07-29
D650 | Asia | 370T094 | Steam Turbine | 176997 | Minor Inspection | 550627 | 2029-04-01 | 2029-05-04
D652 | Latin America | 370T025 | Steam Turbine | 146704 | Major Inspection (MI) | 534055 | 2026-01-11 | 2026-02-14
D652 | NAM North America | 370T057 | Steam Turbine | 146706 | Minor Inspection | 550941 | 2027-10-24 | 2027-11-24
D652 | Asia | 370T045 | Steam Turbine | 146734 | Minor Inspection | 550764 | 2028-07-01 | 2028-07-27
D652 | Asia | 370T044 | Steam Turbine | 146735 | Minor Inspection | 551669 | 2028-12-01 | 2028-12-27
D652 | NAM North America | 370T046 | Steam Turbine | 146855 | Major Inspection (MI) |  | 2029-05-31 | 2029-06-28
D652 | NAM North America | 370T016 | Steam Turbine | 146864 | Major Inspection (MI) | 550321 | 2027-09-13 | 2027-11-14
D652 | MENA | 370T037 | Steam Turbine | 146865 | Minor Inspection | 551992 | 2027-11-16 | 2027-12-10
D652 | MENA | 370T038 | Steam Turbine | 146868 | Minor Inspection | 551993 | 2028-11-15 | 2028-12-09
D652 | MENA | 370T036 | Steam Turbine | 146872 | Major Inspection (MI) | 551994 | 2028-12-19 | 2029-01-16
D652 | NAM North America | 370T041 | Steam Turbine | 146896 | Minor Inspection | 543998 | 2026-03-09 | 2026-04-10
D652 | Europe | 370T058 | Steam Turbine | 147052 | Minor Inspection | 556905 | 2028-03-20 | 2028-03-25
D652 | NAM North America | 370T057 | Steam Turbine | 154364 | Borescope Inspection (BI) | 534766 | 2026-03-14 | 2026-03-31
D652 | Latin America | 370T034 | Steam Turbine | 154422 | Major Inspection (MI) | 553480 | 2028-03-07 | 2028-04-04
D652 | Latin America | 370T027 | Steam Turbine | 162581 | Major Inspection (MI) | 544936 | 2028-11-04 | 2028-12-07
D652 | Latin America | 370T025 | Steam Turbine | 162588 | Minor Inspection | 556897 | 2029-01-14 | 2029-02-06
D652 | NAM North America | 370T041 | Steam Turbine | 163046 | Major Inspection (MI) | 541177 | 2030-05-14 | 2030-06-11
D652 | NAM North America | 370T048 | Steam Turbine | 163105 | Major Inspection (MI) | 562232 | 2029-09-01 | 2029-10-26
D652 | NAM North America | 370T047 | Steam Turbine | 163108 | Major Inspection (MI) | 562234 | 2029-03-01 | 2029-05-04
D652 | Latin America | 370T025 | Steam Turbine | 167316 | Large Call-Out | 544324 | 2026-01-10 | 2026-02-12
D652 | Europe | 370T080 | Steam Turbine | 175772 | Minor Inspection |  | 2030-03-03 | 2030-03-08
D652 | Latin America | 370T026 | Steam Turbine | 176088 | Minor Inspection | 554368 | 2028-01-28 | 2028-02-02
D652 | MENA | 370T037 | Steam Turbine | 176174 | Major Inspection (MI) |  | 2029-12-08 | 2030-01-05
D652 | MENA | 370T038 | Steam Turbine | 176176 | Major Inspection (MI) |  | 2030-11-14 | 2030-12-12
D652 | NAM North America | 370T057 | Steam Turbine | 177476 | Minor Inspection | 550939 | 2027-03-12 | 2027-04-15
D652 | MENA | 370T036 | Steam Turbine | 180738 | Minor Inspection | 552760 | 2026-11-17 | 2026-12-11
D652 | NAM North America | 370T057 | Steam Turbine | 183688 | Stand Alone Large Upgrade | 554526 | 2027-10-24 | 2027-11-22
D652 | Asia | 370T029 | Steam Turbine | 186914 | Major Inspection (MI) | 556740 | 2027-10-09 | 2027-12-20
D652 | Asia | 370T030 | Steam Turbine | 186915 | Major Inspection (MI) | 556741 | 2027-07-03 | 2027-08-14
D652 | Asia | 370T031 | Steam Turbine | 186916 | Major Inspection (MI) | 556742 | 2027-08-14 | 2027-09-25
D652 | Latin America | 370T025 | Steam Turbine | 187124 | Minor Inspection | 556898 | 2029-01-14 | 2029-02-06
D652 | Europe | 370T065 | Steam Turbine | 187378 | Minor Inspection |  | 2029-08-14 | 2029-09-10
D652 | Europe | 370T066 | Steam Turbine | 187379 | Minor Inspection |  | 2029-09-30 | 2029-10-27
D652 | Europe | 370T054 | Steam Turbine | 188351 | Minor Inspection | 557687 | 2028-04-02 | 2028-04-28
D652 | Europe | 370T060 | Steam Turbine | 188366 | Minor Inspection | 557935 | 2029-05-06 | 2029-06-07
D652 | Europe | 370T054 | Steam Turbine | 189204 | Minor Inspection |  | 2028-04-16 | 2028-04-21
D652 | Europe | 370T060 | Steam Turbine | 189205 | Minor Inspection |  | 2028-10-23 | 2028-10-28
D654 | Latin America | 370T013 | Steam Turbine | 184631 | Minor Inspection |  | 2030-03-04 | 2030-03-29
DG | Asia | 980002 | Generator | 162789 | Major Inspection (Rotor Out) | 541039 | 2027-10-10 | 2027-10-28
DG | Asia | 930735 | Generator | 162790 | Major Inspection (Rotor Out) | 541040 | 2028-09-05 | 2028-09-23
DG | Asia | 930483 | Generator | 162791 | Major Inspection (Rotor Out) | 541041 | 2028-10-02 | 2028-10-20
DG | Asia | 934702 | Generator | 186385 | Minor Inspection | 556439 | 2030-12-02 | 2030-12-12
DG | Asia | 934701 | Generator | 186387 | Minor Inspection | 556440 | 2028-11-02 | 2028-11-12
DG | Asia | 934698 | Generator | 186390 | Minor Inspection | 556441 | 2029-01-02 | 2029-01-12
DG | Asia | 934702 | Generator | 186394 | Minor Inspection | 556448 | 2028-05-07 | 2028-05-21
DG | Asia | 934701 | Generator | 186398 | Minor Inspection | 556449 | 2028-08-06 | 2028-08-20
DG | Asia | 934698 | Generator | 186404 | Minor Inspection | 556450 | 2028-11-05 | 2028-11-19
DG | Asia | 934703 | Generator | 186408 | Major Inspection (Robotic) | 556451 | 2030-11-11 | 2030-12-09
DG | Asia | 934700 | Generator | 186463 | Minor Inspection | 556483 | 2027-10-02 | 2027-10-12
DG | Asia | 934703 | Generator | 186464 | Minor Inspection | 556484 | 2028-05-02 | 2028-05-12
DG | Asia | 934699 | Generator | 186467 | Minor Inspection | 556485 | 2028-07-02 | 2028-07-12
DKE1-1N34B | NAM North America | 811118 | Steam Turbine | 159232 | Minor Inspection | 549636 | 2027-03-19 | 2027-04-13
DKE1-1N34B | NAM North America | 811118 | Steam Turbine | 159237 | Major Inspection (MI) | 549638 | 2030-03-02 | 2030-04-30
DKYZ2-1N33A | Europe |  | Steam Turbine | 152811 | Major Inspection (MI) | 533737 | 2026-10-15 | 2026-11-18
DKYZ2-1N33A | Europe |  | Steam Turbine | 181874 | Major Inspection (MI) | 553371 | 2028-03-01 | 2028-04-04
DKYZ2-1N34B | Latin America | ST2403 | Steam Turbine | 167868 | Minor Inspection | 544801 | 2028-08-19 | 2028-09-18
DKYZ2-1N34B | Latin America | ST2403 | Steam Turbine | 183659 | Major Inspection (MI) |  | 2029-12-06 | 2030-01-03
DKYZ2-1N41A | Europe | 818383 | Steam Turbine | 135796 | Minor Inspection | 523434 | 2027-03-12 | 2027-05-08
DKYZ2-1N41B | MENA | 30-0139-41103 | Steam Turbine | 103957 | Major Inspection (MI) | 500265 | 2027-02-07 | 2027-04-07
DKYZ2-1N41B | MENA | 30-0137-41103 | Steam Turbine | 104351 | Major Inspection (MI) | 500260 | 2026-02-01 | 2026-04-01
DKYZ2-1N41B | Europe | V2-0046 | Steam Turbine | 109253 | Major Inspection (MI) | 514583 | 2028-10-16 | 2028-11-23
DKYZ2-1N41B | Asia | 30-0091 | Steam Turbine | 138360 | Major Inspection (MI) | 525092 | 2026-07-19 | 2026-08-17
DKYZ2-1N41B | MENA | GM002353 | Steam Turbine | 151397 | Minor Inspection | 547636 | 2029-01-15 | 2029-02-07
DKYZ2-1N41B | MENA | 30-0138-41103 | Steam Turbine | 153491 | Major Inspection (MI) | 534269 | 2026-02-08 | 2026-05-10
DKYZ2-1N41B | MENA | 30-0137-41103 | Steam Turbine | 153871 | Major Inspection (MI) | 534531 | 2026-10-20 | 2026-12-18
DKYZ2-1N41B | MENA | 30-0138-41103 | Steam Turbine | 153874 | Minor Inspection | 534532 | 2029-09-30 | 2029-10-28
DKYZ2-1N41B | MENA | 30-0139-41103 | Steam Turbine | 153879 | Major Inspection (MI) | 534535 | 2027-10-20 | 2027-12-18
DKYZ2-1N41B | MENA | 30-0137-41103 | Steam Turbine | 155712 | Minor Inspection | 535724 | 2030-01-02 | 2030-03-02
DKYZ2-1N41B | Europe | 30-126 | Steam Turbine | 157650 | Major Inspection (MI) | 537351 | 2030-04-06 | 2030-07-25
DKYZ2-1N41B | Europe | ST2643 | Steam Turbine | 157651 | Major Inspection (MI) | 537352 | 2029-07-07 | 2029-10-25
DKYZ2-1N41B | Europe | ST2648 | Steam Turbine | 157652 | Major Inspection (MI) | 537353 | 2028-07-15 | 2028-11-02
DKYZ2-1N41B | Europe | ST2642 | Steam Turbine | 157653 | Major Inspection (MI) | 537354 | 2029-03-03 | 2029-06-21
DKYZ2-1N41B | MENA | GM002352 | Steam Turbine | 163222 | Minor Inspection | 560527 | 2029-10-01 | 2029-10-24
DKYZ2-1N41B | MENA | GM002352 | Steam Turbine | 167589 | Stand Alone Small Upgrade | 544567 | 2026-09-15 | 2026-12-06
DKYZ2-1N41B | MENA | GM002353 | Steam Turbine | 167590 | Stand Alone Small Upgrade | 544568 | 2026-11-05 | 2027-01-31
DKYZ2-1N41B | Asia | ST2674 | Steam Turbine | 169464 | Major Inspection (MI) | 546044 | 2028-01-26 | 2028-02-20
DKYZ2-1N41B | Asia | 30-0096 | Steam Turbine | 169989 | Minor Inspection | 546363 | 2027-03-01 | 2027-03-08
DKYZ2-1N41B | Europe | V2-0047 | Steam Turbine | 175227 | Minor Inspection | 549462 | 2028-08-14 | 2028-09-27
DKYZ2-1N41B | Europe | V2-0027 | Steam Turbine | 176715 | Minor Inspection | 550466 | 2029-01-14 | 2029-03-03
DKYZ2-1N41B | Asia | ST2674 | Steam Turbine | 177014 | Major Inspection (MI) | 550637 | 2028-01-26 | 2028-02-20
DKYZ2-1N41B | MENA | 30-0128 | Steam Turbine | 178974 | Minor Inspection | 551769 | 2028-02-01 | 2028-02-26
DKYZ2-1N41B | MENA | 30-0128 | Steam Turbine | 179452 | Major Inspection (MI) |  | 2029-06-14 | 2029-07-12
DKYZ2-1N41B | Europe | ST2643 | Steam Turbine | 179755 | Major Inspection (MI) |  | 2027-09-29 | 2027-10-27
DKYZ2-1N41B | Europe | V2-0028 | Steam Turbine | 182103 | Minor Inspection | 554141 | 2029-10-08 | 2029-10-31
DKYZ2-1N41B | Asia | 30-0144 | Steam Turbine | 190724 | Minor Inspection | 559375 | 2029-03-03 | 2029-04-02
DKYZ3-2N41A | Europe | 814915 | Steam Turbine | 190893 | Major Inspection (MI) | 559491 | 2029-04-02 | 2029-05-31
DKYZ3-2N41B | Europe | V2-0016 | Steam Turbine | 138706 | Major Inspection (MI) | 525251 | 2027-08-20 | 2027-10-14
DKYZ3-2N41B | Europe | V2-0048 | Steam Turbine | 144156 | Major Inspection (MI) | 528368 | 2026-06-12 | 2026-10-27
DKYZ3-2N41B | Europe | 30-0117 | Steam Turbine | 148665 | Major Inspection (MI) | 538512 | 2026-08-23 | 2026-11-18
DKYZ3-2N41B | Europe | 30-0116 | Steam Turbine | 148672 | Minor Inspection | 557242 | 2028-04-07 | 2028-06-05
DKYZ3-2N41B | Europe | 30-0115 | Steam Turbine | 148678 | Minor Inspection |  | 2027-05-07 | 2027-07-05
DKYZ3-2N41B | Europe | V2-0016 | Steam Turbine | 149763 | Borescope Inspection (BI) |  | 2026-11-01 | 2026-11-05
DKYZ3-2N41B | Europe | 30-0133 | Steam Turbine | 169110 | Major Inspection (MI) | 556699 | 2030-07-06 | 2030-10-24
DKYZ3-2N41B | Europe | 30-0134 | Steam Turbine | 169111 | Major Inspection (MI) | 556698 | 2028-07-15 | 2028-11-02
DKYZ3-2N41B | Europe | 30-0135 | Steam Turbine | 169112 | Major Inspection (MI) | 562059 | 2028-03-04 | 2028-06-22
DKYZ3-2N41B | Europe | 30-0136 | Steam Turbine | 169113 | Major Inspection (MI) | 556700 | 2030-03-08 | 2030-06-26
DKYZ3-2N41B | Europe | 30-0141 | Steam Turbine | 169114 | Major Inspection (MI) | 556701 | 2029-04-07 | 2029-07-26
DKYZ3-2N41B | Europe | GM02315 | Steam Turbine | 177456 | Major Inspection (MI) | 550917 | 2028-06-19 | 2028-11-06
DKYZ3-2N41B | Europe | 30-0117 | Steam Turbine | 180446 | Major Inspection (MI) | 552536 | 2027-07-05 | 2027-09-30
DKYZ3-2N41B | Europe | 30-0115 | Steam Turbine | 180527 | Major Inspection (MI) | 557241 | 2027-07-30 | 2027-10-28
DKYZ3-2N41B | Europe | V2-0016 | Steam Turbine | 190573 | Large Call-Out |  | 2029-04-15 | 2029-08-15
DKYZ3-2N41B | Europe | 30-0136 | Steam Turbine | 195755 | Major Inspection (MI) |  | 2029-01-15 | 2029-02-12
DKYZXC2-1N20B | NAM North America | V2-0032 | Steam Turbine | 185103 | Major Inspection (MI) |  | 2029-10-05 | 2029-11-05
DKYZXC2-1N20B | NAM North America | V2-0031 | Steam Turbine | 185108 | Major Inspection (MI) |  | 2029-10-02 | 2029-11-02
DKYZXC2-1N24 | NAM North America | V2-0013 | Steam Turbine | 185085 | Major Inspection (MI) |  | 2029-04-13 | 2029-05-12
DKYZXC2-1N24 | NAM North America | V2-0040 | Steam Turbine | 185127 | Minor Inspection |  | 2029-03-09 | 2029-03-23
DKYZXC2-1N24 | NAM North America | V2-0012 | Steam Turbine | 185131 | Minor Inspection |  | 2029-03-05 | 2029-03-19
DKYZXC2-1N24 | NAM North America | V2-0011 | Steam Turbine | 185135 | Minor Inspection |  | 2030-03-04 | 2030-03-18
DKYZXC2-1N24 | NAM North America | V2-0013 | Steam Turbine | 196374 | Large Call-Out |  | 2026-10-17 | 2026-10-30
DKYZXC2-1N34B | Latin America | V2-0057 | Steam Turbine | 109154 | Minor Inspection | 514618 | 2026-01-18 | 2026-02-23
DKYZXC2-1N34B | Latin America | V2-0055 | Steam Turbine | 167696 | Minor Inspection | 544646 | 2026-12-06 | 2027-01-17
DKYZXC2-1N34B | Latin America | V2-0056 | Steam Turbine | 167698 | Major Inspection (MI) | 544647 | 2027-01-10 | 2027-02-13
DKYZXC2-1N34B | Latin America | V2-0057 | Steam Turbine | 167857 | Major Inspection (MI) | 544791 | 2028-10-01 | 2028-10-30
DKYZXC2-1N34B | Latin America | V2-0055 | Steam Turbine | 167860 | Major Inspection (MI) | 544794 | 2030-01-13 | 2030-02-16
DKYZXC2-1N34B | Latin America | V2-0022 | Steam Turbine | 183603 | Minor Inspection | 555032 | 2027-11-01 | 2027-11-29
DKYZXC2-1N34B | NAM North America | V2-0033 | Steam Turbine | 185096 | Major Inspection (MI) | 555487 | 2029-04-13 | 2029-05-27
DKYZXC2-1N34B | NAM North America | V2-0034 | Steam Turbine | 185137 | Major Inspection (MI) |  | 2029-04-03 | 2029-05-03
DKYZZ2-1N41B | Europe | 30-0088 | Steam Turbine | 165282 | Major Inspection (MI) | 542893 | 2028-05-08 | 2028-06-18
DKYZZ2-1N41B | Europe | 30-0083 | Steam Turbine | 165283 | Major Inspection (MI) | 542894 | 2027-04-26 | 2027-06-06
DKYZZ2-1N41B | Asia | V2-0025 | Steam Turbine | 169468 | Major Inspection (MI) | 546045 | 2029-04-01 | 2029-04-30
DKYZZ2-1N41B | Europe | 30-0087 | Steam Turbine | 176828 | Major Inspection (MI) | 560115 | 2029-05-07 | 2029-06-16
DKYZZ2-1N41B | Europe | 30-0083 | Steam Turbine | 182097 | Major Inspection (MI) | 554128 | 2027-04-26 | 2027-06-06
DKYZZ2-1N41B | Europe | 30-0087 | Steam Turbine | 191369 | Minor Inspection | 559870 | 2027-03-22 | 2027-04-12
DKYZZ2-1N41B | Europe | 30-0083 | Steam Turbine | 191770 | Minor Inspection | 560117 | 2029-04-02 | 2029-04-23
DKYZZ2-1N41B | Europe | 30-0088 | Steam Turbine | 191807 | Major Inspection (MI) | 560131 | 2028-05-22 | 2028-06-25
DKYZZ2-1N41B | Europe | 30-0088 | Steam Turbine | 192923 | Minor Inspection | 560835 | 2027-02-22 | 2027-03-15
DKYZZ2-1N41B | Asia | V2-0025 | Steam Turbine | 196030 | Large Call-Out | 563340 | 2027-04-16 | 2027-05-30
DKYZZ3-2N33A | Europe | GM00338 | Steam Turbine | 175345 | Major Inspection (MI) | 549556 | 2027-02-20 | 2027-04-17
DKYZZ3-2N34B | NAM North America | GM02239 | Steam Turbine | 147546 | Major Inspection (MI) |  | 2026-07-04 | 2026-08-01
DKYZZ3-2N34B | Latin America | 811298 | Steam Turbine | 158144 | Major Inspection (MI) | 544404 | 2027-03-01 | 2027-04-14
DKYZZ3-2N34B | NAM North America | GM02239 | Steam Turbine | 177939 | Major Inspection (MI) | 551239 | 2027-04-15 | 2027-05-12
DKYZZ3-2N34B | NAM North America | 810937 | Steam Turbine | 182791 | Major Inspection (MI) | 553949 | 2026-11-01 | 2026-11-14
DKYZZ3-2N34B | NAM North America | 810939 | Steam Turbine | 182792 | Major Inspection (MI) | 553950 | 2027-03-01 | 2027-03-14
DKYZZ3-2N34B | Latin America | 811298 | Steam Turbine | 184540 | Major Inspection (MI) | 555096 | 2027-03-01 | 2027-04-14
DKZ1-1N41B | Latin America | S2-6105 | Steam Turbine | 194324 | Major Inspection (MI) | 561975 | 2026-10-05 | 2026-11-04
DKZ2-2N34A | NAM North America | 2600230 | Steam Turbine | 148318 | Minor Inspection | 530701 | 2026-10-20 | 2026-11-07
DKZ3-4N34B | Latin America | 30-0112 | Steam Turbine | 118057 | Major Inspection (MI) | 513719 | 2027-07-07 | 2027-08-05
DKZ3-4N34B | Latin America | 30-0112 | Steam Turbine | 183512 | Major Inspection (MI) |  | 2030-07-03 | 2030-07-31
GRT45M100(4Noz) | NAM North America | 939149 | Steam Turbine | 191968 | Major Inspection (MI) | 560236 | 2027-09-20 | 2027-10-10
GT11N | NAM North America | 803771 | Gas Turbine | 142736 | C Inspection | 527428 | 2026-11-01 | 2026-12-06
GT11N | NAM North America | 803768 | Gas Turbine | 142739 | A Inspection | 527430 | 2026-03-11 | 2026-03-14
GT11N | NAM North America | 803768 | Gas Turbine | 142740 | C Inspection | 527429 | 2027-04-01 | 2027-05-03
GT11N | NAM North America | 803772 | Gas Turbine | 147680 | B Inspection | 530298 | 2027-03-01 | 2027-03-04
GT11N | NAM North America | 803772 | Gas Turbine | 147681 | A Inspection | 530299 | 2028-09-09 | 2028-09-13
GT11N | NAM North America | 803772 | Gas Turbine | 147682 | C Inspection | 530300 | 2029-11-03 | 2029-12-03
GT11N | NAM North America | 803772 | Gas Turbine | 147683 | A Inspection | 530301 | 2030-02-09 | 2030-02-13
GT11N | NAM North America | 803771 | Gas Turbine | 147684 | A Inspection | 530302 | 2026-03-07 | 2026-03-10
GT11N | NAM North America | 803771 | Gas Turbine | 147685 | B Inspection | 530303 | 2028-05-13 | 2028-05-17
GT11N | NAM North America | 803771 | Gas Turbine | 147686 | A Inspection | 530304 | 2029-09-15 | 2029-09-19
GT11N | NAM North America | 803771 | Gas Turbine | 147687 | C Inspection | 530305 | 2030-11-02 | 2030-12-02
GT11N | NAM North America | 803768 | Gas Turbine | 147688 | A Inspection | 530306 | 2028-01-08 | 2028-01-12
GT11N | NAM North America | 803768 | Gas Turbine | 147689 | B Inspection | 530307 | 2029-05-05 | 2029-05-09
GT11N | NAM North America | 803768 | Gas Turbine | 147690 | A Inspection | 530308 | 2030-09-14 | 2030-09-18
GT11N | NAM North America | 803769 | Gas Turbine | 153420 | C Inspection | 534189 | 2026-02-15 | 2026-03-17
GT11N | NAM North America | 810882 | Gas Turbine | 160143 | C Inspection | 538844 | 2026-04-20 | 2026-05-20
GT11N | NAM North America | 810884 | Gas Turbine | 160156 | C Inspection | 538847 | 2026-02-23 | 2026-03-27
GT11N | NAM North America | 810885 | Gas Turbine | 160158 | C Inspection | 538850 | 2026-11-02 | 2026-12-03
GT11N | NAM North America | 810880 | Gas Turbine | 160159 | C Inspection | 538852 | 2027-02-01 | 2027-03-03
GT11N | NAM North America | 803770 | Gas Turbine | 169244 | C Inspection | 545911 | 2027-02-21 | 2027-03-27
GT11N | NAM North America | 803769 | Gas Turbine | 169246 | C Inspection | 545913 | 2028-02-20 | 2028-03-25
GT11N | NAM North America | 803770 | Gas Turbine | 169249 | B Inspection | 545914 | 2026-02-24 | 2026-02-28
GT11N | NAM North America | 803769 | Gas Turbine | 169250 | B Inspection | 545915 | 2027-03-07 | 2027-03-13
GT11N | NAM North America | 803770 | Gas Turbine | 169251 | B Inspection | 545916 | 2028-03-05 | 2028-03-11
GT11N | NAM North America | 810883 | Gas Turbine | 175776 | C Inspection | 549845 | 2027-10-04 | 2027-11-05
GT11N | NAM North America | 810887 | Gas Turbine | 175777 | C Inspection | 549846 | 2028-02-28 | 2028-03-27
GT11N | NAM North America | 810892 | Gas Turbine | 175781 | C Inspection | 549847 | 2028-01-10 | 2028-02-22
GT11N | NAM North America | 810891 | Gas Turbine | 175783 | C Inspection | 549848 | 2028-09-01 | 2028-09-26
GT11N | NAM North America | 810886 | Gas Turbine | 175784 | C Inspection | 549849 | 2029-02-17 | 2029-03-14
GT11N | NAM North America | 810881 | Gas Turbine | 175787 | C Inspection | 549850 | 2029-03-15 | 2029-04-09
GT11N | NAM North America | 803770 | Gas Turbine | 182289 | C Inspection | 554608 | 2029-02-25 | 2029-03-09
GT11N | NAM North America | 803769 | Gas Turbine | 182290 | C Inspection | 554609 | 2030-02-10 | 2030-03-08
GT11N | NAM North America | 810884 | Gas Turbine | 183693 | C Inspection |  | 2026-04-30 | 2026-05-25
GT11N | NAM North America | 810885 | Gas Turbine | 183694 | C Inspection |  | 2026-10-11 | 2026-11-05
GT11N | NAM North America | 810880 | Gas Turbine | 183695 | C Inspection |  | 2027-04-30 | 2027-05-25
GT11N | NAM North America | 810893 | Gas Turbine | 183696 | C Inspection | 555879 | 2027-09-01 | 2027-09-26
GT11N | NAM North America | 810883 | Gas Turbine | 183697 | C Inspection |  | 2027-11-19 | 2027-12-14
GT11N | NAM North America | 810886 | Gas Turbine | 183698 | C Inspection | 562285 | 2029-01-22 | 2029-02-23
GT11N | NAM North America | 810891 | Gas Turbine | 183699 | C Inspection | 554848 | 2028-09-01 | 2028-09-26
GT11N | NAM North America | 810892 | Gas Turbine | 183700 | C Inspection |  | 2028-09-01 | 2028-09-26
GT11N | NAM North America | 810890 | Gas Turbine | 183701 | C Inspection | 554531 | 2028-11-25 | 2028-12-20
GT11N | NAM North America | 810887 | Gas Turbine | 183703 | C Inspection |  | 2028-11-26 | 2028-12-21
GT11N | NAM North America | 810881 | Gas Turbine | 183704 | C Inspection |  | 2029-02-12 | 2029-03-09
GT11N | NAM North America | 810893 | Gas Turbine | 189613 | A Inspection | 558580 | 2026-01-08 | 2026-01-09
GT11N | NAM North America | 810885 | Gas Turbine | 190515 | A Inspection | 559286 | 2026-02-11 | 2026-02-12
GT11N | NAM North America | 810892 | Gas Turbine | 191061 | A Inspection | 559627 | 2026-02-09 | 2026-02-10
GT11N | NAM North America | 810881 | Gas Turbine | 192621 | A Inspection | 560687 | 2026-04-02 | 2026-04-03
GT11N | NAM North America | 810887 | Gas Turbine | 192622 | A Inspection | 560686 | 2026-04-07 | 2026-04-08
GT11N | NAM North America | 810886 | Gas Turbine | 193371 | A Inspection | 561251 | 2026-04-29 | 2026-04-30
GT11N | NAM North America | 810890 | Gas Turbine | 193396 | A Inspection | 561254 | 2026-05-24 | 2026-05-25
GT11N | NAM North America | 810893 | Gas Turbine | 193397 | A Inspection | 561255 | 2026-06-05 | 2026-06-06
GT11N | NAM North America | 803769 | Gas Turbine | 193701 | A Inspection | 561443 | 2027-08-21 | 2027-08-22
GT11N | NAM North America | 803770 | Gas Turbine | 193703 | A Inspection | 561444 | 2027-09-11 | 2027-09-12
GT11N | NAM North America | 803769 | Gas Turbine | 193705 | A Inspection | 563403 | 2026-08-22 | 2026-08-23
GT11N | NAM North America | 803770 | Gas Turbine | 193706 | A Inspection | 563402 | 2026-09-12 | 2026-09-13
GT11N | NAM North America | 803769 | Gas Turbine | 193710 | A Inspection |  | 2028-08-26 | 2028-08-27
GT11N | NAM North America | 803770 | Gas Turbine | 193711 | A Inspection |  | 2028-09-16 | 2028-09-17
GT11N | NAM North America | 810880 | Gas Turbine | 194767 | A Inspection | 562442 | 2026-07-07 | 2026-07-08
GT11N | NAM North America | 810885 | Gas Turbine | 194768 | A Inspection | 562584 | 2026-06-22 | 2026-06-23
GT11N | NAM North America | 810892 | Gas Turbine | 194770 | A Inspection | 562586 | 2026-07-27 | 2026-07-28
GT11N | NAM North America | 810884 | Gas Turbine | 195484 | C Inspection | 562925 | 2030-01-24 | 2030-02-18
GT11N | NAM North America | 810885 | Gas Turbine | 195486 | C Inspection | 562926 | 2030-04-30 | 2030-05-25
GT11N | NAM North America | 810883 | Gas Turbine | 195936 | A Inspection | 563291 | 2026-08-04 | 2026-08-06
GT11N | NAM North America | 810891 | Gas Turbine | 195937 | A Inspection | 563290 | 2026-08-17 | 2026-08-19
GT11N2 | Latin America | 804598 | Gas Turbine | 136440 | C Inspection | 523925 | 2026-06-05 | 2026-07-16
GT11N2 | Latin America | V00362 | Gas Turbine | 149831 | C Inspection | 531715 | 2026-11-27 | 2027-01-05
GT11N2 | Latin America | V00363 | Gas Turbine | 149833 | C Inspection | 531716 | 2026-07-14 | 2026-08-20
GT11N2 | Latin America | V00362 | Gas Turbine | 165604 | B Inspection | 545154 | 2026-01-13 | 2026-01-16
GT11N2 | Latin America | V00362 | Gas Turbine | 165605 | A Inspection | 545155 | 2026-09-01 | 2026-09-08
GT11N2 | NAM North America | 804970 | Gas Turbine | 169215 | C Inspection |  | 2029-09-01 | 2029-09-26
GT11N2 | Latin America | 804686 | Gas Turbine | 179383 | Large Call-Out | 551962 | 2026-07-17 | 2026-08-06
GT11N2 | Latin America | 804690 | Gas Turbine | 183413 | C Inspection |  | 2028-06-01 | 2028-06-25
GT11N2 | Latin America | 804689 | Gas Turbine | 183414 | C Inspection |  | 2028-07-01 | 2028-07-25
GT11N2 | Latin America | 804659 | Gas Turbine | 183415 | C Inspection |  | 2029-06-01 | 2029-06-25
GT11N2 | Latin America | 804686 | Gas Turbine | 183416 | C Inspection |  | 2029-07-01 | 2029-07-25
GT11N2 | Latin America | 804598 | Gas Turbine | 183417 | C Inspection |  | 2029-10-01 | 2029-10-26
GT11N2 | Latin America | V00363 | Gas Turbine | 183508 | C Inspection | 554430 | 2030-07-03 | 2030-08-01
GT11N2 | Latin America | V00363 | Gas Turbine | 185722 | C Inspection | 555954 | 2028-07-03 | 2028-07-28
GT11N2 | Latin America | V00362 | Gas Turbine | 185725 | C Inspection | 555955 | 2029-01-09 | 2029-02-03
GT11N2 | Latin America | V00363 | Gas Turbine | 189872 | A Inspection |  | 2027-01-05 | 2027-01-08
GT11N2 | Latin America | V00363 | Gas Turbine | 189873 | B Inspection | 558743 | 2027-07-05 | 2027-07-08
GT11N2 | Latin America | V00363 | Gas Turbine | 189874 | A Inspection | 558744 | 2028-01-10 | 2028-01-13
GT11N2 | Latin America | V00362 | Gas Turbine | 189875 | A Inspection | 558745 | 2027-07-05 | 2027-07-09
GT11N2 | Latin America | V00362 | Gas Turbine | 189876 | B Inspection | 558747 | 2028-02-07 | 2028-02-10
GT11N2 | Latin America | V00362 | Gas Turbine | 189877 | A Inspection | 558748 | 2028-08-14 | 2028-08-17
GT11N2 | Latin America | 804659 | Gas Turbine | 190475 | A Inspection | 561716 | 2026-05-02 | 2026-05-05
GT11N2 | Latin America | 804689 | Gas Turbine | 190476 | B Inspection |  | 2026-08-28 | 2026-08-31
GT11N2 | Latin America | 804690 | Gas Turbine | 190664 | B Inspection | 562289 | 2026-08-14 | 2026-08-17
GT13E2 | MENA | G00277 | Gas Turbine | 125189 | C Inspection | 521315 | 2026-10-15 | 2026-11-25
GT13E2 | Latin America | G00366 | Gas Turbine | 133357 | C Inspection | 532452 | 2027-07-26 | 2027-08-26
GT13E2 | Latin America | G00367 | Gas Turbine | 133362 | C Inspection | 532614 | 2027-07-26 | 2027-08-26
GT13E2 | China | G00361 | Gas Turbine | 145508 | C Inspection | 554492 | 2028-04-15 | 2028-05-28
GT13E2 | MENA | G00328 | Gas Turbine | 145509 | C Inspection | 532404 | 2026-12-15 | 2027-02-17
GT13E2 | Europe | 804333 | Gas Turbine | 154638 | B Inspection | 534974 | 2028-05-08 | 2028-05-13
GT13E2 | Asia | G00313 | Gas Turbine | 155603 | A Inspection | 535636 | 2026-03-02 | 2026-03-06
GT13E2 | Latin America | G00367 | Gas Turbine | 157871 | C Inspection | 537406 | 2026-06-22 | 2026-07-23
GT13E2 | Latin America | G00367 | Gas Turbine | 157872 | C Inspection |  | 2026-06-22 | 2026-07-23
GT13E2 | China | G00362 | Gas Turbine | 158641 | C Inspection |  | 2030-02-10 | 2030-03-07
GT13E2 | China | G00363 | Gas Turbine | 158642 | C Inspection |  | 2030-09-19 | 2030-10-14
GT13E2 | MENA | G00326 | Gas Turbine | 159028 | C Inspection | 538169 | 2030-09-01 | 2030-10-13
GT13E2 | MENA | G00325 | Gas Turbine | 159029 | C Inspection | 538170 | 2029-09-26 | 2029-11-06
GT13E2 | China | G00361 | Gas Turbine | 160653 | A Inspection | 539288 | 2027-03-15 | 2027-03-21
GT13E2 | China | G00362 | Gas Turbine | 160719 | A Inspection | 539332 | 2026-09-16 | 2026-09-25
GT13E2 | China | G00362 | Gas Turbine | 160721 | Borescope Inspection (BI) | 539333 | 2026-06-01 | 2026-06-03
GT13E2 | China | G00362 | Gas Turbine | 160722 | B Inspection | 539334 | 2027-11-01 | 2027-11-10
GT13E2 | China | G00363 | Gas Turbine | 160725 | A Inspection | 539337 | 2027-04-01 | 2027-04-10
GT13E2 | MENA | G00325 | Gas Turbine | 169768 | A Inspection | 546186 | 2026-09-26 | 2026-10-02
GT13E2 | MENA | G00326 | Gas Turbine | 169769 | A Inspection | 546187 | 2027-03-16 | 2027-03-22
GT13E2 | Asia | G00313 | Gas Turbine | 169988 | B Inspection | 546362 | 2027-03-01 | 2027-03-08
GT13E2 | MENA | G00277 | Gas Turbine | 170172 | A Inspection | 546447 | 2028-01-15 | 2028-01-20
GT13E2 | MENA | G00277 | Gas Turbine | 170173 | B Inspection | 546448 | 2030-01-14 | 2030-01-19
GT13E2 | MENA | G00287 | Gas Turbine | 170182 | A Inspection | 546455 | 2027-11-15 | 2027-11-20
GT13E2 | MENA | G00287 | Gas Turbine | 170183 | B Inspection | 546456 | 2029-11-14 | 2029-11-19
GT13E2 | China | G00360 | Gas Turbine | 170384 | C Inspection | 546615 | 2028-03-01 | 2028-04-14
GT13E2 | Europe | G501 | Gas Turbine | 173680 | C Inspection | 548438 | 2026-05-01 | 2026-06-24
GT13E2 | Asia | G00307 | Gas Turbine | 177163 | A Inspection | 550785 | 2027-08-10 | 2027-08-14
GT13E2 | Asia | G00296 | Gas Turbine | 177164 | A Inspection | 550786 | 2028-05-18 | 2028-05-22
GT13E2 | Asia | G00293 | Gas Turbine | 177166 | C Inspection | 550787 | 2027-08-02 | 2027-09-16
GT13E2 | Asia | G00296 | Gas Turbine | 177167 | C Inspection | 550788 | 2026-10-26 | 2026-12-10
GT13E2 | Asia | G00306 | Gas Turbine | 177168 | A Inspection | 550790 | 2028-08-05 | 2028-08-09
GT13E2 | Latin America | G00366 | Gas Turbine | 177180 | C Inspection |  | 2030-02-21 | 2030-03-18
GT13E2 | Latin America | G00367 | Gas Turbine | 177181 | C Inspection |  | 2030-02-21 | 2030-03-18
GT13E2 | MENA | G00332 | Gas Turbine | 177267 | C Inspection | 550862 | 2028-04-03 | 2028-05-04
GT13E2 | MENA | G00331 | Gas Turbine | 177269 | C Inspection | 550863 | 2028-02-28 | 2028-03-30
GT13E2 | Asia | G00288 | Gas Turbine | 179922 | C Inspection | 552285 | 2029-08-01 | 2029-09-15
GT13E2 | MENA | G00309 | Gas Turbine | 180770 | C Inspection | 552787 | 2028-05-20 | 2028-06-26
GT13E2 | MENA | G00308 | Gas Turbine | 180773 | C Inspection | 552788 | 2029-01-01 | 2029-01-26
GT13E2 | MENA | G00311 | Gas Turbine | 180774 | C Inspection | 553187 | 2029-08-15 | 2029-09-09
GT13E2 | MENA | G00310 | Gas Turbine | 180775 | C Inspection |  | 2030-04-07 | 2030-05-02
GT13E2 | Europe | G00373 | Gas Turbine | 182356 | B Inspection | 554894 | 2026-09-09 | 2026-09-14
GT13E2 | MENA | G00332 | Gas Turbine | 182421 | A Inspection | 553729 | 2026-11-21 | 2026-11-25
GT13E2 | MENA | G00331 | Gas Turbine | 182422 | A Inspection | 553728 | 2026-11-16 | 2026-11-20
GT13E2 | Europe | G500 | Gas Turbine | 183309 | C Inspection | 554312 | 2030-05-01 | 2030-06-17
GT13E2 | Europe | G501 | Gas Turbine | 183310 | C Inspection | 554313 | 2029-12-29 | 2030-01-23
GT13E2 | Asia | G00288 | Gas Turbine | 183641 | A Inspection | 554501 | 2027-09-07 | 2027-09-11
GT13E2 | MENA | G00309 | Gas Turbine | 186022 | B Inspection | 556339 | 2026-11-15 | 2026-11-20
GT13E2 | MENA | G00308 | Gas Turbine | 186139 | B Inspection | 556246 | 2026-11-22 | 2026-11-27
GT13E2 | China | G00362 | Gas Turbine | 187569 | C Inspection |  | 2030-03-25 | 2030-04-19
GT13E2 | China | G00360 | Gas Turbine | 187570 | C Inspection |  | 2027-01-01 | 2027-01-26
GT13E2 | China | G00361 | Gas Turbine | 187571 | C Inspection |  | 2028-02-01 | 2028-02-26
GT13E2 | Latin America | G00367 | Gas Turbine | 187622 | C Inspection |  | 2027-02-01 | 2027-02-26
GT13E2 | Latin America | G00366 | Gas Turbine | 187623 | C Inspection |  | 2027-02-01 | 2027-02-26
GT13E2 | MENA | G00264 | Gas Turbine | 188656 | C Inspection | 559268 | 2028-03-01 | 2028-03-31
GT13E2 | MENA | 804757 | Gas Turbine | 188660 | C Inspection | 559267 | 2028-02-01 | 2028-03-01
GT13E2 | MENA | 804862 | Gas Turbine | 188661 | C Inspection | 559374 | 2028-10-01 | 2028-10-30
GT13E2 | MENA | G00266 | Gas Turbine | 188663 | C Inspection | 559269 | 2028-10-01 | 2028-10-31
GT13E2 | MENA | G00273 | Gas Turbine | 188664 | C Inspection | 559270 | 2030-04-01 | 2030-04-30
GT13E2 | MENA | G00266 | Gas Turbine | 188948 | B Inspection | 558518 | 2026-01-13 | 2026-01-17
GT13E2 | MENA | G00273 | Gas Turbine | 188949 | A Inspection | 558516 | 2026-04-15 | 2026-04-18
GT13E2 | MENA | 804862 | Gas Turbine | 190310 | A Inspection | 559313 | 2026-02-22 | 2026-02-24
GT13E2 | Asia | G00293 | Gas Turbine | 190450 | A Inspection | 559174 | 2029-10-01 | 2029-10-10
GT13E2 | Europe | G500 | Gas Turbine | 190609 | A Inspection |  | 2026-04-20 | 2026-04-25
GT13E2 | Europe | G00373 | Gas Turbine | 191485 | A Inspection | 559948 | 2027-10-14 | 2027-10-18
GT13E2 | Europe | G500 | Gas Turbine | 191604 | A Inspection | 562336 | 2027-05-09 | 2027-05-16
GT13E2 | Europe | G501 | Gas Turbine | 191609 | A Inspection | 560038 | 2027-05-02 | 2027-05-09
GT13E2 | Europe | G500 | Gas Turbine | 191616 | B Inspection | 560039 | 2028-05-19 | 2028-05-29
GT13E2 | Europe | G500 | Gas Turbine | 191619 | A Inspection | 560040 | 2028-05-01 | 2028-05-08
GT13E2 | Europe | G501 | Gas Turbine | 191625 | B Inspection | 560041 | 2028-05-08 | 2028-05-18
GT13E2 | Latin America | G00300 | Gas Turbine | 194067 | C Inspection | 561779 | 2026-09-09 | 2026-10-08
GT13E2 | Latin America | G00299 | Gas Turbine | 194070 | C Inspection | 561780 | 2026-10-13 | 2026-11-11
GT13E2 | China | G00362 | Gas Turbine | 194599 | C Inspection |  | 2030-03-25 | 2030-04-19
GT13E2 | China | G00360 | Gas Turbine | 194600 | C Inspection |  | 2027-01-01 | 2027-01-26
GT13E2 | China | G00361 | Gas Turbine | 194601 | C Inspection |  | 2028-02-01 | 2028-02-26
GT13E2 | MENA | G00325 | Gas Turbine | 196019 | B Inspection | 563322 | 2027-09-01 | 2027-09-08
GT13E2 | MENA | G00325 | Gas Turbine | 196020 | A Inspection | 563323 | 2028-09-26 | 2028-10-02
GT13E2 | MENA | G00326 | Gas Turbine | 196021 | A Inspection | 563324 | 2029-09-16 | 2029-09-22
GT13E2 | MENA | G00326 | Gas Turbine | 196022 | B Inspection | 563325 | 2028-09-02 | 2028-09-09
GT13E2 | MENA | G00328 | Gas Turbine | 196023 | A Inspection | 563326 | 2028-03-19 | 2028-03-25
GT13E2 | MENA | G00328 | Gas Turbine | 196024 | B Inspection | 563327 | 2029-09-06 | 2029-09-13
GT13E2 | MENA | G00328 | Gas Turbine | 196025 | A Inspection | 563328 | 2030-10-15 | 2030-10-21
GT24 | Latin America | V02447 | Gas Turbine | 107418 | C Inspection | 504436 | 2030-01-14 | 2030-02-17
GT24 | Latin America | V02456 | Gas Turbine | 107945 | C Inspection | 504435 | 2029-10-01 | 2029-10-31
GT24 | Latin America | V02456 | Gas Turbine | 109511 | C Inspection | 504425 | 2027-11-13 | 2027-12-18
GT24 | Latin America | V02448 | Gas Turbine | 112228 | C Inspection | 504437 | 2030-02-10 | 2030-03-13
GT24 | Latin America | V02449 | Gas Turbine | 112430 | C Inspection | 504429 | 2029-01-21 | 2029-02-26
GT24 | Latin America | V02456 | Gas Turbine | 112938 | C Inspection | 504430 | 2026-11-23 | 2026-12-23
GT24 | Latin America | V02448 | Gas Turbine | 115052 | C Inspection | 504433 | 2027-12-06 | 2028-01-05
GT24 | Latin America | V02448 | Gas Turbine | 115934 | C Inspection | 504428 | 2027-01-10 | 2027-02-13
GT24 | Latin America | V02447 | Gas Turbine | 120662 | C Inspection | 504432 | 2027-12-18 | 2028-01-17
GT24 | Latin America | V02449 | Gas Turbine | 121697 | C Inspection | 504434 | 2028-06-28 | 2028-07-28
GT24 | Latin America | V02447 | Gas Turbine | 122495 | C Inspection | 504427 | 2026-12-06 | 2027-01-17
GT24 | Latin America | V02449 | Gas Turbine | 122742 | C Inspection | 504424 | 2026-01-18 | 2026-02-23
GT24 | Latin America | V02500 | Gas Turbine | 122835 | C Inspection | 504431 | 2028-08-19 | 2028-09-18
GT24 | NAM North America | 811845 | Gas Turbine | 132009 | C Inspection | 521852 | 2026-09-21 | 2026-10-21
GT24 | NAM North America | 816519 | Gas Turbine | 132500 | C Inspection | 522247 | 2026-04-13 | 2026-05-17
GT24 | NAM North America | V02420 | Gas Turbine | 132508 | C Inspection | 522255 | 2027-03-02 | 2027-04-05
GT24 | NAM North America | V02421 | Gas Turbine | 132509 | C Inspection | 522256 | 2026-03-02 | 2026-04-05
GT24 | NAM North America | V02422 | Gas Turbine | 132510 | A Inspection | 522257 | 2026-04-17 | 2026-04-21
GT24 | NAM North America | V02442 | Gas Turbine | 132512 | A Inspection | 522259 | 2026-03-28 | 2026-04-01
GT24 | NAM North America | 816518 | Gas Turbine | 132514 | C Inspection | 522261 | 2027-04-14 | 2027-05-16
GT24 | NAM North America | V02440 | Gas Turbine | 145028 | C Inspection | 528794 | 2026-03-12 | 2026-04-15
GT24 | NAM North America | 816517 | Gas Turbine | 145163 | A Inspection | 528899 | 2026-04-23 | 2026-04-27
GT24 | NAM North America | 816517 | Gas Turbine | 145166 | C Inspection | 528901 | 2027-10-02 | 2027-11-02
GT24 | NAM North America | 816518 | Gas Turbine | 145168 | B Inspection | 528903 | 2028-03-04 | 2028-03-08
GT24 | NAM North America | 816519 | Gas Turbine | 145169 | B Inspection | 528904 | 2026-05-06 | 2026-05-10
GT24 | NAM North America | 816519 | Gas Turbine | 145170 | A Inspection | 528905 | 2027-04-12 | 2027-04-16
GT24 | NAM North America | 816520 | Gas Turbine | 145171 | A Inspection | 528906 | 2026-05-06 | 2026-05-11
GT24 | NAM North America | 816520 | Gas Turbine | 145172 | C Inspection | 528907 | 2027-04-03 | 2027-05-03
GT24 | NAM North America | V02419 | Gas Turbine | 145174 | B Inspection | 528909 | 2026-04-14 | 2026-04-18
GT24 | NAM North America | V02419 | Gas Turbine | 145176 | A Inspection | 528911 | 2027-03-01 | 2027-03-05
GT24 | NAM North America | V02419 | Gas Turbine | 145177 | C Inspection | 528912 | 2028-03-06 | 2028-04-02
GT24 | NAM North America | V02420 | Gas Turbine | 145181 | B Inspection | 528915 | 2029-03-12 | 2029-03-16
GT24 | NAM North America | V02421 | Gas Turbine | 145182 | A Inspection | 528917 | 2026-04-17 | 2026-04-21
GT24 | NAM North America | V02421 | Gas Turbine | 145183 | B Inspection | 528918 | 2028-03-15 | 2028-03-19
GT24 | NAM North America | V02422 | Gas Turbine | 145185 | A Inspection | 528919 | 2028-03-25 | 2028-03-29
GT24 | NAM North America | V02422 | Gas Turbine | 145186 | B Inspection | 528921 | 2027-03-22 | 2027-03-26
GT24 | NAM North America | V02440 | Gas Turbine | 145187 | A Inspection | 528922 | 2027-03-18 | 2027-03-22
GT24 | NAM North America | V02440 | Gas Turbine | 145188 | B Inspection | 528923 | 2028-03-20 | 2028-03-24
GT24 | NAM North America | V02442 | Gas Turbine | 145189 | B Inspection | 528924 | 2027-04-24 | 2027-04-28
GT24 | NAM North America | V02442 | Gas Turbine | 145190 | C Inspection | 528925 | 2029-03-05 | 2029-04-04
GT24 | NAM North America | V02425 | Gas Turbine | 147005 | C Inspection | 529931 | 2026-10-01 | 2026-10-31
GT24 | NAM North America | 816517 | Gas Turbine | 147691 | A Inspection | 530310 | 2028-05-06 | 2028-05-10
GT24 | NAM North America | 816517 | Gas Turbine | 147692 | B Inspection | 530311 | 2029-04-07 | 2029-04-11
GT24 | NAM North America | 816517 | Gas Turbine | 147693 | A Inspection | 530312 | 2030-03-09 | 2030-03-13
GT24 | NAM North America | 816518 | Gas Turbine | 147694 | A Inspection | 530313 | 2026-04-16 | 2026-04-20
GT24 | NAM North America | 816518 | Gas Turbine | 147695 | C Inspection | 530314 | 2030-10-05 | 2030-11-05
GT24 | NAM North America | 816518 | Gas Turbine | 147696 | A Inspection | 530315 | 2030-03-02 | 2030-03-06
GT24 | NAM North America | 816519 | Gas Turbine | 147697 | C Inspection | 530316 | 2030-04-17 | 2030-05-21
GT24 | NAM North America | 816519 | Gas Turbine | 147698 | A Inspection | 530317 | 2029-03-03 | 2029-03-07
GT24 | NAM North America | 816519 | Gas Turbine | 147699 | B Inspection | 530318 | 2028-03-09 | 2028-03-13
GT24 | NAM North America | 816520 | Gas Turbine | 147700 | A Inspection | 530319 | 2028-03-04 | 2028-03-08
GT24 | NAM North America | 816520 | Gas Turbine | 147701 | B Inspection | 530320 | 2029-03-03 | 2029-03-07
GT24 | NAM North America | 816520 | Gas Turbine | 147702 | A Inspection | 530321 | 2030-03-09 | 2030-03-13
GT24 | NAM North America | V02419 | Gas Turbine | 147703 | A Inspection | 530322 | 2028-05-06 | 2028-05-10
GT24 | NAM North America | V02419 | Gas Turbine | 147704 | B Inspection | 530323 | 2029-03-03 | 2029-03-07
GT24 | NAM North America | V02419 | Gas Turbine | 147705 | A Inspection | 530324 | 2030-03-02 | 2030-03-06
GT24 | NAM North America | V02420 | Gas Turbine | 147706 | A Inspection | 530325 | 2028-03-13 | 2028-03-17
GT24 | NAM North America | V02420 | Gas Turbine | 147708 | A Inspection | 530327 | 2030-03-18 | 2030-03-22
GT24 | NAM North America | V02421 | Gas Turbine | 147709 | A Inspection | 530328 | 2027-03-16 | 2027-03-20
GT24 | NAM North America | V02421 | Gas Turbine | 147710 | C Inspection | 530329 | 2030-03-04 | 2030-04-07
GT24 | NAM North America | V02421 | Gas Turbine | 147711 | A Inspection | 530330 | 2029-03-20 | 2029-03-24
GT24 | NAM North America | V02422 | Gas Turbine | 147712 | A Inspection | 530331 | 2030-03-09 | 2030-03-13
GT24 | NAM North America | V02422 | Gas Turbine | 147713 | C Inspection | 530332 | 2029-03-15 | 2029-04-11
GT24 | NAM North America | V02422 | Gas Turbine | 147714 | A Inspection | 530333 | 2030-03-09 | 2030-03-13
GT24 | NAM North America | V02440 | Gas Turbine | 147715 | A Inspection | 530334 | 2029-03-13 | 2029-03-17
GT24 | NAM North America | V02440 | Gas Turbine | 147716 | C Inspection | 530335 | 2030-03-25 | 2030-04-24
GT24 | NAM North America | V02442 | Gas Turbine | 147718 | A Inspection | 530337 | 2028-04-15 | 2028-04-19
GT24 | NAM North America | V02442 | Gas Turbine | 147720 | A Inspection | 530339 | 2030-04-15 | 2030-04-19
GT24 | NAM North America | 811853 | Gas Turbine | 148599 | B Inspection | 530836 | 2026-04-04 | 2026-04-11
GT24 | NAM North America | 811854 | Gas Turbine | 148600 | A Inspection | 530837 | 2026-04-18 | 2026-04-25
GT24 | NAM North America | 811855 | Gas Turbine | 148603 | A Inspection | 530838 | 2026-05-02 | 2026-05-09
GT24 | NAM North America | 811853 | Gas Turbine | 148604 | A Inspection | 530839 | 2027-04-03 | 2027-04-10
GT24 | NAM North America | 811855 | Gas Turbine | 148606 | B Inspection | 530841 | 2027-04-10 | 2027-04-17
GT24 | NAM North America | 811853 | Gas Turbine | 148608 | C Inspection | 530842 | 2027-11-01 | 2027-12-01
GT24 | NAM North America | 811854 | Gas Turbine | 148609 | A Inspection | 530843 | 2028-05-06 | 2028-05-13
GT24 | NAM North America | 811855 | Gas Turbine | 148610 | A Inspection | 530844 | 2028-05-20 | 2028-05-27
GT24 | NAM North America | 811780 | Gas Turbine | 152527 | C Inspection | 533510 | 2027-03-25 | 2027-04-26
GT24 | NAM North America | 811778 | Gas Turbine | 153781 | C Inspection | 534471 | 2027-03-01 | 2027-04-02
GT24 | NAM North America | 811782 | Gas Turbine | 153782 | C Inspection | 534472 | 2028-03-15 | 2028-04-15
GT24 | NAM North America | 811784 | Gas Turbine | 153783 | C Inspection | 534473 | 2028-04-12 | 2028-05-12
GT24 | NAM North America | 811782 | Gas Turbine | 153788 | A Inspection | 534476 | 2026-10-09 | 2026-10-16
GT24 | NAM North America | 811784 | Gas Turbine | 153790 | A Inspection | 534478 | 2026-10-03 | 2026-10-10
GT24 | NAM North America | 811780 | Gas Turbine | 153795 | A Inspection | 534483 | 2026-03-14 | 2026-03-20
GT24 | NAM North America | 811778 | Gas Turbine | 153798 | A Inspection | 534485 | 2026-03-19 | 2026-03-25
GT24 | Latin America | V02447 | Gas Turbine | 157041 | B Inspection | 536692 | 2026-01-05 | 2026-01-09
GT24 | Latin America | V02448 | Gas Turbine | 157043 | B Inspection | 536694 | 2026-09-01 | 2026-09-05
GT24 | NAM North America | V02424 | Gas Turbine | 158345 | B Inspection | 537788 | 2027-05-17 | 2027-05-24
GT24 | NAM North America | V02425 | Gas Turbine | 158346 | A Inspection | 537783 | 2027-10-09 | 2027-10-16
GT24 | NAM North America | V02424 | Gas Turbine | 158347 | A Inspection | 537784 | 2028-05-13 | 2028-05-20
GT24 | NAM North America | V02425 | Gas Turbine | 158348 | B Inspection | 537785 | 2028-10-14 | 2028-10-21
GT24 | Latin America | V02447 | Gas Turbine | 167699 | A Inspection | 544648 | 2028-01-15 | 2028-01-18
GT24 | Latin America | V02448 | Gas Turbine | 167700 | A Inspection | 544649 | 2028-02-20 | 2028-02-23
GT24 | Latin America | V02449 | Gas Turbine | 167701 | A Inspection | 544650 | 2027-01-05 | 2027-01-08
GT24 | Latin America | V02456 | Gas Turbine | 167702 | A Inspection | 544651 | 2026-12-04 | 2026-12-07
GT24 | Latin America | V02447 | Gas Turbine | 167703 | B Inspection | 544652 | 2029-01-13 | 2029-01-16
GT24 | Latin America | V02448 | Gas Turbine | 167704 | B Inspection | 544653 | 2029-02-17 | 2029-02-20
GT24 | Latin America | V02449 | Gas Turbine | 167705 | B Inspection | 544654 | 2028-01-15 | 2028-01-19
GT24 | Latin America | V02456 | Gas Turbine | 167706 | B Inspection | 544655 | 2027-09-17 | 2027-09-21
GT24 | Latin America | V02449 | Gas Turbine | 167861 | A Inspection | 544795 | 2027-12-09 | 2027-12-12
GT24 | Latin America | V02456 | Gas Turbine | 167862 | A Inspection | 544796 | 2028-06-23 | 2028-06-26
GT24 | Latin America | V02500 | Gas Turbine | 167863 | A Inspection | 544797 | 2026-02-21 | 2026-02-25
GT24 | Latin America | V02456 | Gas Turbine | 167864 | B Inspection | 544798 | 2027-02-05 | 2027-02-08
GT24 | Latin America | V02500 | Gas Turbine | 167865 | B Inspection | 544799 | 2027-02-05 | 2027-02-08
GT24 | Latin America | V02500 | Gas Turbine | 167866 | A Inspection | 544800 | 2028-02-11 | 2028-02-14
GT24 | NAM North America | 804341 | Gas Turbine | 169450 | C Inspection |  | 2027-06-21 | 2027-07-16
GT24 | NAM North America | 816519 | Gas Turbine | 169775 | Large Call-Out | 547103 | 2026-04-13 | 2026-05-06
GT24 | NAM North America | V02424 | Gas Turbine | 172290 | A Inspection | 547613 | 2029-05-12 | 2029-05-19
GT24 | NAM North America | V02425 | Gas Turbine | 172291 | A Inspection | 547614 | 2029-10-13 | 2029-10-20
GT24 | Latin America | V02431 | Gas Turbine | 176797 | C Inspection | 550497 | 2027-11-01 | 2027-12-06
GT24 | NAM North America | V02420 | Gas Turbine | 177676 | A Inspection | 551096 | 2026-04-30 | 2026-05-04
GT24 | NAM North America | V02425 | Gas Turbine | 181632 | A Inspection | 553407 | 2026-05-16 | 2026-05-23
GT24 | NAM North America | 816517 | Gas Turbine | 182283 | C Inspection |  | 2030-12-19 | 2031-01-13
GT24 | NAM North America | 816517 | Gas Turbine | 185499 | Large Call-Out | 559095 | 2026-04-22 | 2026-05-06
GT24 | NAM North America | V02441 | Gas Turbine | 186768 | A Inspection | 556710 | 2026-02-21 | 2026-02-27
GT24 | NAM North America | V02444 | Gas Turbine | 186769 | B Inspection | 556711 | 2026-02-28 | 2026-03-08
GT24 | NAM North America | V02445 | Gas Turbine | 186770 | B Inspection | 556712 | 2026-03-09 | 2026-03-17
GT24 | NAM North America | V02441 | Gas Turbine | 186783 | C Inspection |  | 2030-04-01 | 2030-04-26
GT24 | NAM North America | V02443 | Gas Turbine | 186960 | C Inspection | 556805 | 2026-01-17 | 2026-02-21
GT24 | NAM North America | V02444 | Gas Turbine | 187048 | C Inspection | 556889 | 2027-03-01 | 2027-03-26
GT24 | NAM North America | V02445 | Gas Turbine | 187135 | C Inspection | 556938 | 2028-04-01 | 2028-04-26
GT24 | NAM North America | V02424 | Gas Turbine | 187196 | C Inspection | 556942 | 2029-10-01 | 2029-10-31
GT24 | NAM North America | V02425 | Gas Turbine | 187197 | C Inspection | 556943 | 2030-05-01 | 2030-05-31
GT24 | NAM North America | 811845 | Gas Turbine | 188927 | A Inspection | 561708 | 2026-05-18 | 2026-05-22
GT24 | NAM North America | 805598 | Gas Turbine | 191530 | B Inspection | 560014 | 2026-10-19 | 2026-10-25
GT24 | NAM North America | 804341 | Gas Turbine | 191531 | B Inspection | 560013 | 2026-10-26 | 2026-11-02
GT24 | NAM North America | 805598 | Gas Turbine | 191532 | A Inspection | 559992 | 2027-11-29 | 2027-12-10
GT24 | NAM North America | 805598 | Gas Turbine | 191533 | A Inspection | 559993 | 2028-12-04 | 2028-12-15
GT24 | NAM North America | 805598 | Gas Turbine | 191534 | A Inspection | 559994 | 2029-12-03 | 2029-12-14
GT24 | NAM North America | 804341 | Gas Turbine | 191536 | A Inspection | 559996 | 2027-11-29 | 2027-12-10
GT24 | NAM North America | 804341 | Gas Turbine | 191537 | A Inspection | 559997 | 2028-12-04 | 2028-12-15
GT24 | NAM North America | 804341 | Gas Turbine | 191538 | A Inspection | 559998 | 2029-12-03 | 2029-12-14
GT24 | NAM North America | 804341 | Gas Turbine | 191539 | A Inspection | 559999 | 2030-12-02 | 2030-12-13
GT24 | NAM North America | V02441 | Gas Turbine | 191824 | B Inspection | 560143 | 2027-02-28 | 2027-03-04
GT24 | NAM North America | V02443 | Gas Turbine | 191825 | A Inspection | 560144 | 2027-03-06 | 2027-03-12
GT24 | NAM North America | V02444 | Gas Turbine | 191826 | A Inspection | 560145 | 2027-03-29 | 2027-04-02
GT24 | NAM North America | V02445 | Gas Turbine | 191827 | A Inspection | 560146 | 2027-03-12 | 2027-03-16
GT24 | NAM North America | V02441 | Gas Turbine | 191828 | A Inspection | 560148 | 2028-02-21 | 2028-02-25
GT24 | NAM North America | V02443 | Gas Turbine | 191829 | A Inspection | 560149 | 2028-02-28 | 2028-03-03
GT24 | NAM North America | V02444 | Gas Turbine | 191831 | A Inspection | 560151 | 2028-03-27 | 2028-03-31
GT24 | NAM North America | 811854 | Gas Turbine | 191961 | C Inspection | 560233 | 2027-05-01 | 2027-05-31
GT24 | NAM North America | V02441 | Gas Turbine | 193567 | C Inspection |  | 2030-04-01 | 2030-04-26
GT24 | NAM North America | V02444 | Gas Turbine | 193569 | C Inspection |  | 2027-03-01 | 2027-03-26
GT24 | NAM North America | V02445 | Gas Turbine | 193571 | C Inspection |  | 2028-04-01 | 2028-04-26
GT24 | NAM North America | 816517 | Gas Turbine | 193822 | Large Call-Out | 561549 | 2026-04-30 | 2026-05-18
GT24 | NAM North America | V02424 | Gas Turbine | 194159 | A Inspection | 562815 | 2026-10-17 | 2026-10-24
GT24 | NAM North America | 811853 | Gas Turbine | 194639 | A Inspection | 562264 | 2029-05-05 | 2029-05-11
GT24 | NAM North America | 811854 | Gas Turbine | 194640 | B Inspection | 562265 | 2029-05-12 | 2029-05-18
GT24 | NAM North America | 811855 | Gas Turbine | 194641 | C Inspection | 562266 | 2029-04-01 | 2029-04-26
GT24 | NAM North America | 811853 | Gas Turbine | 194642 | B Inspection | 562267 | 2030-04-06 | 2030-04-12
GT24 | NAM North America | 811854 | Gas Turbine | 194643 | A Inspection | 562268 | 2030-04-13 | 2030-04-19
GT24 | NAM North America | 811855 | Gas Turbine | 194644 | A Inspection | 562270 | 2030-05-04 | 2030-05-10
GT24 | NAM North America | V02444 | Gas Turbine | 196106 | Stand Alone Small Upgrade |  | 2027-03-01 | 2027-03-06
GT26 | MENA | G02669 | Gas Turbine | 103647 | C Inspection | 500025 | 2026-02-01 | 2026-04-01
GT26 | MENA | G02671 | Gas Turbine | 104984 | C Inspection | 500263 | 2029-09-30 | 2029-10-28
GT26 | MENA | G02672 | Gas Turbine | 105737 | C Inspection | 500266 | 2027-02-07 | 2027-04-07
GT26 | MENA | G02669 | Gas Turbine | 105808 | C Inspection | 500023 | 2027-06-12 | 2027-07-10
GT26 | Europe | 804973 | Gas Turbine | 106784 | C Inspection | 514016 | 2027-03-12 | 2027-05-08
GT26 | Europe | G02615 | Gas Turbine | 109821 | C Inspection | 503615 | 2028-10-16 | 2028-12-07
GT26 | Europe | G02655 | Gas Turbine | 115575 | C Inspection | 506623 | 2026-08-23 | 2026-11-18
GT26 | Europe | G02604 | Gas Turbine | 118794 | B Inspection | 503832 | 2026-05-01 | 2026-05-15
GT26 | Asia | G02624 | Gas Turbine | 120367 | C Inspection | 515291 | 2026-02-15 | 2026-04-15
GT26 | Europe | G02614 | Gas Turbine | 121287 | C Inspection | 503977 | 2026-06-12 | 2026-10-27
GT26 | Asia | G02625 | Gas Turbine | 122308 | C Inspection | 515293 | 2026-06-02 | 2026-07-26
GT26 | Asia | G26102 | Gas Turbine | 136657 | C Inspection | 524084 | 2026-06-05 | 2026-07-10
GT26 | Asia | G02682 | Gas Turbine | 137757 | C Inspection | 525089 | 2026-07-19 | 2026-08-17
GT26 | Asia | G02624 | Gas Turbine | 138410 | A Inspection | 525135 | 2027-04-03 | 2027-04-09
GT26 | Europe | G02613 | Gas Turbine | 138701 | A Inspection | 525249 | 2026-07-20 | 2026-08-20
GT26 | Europe | G02613 | Gas Turbine | 138703 | C Inspection | 525250 | 2027-08-20 | 2027-10-14
GT26 | Europe | G02679 | Gas Turbine | 143810 | A Inspection | 559679 | 2026-04-25 | 2026-05-08
GT26 | Europe | G02657 | Gas Turbine | 147159 | B Inspection | 530042 | 2026-04-07 | 2026-04-17
GT26 | Europe | G02647 | Gas Turbine | 147251 | C Inspection | 531712 | 2026-07-05 | 2026-08-31
GT26 | Europe | G02654 | Gas Turbine | 148668 | A Inspection | 538514 | 2026-11-06 | 2026-11-11
GT26 | Europe | G02654 | Gas Turbine | 148669 | C Inspection | 530893 | 2028-04-07 | 2028-06-05
GT26 | Europe | G02653 | Gas Turbine | 148675 | A Inspection |  | 2026-05-01 | 2026-05-06
GT26 | Europe | G02653 | Gas Turbine | 148676 | C Inspection | 530894 | 2027-05-07 | 2027-07-05
GT26 | Europe | G02628 | Gas Turbine | 152132 | A Inspection | 533193 | 2026-11-23 | 2026-11-27
GT26 | Europe | G02628 | Gas Turbine | 152133 | C Inspection | 533194 | 2028-01-10 | 2028-02-26
GT26 | Europe | G02686 | Gas Turbine | 152802 | C Inspection | 533732 | 2026-10-15 | 2026-11-18
GT26 | MENA | G02669 | Gas Turbine | 153157 | A Inspection | 534116 | 2026-04-05 | 2026-04-09
GT26 | MENA | G02672 | Gas Turbine | 153489 | A Inspection | 534272 | 2026-11-15 | 2026-11-19
GT26 | MENA | G02671 | Gas Turbine | 153492 | C Inspection | 534270 | 2026-02-09 | 2026-05-15
GT26 | MENA | G02672 | Gas Turbine | 153493 | B Inspection | 534271 | 2026-01-04 | 2026-01-13
GT26 | MENA | G02669 | Gas Turbine | 153495 | A Inspection | 535819 | 2027-10-03 | 2027-10-07
GT26 | MENA | G02669 | Gas Turbine | 153496 | B Inspection | 535816 | 2028-03-30 | 2028-04-09
GT26 | MENA | G02669 | Gas Turbine | 153497 | A Inspection | 535815 | 2029-06-25 | 2029-06-30
GT26 | MENA | G02669 | Gas Turbine | 153498 | A Inspection | 535808 | 2030-10-18 | 2030-10-23
GT26 | MENA | G02669 | Gas Turbine | 153870 | C Inspection | 534530 | 2026-10-20 | 2026-12-18
GT26 | MENA | G02671 | Gas Turbine | 153873 | C Inspection | 535812 | 2029-09-30 | 2029-10-28
GT26 | MENA | G02672 | Gas Turbine | 153878 | C Inspection | 534534 | 2027-10-20 | 2027-12-18
GT26 | Asia | G02621 | Gas Turbine | 155583 | A Inspection | 550744 | 2026-04-30 | 2026-05-05
GT26 | MENA | G02669 | Gas Turbine | 155711 | C Inspection | 535811 | 2030-01-02 | 2030-03-02
GT26 | MENA | G02672 | Gas Turbine | 155718 | A Inspection | 535814 | 2028-09-15 | 2028-09-19
GT26 | MENA | G02671 | Gas Turbine | 155719 | A Inspection | 535820 | 2026-11-22 | 2026-11-26
GT26 | MENA | G02671 | Gas Turbine | 155720 | B Inspection | 535818 | 2027-09-15 | 2027-09-24
GT26 | MENA | G02671 | Gas Turbine | 155721 | A Inspection | 535817 | 2028-03-20 | 2028-03-24
GT26 | MENA | G02671 | Gas Turbine | 155722 | A Inspection | 535809 | 2030-02-18 | 2030-02-22
GT26 | MENA | G02671 | Gas Turbine | 155723 | B Inspection | 535807 | 2030-12-13 | 2030-12-22
GT26 | MENA | G02672 | Gas Turbine | 155725 | B Inspection | 535813 | 2029-03-20 | 2029-03-29
GT26 | MENA | G02672 | Gas Turbine | 155726 | A Inspection | 535810 | 2030-01-21 | 2030-01-25
GT26 | Asia | G02611 | Gas Turbine | 156461 | A Inspection | 536211 | 2027-12-13 | 2027-12-18
GT26 | Europe | G02665 | Gas Turbine | 157505 | B Inspection | 537345 | 2027-03-30 | 2027-04-09
GT26 | Europe | G02665 | Gas Turbine | 157506 | C Inspection | 537108 | 2030-04-06 | 2030-07-25
GT26 | Europe | G02662 | Gas Turbine | 157642 | B Inspection | 537348 | 2027-05-08 | 2027-05-18
GT26 | Europe | G02662 | Gas Turbine | 157643 | C Inspection | 537215 | 2029-07-07 | 2029-10-25
GT26 | Europe | G02657 | Gas Turbine | 157645 | C Inspection | 537216 | 2028-07-15 | 2028-11-02
GT26 | Europe | G02656 | Gas Turbine | 157647 | B Inspection | 537347 | 2027-06-05 | 2027-06-14
GT26 | Europe | G02656 | Gas Turbine | 157648 | C Inspection | 537217 | 2029-03-03 | 2029-06-21
GT26 | Europe | G02677 | Gas Turbine | 158788 | B Inspection | 563365 | 2026-07-04 | 2026-07-26
GT26 | Europe | G02678 | Gas Turbine | 158789 | B Inspection |  | 2026-08-01 | 2026-08-15
GT26 | Europe | G02676 | Gas Turbine | 158791 | B Inspection |  | 2027-08-21 | 2027-08-30
GT26 | Europe | G02680 | Gas Turbine | 158792 | B Inspection |  | 2027-07-31 | 2027-08-09
GT26 | Europe | G02679 | Gas Turbine | 158793 | B Inspection | 563107 | 2028-04-29 | 2028-05-08
GT26 | Europe | G02679 | Gas Turbine | 158794 | C Inspection | 543942 | 2030-03-08 | 2030-06-26
GT26 | Europe | G02680 | Gas Turbine | 158795 | C Inspection | 543941 | 2029-04-07 | 2029-07-26
GT26 | Europe | G02677 | Gas Turbine | 158796 | C Inspection | 543939 | 2028-07-15 | 2028-11-02
GT26 | Europe | G02676 | Gas Turbine | 158800 | C Inspection | 543938 | 2030-07-06 | 2030-10-24
GT26 | Europe | G02678 | Gas Turbine | 158801 | C Inspection | 543937 | 2028-03-04 | 2028-06-22
GT26 | Asia | G02684 | Gas Turbine | 159556 | A Inspection | 538568 | 2027-06-03 | 2027-06-10
GT26 | Asia | G02684 | Gas Turbine | 159557 | B Inspection | 538569 | 2028-11-07 | 2028-11-14
GT26 | Europe | G02673 | Gas Turbine | 159667 | B Inspection | 538646 | 2027-05-10 | 2027-05-16
GT26 | Europe | G02674 | Gas Turbine | 159668 | B Inspection | 538647 | 2027-05-17 | 2027-05-23
GT26 | Europe | G02675 | Gas Turbine | 159669 | B Inspection | 538648 | 2027-05-24 | 2027-05-30
GT26 | Europe | G02675 | Gas Turbine | 159670 | A Inspection | 538649 | 2028-08-30 | 2028-09-02
GT26 | Europe | G02674 | Gas Turbine | 159671 | A Inspection | 538650 | 2028-08-25 | 2028-08-29
GT26 | Europe | G02673 | Gas Turbine | 159672 | A Inspection | 538651 | 2028-08-21 | 2028-08-24
GT26 | Asia | G02682 | Gas Turbine | 159830 | A Inspection | 538787 | 2026-04-04 | 2026-04-08
GT26 | Asia | G02640 | Gas Turbine | 160250 | A Inspection | 538942 | 2026-05-04 | 2026-05-13
GT26 | Asia | G26102 | Gas Turbine | 160448 | Borescope Inspection (BI) | 539125 | 2026-02-25 | 2026-02-26
GT26 | Asia | G26103 | Gas Turbine | 160455 | Borescope Inspection (BI) | 539132 | 2026-10-28 | 2026-10-30
GT26 | Europe | G02629 | Gas Turbine | 165281 | C Inspection | 542893 | 2028-05-08 | 2028-06-18
GT26 | Europe | G02626 | Gas Turbine | 165284 | C Inspection | 542894 | 2027-04-26 | 2027-06-06
GT26 | Asia | G26103 | Gas Turbine | 168310 | C Inspection | 545174 | 2026-02-21 | 2026-04-05
GT26 | Europe | G02673 | Gas Turbine | 169059 | C Inspection | 545791 | 2029-06-12 | 2029-08-08
GT26 | Europe | G02674 | Gas Turbine | 169062 | C Inspection | 545793 | 2029-06-23 | 2029-08-19
GT26 | Europe | G02675 | Gas Turbine | 169064 | C Inspection | 545794 | 2029-07-04 | 2029-08-30
GT26 | Asia | G26102 | Gas Turbine | 169213 | C Inspection |  | 2030-01-11 | 2030-02-05
GT26 | Asia | G02681 | Gas Turbine | 169462 | C Inspection | 552713 | 2029-05-01 | 2029-05-26
GT26 | Asia | G02683 | Gas Turbine | 169463 | C Inspection | 546044 | 2028-01-26 | 2028-02-20
GT26 | Asia | G02682 | Gas Turbine | 169466 | C Inspection | 552712 | 2030-12-09 | 2031-01-03
GT26 | Asia | G02621 | Gas Turbine | 169469 | C Inspection | 546045 | 2029-04-01 | 2029-04-30
GT26 | Asia | G02684 | Gas Turbine | 169470 | C Inspection | 552688 | 2030-05-13 | 2030-06-07
GT26 | Asia | G02621 | Gas Turbine | 169907 | B Inspection | 546288 | 2027-04-16 | 2027-06-04
GT26 | Asia | G02683 | Gas Turbine | 169937 | A Inspection | 546319 | 2026-09-01 | 2026-09-14
GT26 | Asia | G02683 | Gas Turbine | 169938 | B Inspection | 546320 | 2027-11-14 | 2027-11-27
GT26 | Asia | G02640 | Gas Turbine | 170015 | B Inspection | 546369 | 2028-08-01 | 2028-08-06
GT26 | Asia | G02640 | Gas Turbine | 170016 | A Inspection | 546370 | 2029-07-01 | 2029-07-04
GT26 | Asia | G02681 | Gas Turbine | 170106 | B Inspection | 554535 | 2027-07-31 | 2027-08-13
GT26 | Asia | G02682 | Gas Turbine | 170107 | A Inspection | 547426 | 2027-07-01 | 2027-07-08
GT26 | Europe | G02685 | Gas Turbine | 170351 | A Inspection | 553510 | 2026-04-26 | 2026-05-01
GT26 | Europe | G02614 | Gas Turbine | 175196 | C Inspection | 528368 | 2026-06-05 | 2026-07-20
GT26 | Europe | G02617 | Gas Turbine | 175223 | B Inspection | 549459 | 2026-02-23 | 2026-03-22
GT26 | Europe | G02617 | Gas Turbine | 175224 | A Inspection | 549460 | 2027-02-15 | 2027-02-24
GT26 | Europe | G02617 | Gas Turbine | 175225 | C Inspection | 549461 | 2028-08-14 | 2028-09-27
GT26 | Europe | G02618 | Gas Turbine | 176352 | A Inspection | 550357 | 2026-06-08 | 2026-06-16
GT26 | Europe | G02616 | Gas Turbine | 176711 | B Inspection | 550463 | 2026-06-17 | 2026-07-05
GT26 | Europe | G02627 | Gas Turbine | 176827 | C Inspection | 560114 | 2029-05-07 | 2029-06-16
GT26 | Asia | G02621 | Gas Turbine | 177974 | A Inspection | 551259 | 2028-04-01 | 2028-04-08
GT26 | Europe | G02653 | Gas Turbine | 180443 | C Inspection | 552533 | 2027-07-30 | 2027-10-28
GT26 | Europe | G02654 | Gas Turbine | 180529 | C Inspection | 552591 | 2030-07-08 | 2030-08-02
GT26 | Europe | G02614 | Gas Turbine | 180531 | C Inspection |  | 2030-09-27 | 2030-10-22
GT26 | Asia | G02681 | Gas Turbine | 180691 | A Inspection | 552711 | 2026-07-04 | 2026-07-09
GT26 | Europe | G02618 | Gas Turbine | 180742 | B Inspection | 554142 | 2028-01-17 | 2028-01-23
GT26 | Europe | G02618 | Gas Turbine | 180743 | C Inspection | 553877 | 2029-10-08 | 2029-11-25
GT26 | Europe | G02685 | Gas Turbine | 181869 | B Inspection | 553367 | 2027-03-01 | 2027-03-08
GT26 | Europe | G02685 | Gas Turbine | 181870 | C Inspection | 553368 | 2028-03-01 | 2028-04-04
GT26 | Europe | G02686 | Gas Turbine | 181872 | A Inspection | 553369 | 2027-03-22 | 2027-03-28
GT26 | Europe | G02686 | Gas Turbine | 181873 | B Inspection | 553370 | 2028-05-08 | 2028-05-14
GT26 | Europe | G02626 | Gas Turbine | 182046 | A Inspection | 554143 | 2026-02-06 | 2026-02-15
GT26 | Europe | G02627 | Gas Turbine | 182047 | A Inspection | 554144 | 2026-11-23 | 2026-11-29
GT26 | Europe | G02627 | Gas Turbine | 182048 | B Inspection | 554146 | 2027-03-22 | 2027-03-28
GT26 | Europe | G02629 | Gas Turbine | 182049 | B Inspection | 554130 | 2026-05-18 | 2026-05-24
GT26 | Europe | G02629 | Gas Turbine | 182051 | A Inspection | 554145 | 2027-02-22 | 2027-02-28
GT26 | Europe | G02626 | Gas Turbine | 182054 | A Inspection | 554147 | 2028-05-01 | 2028-05-07
GT26 | Europe | G02627 | Gas Turbine | 182055 | A Inspection | 554148 | 2028-08-28 | 2028-09-02
GT26 | Europe | G02685 | Gas Turbine | 182251 | A Inspection | 553647 | 2027-10-01 | 2027-10-07
GT26 | Europe | G02615 | Gas Turbine | 183725 | C Inspection |  | 2026-01-16 | 2026-02-10
GT26 | Europe | G02608 | Gas Turbine | 183780 | A Inspection | 563564 | 2027-05-27 | 2027-05-31
GT26 | Europe | G02610 | Gas Turbine | 183781 | A Inspection | 563565 | 2027-05-31 | 2027-06-04
GT26 | Europe | G02608 | Gas Turbine | 183782 | B Inspection |  | 2028-03-03 | 2028-03-09
GT26 | Europe | G02610 | Gas Turbine | 183783 | B Inspection |  | 2028-03-10 | 2028-03-16
GT26 | Europe | G02608 | Gas Turbine | 183784 | A Inspection |  | 2029-05-04 | 2029-05-08
GT26 | Europe | G02610 | Gas Turbine | 183785 | A Inspection |  | 2029-05-11 | 2029-05-15
GT26 | MENA | G02669 | Gas Turbine | 184184 | Stand Alone Small Upgrade | 554825 | 2026-11-22 | 2026-11-28
GT26 | MENA | G02671 | Gas Turbine | 184186 | Stand Alone Small Upgrade | 555737 | 2026-11-22 | 2026-11-26
GT26 | MENA | G02672 | Gas Turbine | 184187 | Stand Alone Small Upgrade | 555939 | 2026-06-10 | 2026-06-14
GT26 | Asia | G26102 | Gas Turbine | 184196 | A Inspection | 556771 | 2027-12-01 | 2027-12-20
GT26 | Asia | G26102 | Gas Turbine | 184197 | B Inspection | 556772 | 2028-12-01 | 2028-12-20
GT26 | Asia | G26103 | Gas Turbine | 184198 | A Inspection | 556810 | 2028-02-15 | 2028-03-05
GT26 | Asia | G02621 | Gas Turbine | 186195 | A Inspection | 556285 | 2026-05-08 | 2026-05-15
GT26 | Europe | G02653 | Gas Turbine | 186651 | A Inspection | 559773 | 2026-10-08 | 2026-10-13
GT26 | Europe | G02653 | Gas Turbine | 186652 | A Inspection |  | 2028-08-11 | 2028-08-18
GT26 | Europe | G02655 | Gas Turbine | 186653 | A Inspection | 560401 | 2027-09-23 | 2027-09-30
GT26 | Europe | G02655 | Gas Turbine | 186654 | B Inspection |  | 2028-09-22 | 2028-09-29
GT26 | Europe | 804973 | Gas Turbine | 186655 | A Inspection |  | 2028-07-23 | 2028-07-30
GT26 | Europe | G02614 | Gas Turbine | 186812 | A Inspection |  | 2027-08-06 | 2027-08-20
GT26 | Europe | G02614 | Gas Turbine | 186813 | B Inspection |  | 2028-08-04 | 2028-08-18
GT26 | Europe | G02614 | Gas Turbine | 186814 | A Inspection |  | 2029-08-10 | 2029-08-24
GT26 | Asia | G02681 | Gas Turbine | 187036 | A Inspection | 556808 | 2028-07-01 | 2028-07-05
GT26 | Asia | G02682 | Gas Turbine | 187037 | B Inspection | 556809 | 2028-07-10 | 2028-07-22
GT26 | Asia | G02682 | Gas Turbine | 187038 | A Inspection | 558874 | 2029-07-01 | 2029-07-05
GT26 | Asia | G02681 | Gas Turbine | 187042 | C Inspection | 556813 | 2029-03-03 | 2029-03-28
GT26 | Asia | G02683 | Gas Turbine | 187044 | C Inspection | 556814 | 2028-10-26 | 2028-11-20
GT26 | Europe | G02613 | Gas Turbine | 190572 | Large Call-Out |  | 2029-04-15 | 2029-08-15
GT26 | Europe | G02626 | Gas Turbine | 191769 | A Inspection | 560116 | 2029-04-02 | 2029-04-07
GT26 | Europe | G02629 | Gas Turbine | 191773 | A Inspection | 560113 | 2029-07-02 | 2029-07-07
GT26 | Europe | G02629 | Gas Turbine | 191806 | C Inspection | 560130 | 2028-05-22 | 2028-07-02
GT26 | Europe | G02608 | Gas Turbine | 191842 | Large Call-Out | 560365 | 2026-02-26 | 2026-05-17
GT26 | Europe | 804973 | Gas Turbine | 192026 | B Inspection | 560278 | 2029-07-23 | 2029-07-30
GT26 | Europe | 804973 | Gas Turbine | 192027 | A Inspection | 560279 | 2030-07-23 | 2030-07-30
GT26 | Europe | G02653 | Gas Turbine | 192028 | B Inspection |  | 2029-09-11 | 2029-09-18
GT26 | Europe | G02653 | Gas Turbine | 192029 | A Inspection |  | 2030-09-11 | 2030-09-18
GT26 | Europe | G02655 | Gas Turbine | 192031 | A Inspection |  | 2029-09-22 | 2029-09-29
GT26 | Europe | G02654 | Gas Turbine | 192032 | A Inspection |  | 2029-06-23 | 2029-06-30
GT26 | Europe | G02654 | Gas Turbine | 192033 | B Inspection |  | 2030-06-23 | 2030-06-30
GT26 | Europe | G02615 | Gas Turbine | 192258 | A Inspection | 562339 | 2026-06-29 | 2026-07-03
GT26 | Europe | G02610 | Gas Turbine | 193425 | Large Call-Out | 561368 | 2026-05-04 | 2026-05-28
H35 | NAM North America | GG10644 | Generator | 115491 | Minor Inspection |  | 2026-03-16 | 2026-03-22
H35 | NAM North America | GG10643 | Generator | 116913 | Minor Inspection |  | 2026-03-16 | 2026-03-22
H35 | Latin America | 761X210 | Generator | 146297 | Major Inspection (Robotic) | 503019 | 2026-01-28 | 2026-03-01
H35 | NAM North America | GG10782 | Generator | 158222 | Major Inspection (Robotic) | 539479 | 2026-05-18 | 2026-05-24
H35 | NAM North America | GG10783 | Generator | 158225 | Major Inspection (Robotic) | 539480 | 2026-05-21 | 2026-05-28
H35 | NAM North America | GG10784 | Generator | 158227 | Major Inspection (Robotic) | 539863 | 2026-05-25 | 2026-05-30
H35 | NAM North America | GG10787 | Generator | 159184 | Minor Inspection | 538263 | 2028-10-28 | 2028-11-15
H35 | NAM North America | GG10785 | Generator | 159186 | Minor Inspection | 538264 | 2029-11-03 | 2029-11-23
H35 | NAM North America | GG10611 | Generator | 159213 | Minor Inspection | 528945 | 2026-10-14 | 2026-10-31
H35 | NAM North America | GG10645 | Generator | 162800 | Major Inspection (Robotic) | 541046 | 2029-04-17 | 2029-05-18
H35 | NAM North America | GG10646 | Generator | 162801 | Major Inspection (Robotic) | 541047 | 2029-04-17 | 2029-05-18
H35 | NAM North America | 761X211 | Generator | 162996 | Minor Inspection | 502807 | 2027-03-12 | 2027-03-28
H35 | NAM North America | 761X212 | Generator | 162997 | Minor Inspection | 541151 | 2028-10-01 | 2028-10-29
H35 | NAM North America | 761X213 | Generator | 163007 | Major Inspection (Robotic) | 541161 | 2027-03-08 | 2027-05-05
H35 | NAM North America | 761X214 | Generator | 163008 | Major Inspection (Robotic) | 541162 | 2027-10-20 | 2027-11-17
H35 | NAM North America | GG10556 | Generator | 166951 | Minor Inspection | 531487 | 2026-12-03 | 2026-12-20
H35 | NAM North America | GG10646 | Generator | 169336 | Minor Inspection | 545977 | 2026-04-01 | 2026-04-06
H35 | NAM North America | GG10611 | Generator | 173091 | Major Inspection (Robotic) | 548103 | 2030-05-09 | 2030-06-06
H35 | NAM North America | GG10610 | Generator | 173093 | Major Inspection (Robotic) | 548104 | 2029-11-13 | 2029-12-11
H35 | NAM North America | SG10222 | Generator | 175535 | Major Inspection (Robotic) | 545806 | 2027-03-20 | 2027-05-18
H35 | Latin America | 761X210 | Generator | 176087 | Minor Inspection | 550043 | 2030-03-25 | 2030-04-08
H35 | NAM North America | GG10643 | Generator | 176695 | Major Inspection (Robotic) |  | 2028-03-06 | 2028-04-06
H35 | NAM North America | GG10643 | Generator | 176946 | Major Inspection (Robotic) | 546844 | 2029-03-06 | 2029-04-06
H35 | NAM North America | GG10644 | Generator | 176949 | Major Inspection (Robotic) | 549449 | 2029-03-06 | 2029-04-06
H35 | MENA | GG10812 | Generator | 179414 | Minor Inspection | 551983 | 2030-03-14 | 2030-04-04
H35 | NAM North America | GG10786 | Generator | 179440 | Minor Inspection | 552007 | 2029-04-05 | 2029-04-25
H35 | NAM North America | GG10645 | Generator | 180518 | Minor Inspection |  | 2026-03-02 | 2026-03-06
H35 | NAM North America | GG10646 | Generator | 180519 | Minor Inspection |  | 2026-03-02 | 2026-03-08
H35 | MENA | GG10810 | Generator | 182181 | Minor Inspection | 553612 | 2029-03-14 | 2029-04-11
H35 | MENA | GG10811 | Generator | 182183 | Minor Inspection | 553613 | 2030-02-17 | 2030-03-10
H35 | NAM North America | SG10212 | Generator | 183468 | Major Inspection (Robotic) | 554406 | 2026-03-01 | 2026-05-08
H35 | NAM North America | GG10627 | Generator | 186871 | Major Inspection (Robotic) | 556724 | 2027-09-11 | 2027-10-14
H35 | MENA | GG10810 | Generator | 193530 | Minor Inspection | 561045 | 2028-12-08 | 2028-12-30
H35 | NAM North America | GG10844 | Generator | 194943 | Minor Inspection | 562529 | 2028-04-08 | 2028-05-14
H35 | NAM North America | GG10844 | Generator | 194944 | Minor Inspection | 562528 | 2028-04-08 | 2028-05-14
H35 | Asia | GG10845 | Generator | 195236 | Minor Inspection | 562736 | 2029-01-01 | 2029-01-17
H53 | MENA | GG10694 | Generator | 149765 | Minor Inspection | 531671 | 2026-04-01 | 2026-04-10
H53 | Latin America | SG10239 | Generator | 157409 | Major Inspection (Robotic) | 534055 | 2026-01-11 | 2026-02-14
H53 | Latin America | GG10651 | Generator | 157410 | Major Inspection (Robotic) | 534720 | 2026-01-10 | 2026-02-11
H53 | Latin America | GG10652 | Generator | 157411 | Major Inspection (Robotic) | 534721 | 2026-01-10 | 2026-02-16
H53 | MENA | GG10402 | Generator | 158977 | Minor Inspection | 538152 | 2027-10-04 | 2027-11-02
H53 | MENA | GG10423 | Generator | 159014 | Minor Inspection | 500415 | 2027-02-01 | 2027-03-02
H53 | Latin America | GG10664 | Generator | 162583 | Major Inspection (Robotic) | 540913 | 2028-11-04 | 2028-12-07
H53 | Latin America | GG10652 | Generator | 162589 | Minor Inspection | 540916 | 2029-01-10 | 2029-02-02
H53 | Latin America | GG10651 | Generator | 162591 | Minor Inspection | 540917 | 2029-01-10 | 2029-02-02
H53 | Latin America | GG10696 | Generator | 162773 | Minor Inspection | 541024 | 2027-01-16 | 2027-01-30
H53 | Latin America | GG10697 | Generator | 162774 | Minor Inspection | 541025 | 2027-02-12 | 2027-02-26
H53 | Latin America | GG10665 | Generator | 168024 | Major Inspection (Robotic) | 544935 | 2028-11-04 | 2028-12-07
H53 | Latin America | SG10246 | Generator | 168025 | Major Inspection (Robotic) | 544936 | 2028-11-04 | 2028-12-07
H53 | MENA | GG10695 | Generator | 169401 | Major Inspection (Rotor Out) | 546020 | 2026-11-08 | 2026-11-25
H53 | MENA | GG10694 | Generator | 169402 | Minor Inspection | 546021 | 2027-10-15 | 2027-10-19
H53 | MENA | GG10824 | Generator | 170814 | Minor Inspection | 546781 | 2026-01-02 | 2026-02-04
H53 | MENA | SG10270 | Generator | 170816 | Minor Inspection | 546782 | 2026-10-03 | 2026-10-18
H53 | MENA | GG10738 | Generator | 170818 | Minor Inspection | 546783 | 2026-10-01 | 2026-10-22
H53 | MENA | GG10738 | Generator | 172586 | Major Inspection (Robotic) | 547834 | 2030-08-02 | 2030-08-30
H53 | Latin America | GG10696 | Generator | 175966 | Major Inspection (Robotic) | 549947 | 2029-05-13 | 2029-06-10
H53 | Latin America | GG10697 | Generator | 175967 | Major Inspection (Robotic) | 549948 | 2030-01-16 | 2030-02-13
H53 | MENA | GG10837 | Generator | 179446 | Minor Inspection | 552012 | 2029-09-30 | 2029-10-14
H53 | MENA | SG10257 | Generator | 180651 | Minor Inspection | 552672 | 2028-10-29 | 2028-11-03
H53 | MENA | SG10233 | Generator | 180847 | Minor Inspection | 552827 | 2028-11-29 | 2028-12-04
H53 | MENA | SG10234 | Generator | 180848 | Minor Inspection | 552828 | 2029-03-24 | 2029-03-29
H53 | MENA | GG10737 | Generator | 182256 | Major Inspection (Stator Rewind) | 553650 | 2027-04-30 | 2027-06-28
H53 | Latin America | GG10660 | Generator | 184584 | Minor Inspection | 555125 | 2028-01-28 | 2028-02-25
H53 | Latin America | GG10661 | Generator | 184588 | Minor Inspection | 555127 | 2028-01-10 | 2028-02-04
H53 | Latin America | SG10245 | Generator | 184589 | Minor Inspection | 555129 | 2028-01-10 | 2028-02-04
H53 | Latin America | SG10239 | Generator | 187123 | Minor Inspection | 556898 | 2029-01-14 | 2029-02-06
H53 | MENA | GG10694 | Generator | 193495 | Stand Alone Small Upgrade | 561293 | 2026-11-30 | 2026-12-04
H53 | MENA | GG10695 | Generator | 193498 | Stand Alone Small Upgrade | 561297 | 2026-11-30 | 2026-12-05
H53 | MENA | SG10234 | Generator | 193566 | Major Inspection (Stator Rewind) | 561319 | 2028-01-09 | 2028-03-30
H65 | Latin America | GG10614 | Generator | 136590 | Minor Inspection | 524024 | 2028-09-11 | 2028-09-16
H65 | Latin America | GG10615 | Generator | 136591 | Minor Inspection | 524025 | 2026-04-13 | 2026-04-17
H65 | Latin America | GG10616 | Generator | 136592 | Minor Inspection | 524026 | 2026-04-22 | 2026-04-25
H65 | NAM North America | GG10700 | Generator | 140974 | Minor Inspection | 526443 | 2026-10-22 | 2026-11-23
H65 | NAM North America | GG10487 | Generator | 150823 | Minor Inspection | 532313 | 2030-10-08 | 2030-11-04
H65 | NAM North America | GG10486 | Generator | 150839 | Major Inspection (Robotic) | 532319 | 2026-10-03 | 2026-11-06
H65 | NAM North America | GG10699 | Generator | 154807 | Minor Inspection | 535056 | 2026-04-01 | 2026-05-09
H65 | Asia | GG10707 | Generator | 156162 | Major Inspection (Rotor Out) | 531472 | 2027-10-01 | 2027-11-09
H65 | Asia | GG10707 | Generator | 158584 | Minor Inspection | 537923 | 2030-10-01 | 2030-10-14
H65 | Latin America | GG10857 | Generator | 159259 | Minor Inspection | 538252 | 2030-05-14 | 2030-05-28
H65 | Latin America | GG10838 | Generator | 159260 | Minor Inspection | 538257 | 2030-05-14 | 2030-05-28
H65 | NAM North America | GG10468 | Generator | 163086 | Major Inspection (Robotic) | 541206 | 2028-04-18 | 2028-06-04
H65 | NAM North America | GG10470 | Generator | 163087 | Major Inspection (Robotic) | 541207 | 2028-04-18 | 2028-06-04
H65 | NAM North America | GG10746 | Generator | 163092 | Minor Inspection | 541211 | 2027-10-24 | 2027-11-23
H65 | NAM North America | GG10730 | Generator | 163207 | Minor Inspection | 534219 | 2027-03-08 | 2027-04-08
H65 | NAM North America | GG10731 | Generator | 163208 | Minor Inspection | 541307 | 2027-03-08 | 2027-04-08
H65 | NAM North America | GG10730 | Generator | 163210 | Major Inspection (Robotic) | 541308 | 2030-12-25 | 2031-01-22
H65 | NAM North America | GG10703 | Generator | 165734 | Minor Inspection | 531779 | 2026-02-16 | 2026-03-24
H65 | NAM North America | GG10704 | Generator | 165735 | Minor Inspection | 539683 | 2026-02-16 | 2026-03-28
H65 | NAM North America | GG10745 | Generator | 171968 | Minor Inspection | 547351 | 2026-10-12 | 2026-11-04
H65 | NAM North America | GG10745 | Generator | 171970 | Minor Inspection | 547352 | 2027-02-20 | 2027-03-15
H65 | NAM North America | GG10590 | Generator | 173047 | Major Inspection (Robotic) | 548070 | 2027-03-05 | 2027-05-03
H65 | NAM North America | GG10590 | Generator | 173048 | Major Inspection (Robotic) | 531637 | 2027-03-20 | 2027-05-18
H65 | NAM North America | GG10746 | Generator | 175985 | Major Inspection (Robotic) | 549961 | 2030-11-17 | 2030-12-15
H65 | NAM North America | GG10613 | Generator | 177191 | Major Inspection (Robotic) | 544849 | 2028-04-03 | 2028-05-19
H65 | NAM North America | GG10612 | Generator | 177192 | Major Inspection (Robotic) | 544850 | 2028-04-03 | 2028-05-19
H65 | NAM North America | SG10268 | Generator | 177474 | Minor Inspection | 550939 | 2027-03-12 | 2027-04-15
H65 | NAM North America | SG10268 | Generator | 177478 | Minor Inspection | 550941 | 2027-10-24 | 2027-11-24
H65 | NAM North America | GG10535 | Generator | 184992 | Major Inspection (Robotic) | 541548 | 2026-03-01 | 2026-04-15
H65 | NAM North America | GG10471 | Generator | 190671 | Major Inspection (Robotic) | 559335 | 2027-11-29 | 2028-01-12
H65 | NAM North America | GG10468 | Generator | 193433 | Large Call-Out | 561191 | 2026-04-04 | 2026-04-20
H78 | Europe | GG10828 | Generator | 176672 | Major Inspection (Robotic) | 553035 | 2028-06-04 | 2028-06-16
H78 | Europe | GG10859 | Generator | 196436 | Minor Inspection | 563685 | 2027-09-06 | 2027-09-17
H84 | MENA | GG10538 | Generator | 141513 | Major Inspection (Robotic) | 502373 | 2026-02-01 | 2026-08-31
H84 | MENA | GG10537 | Generator | 141514 | Major Inspection (Rotor Out) | 502374 | 2026-02-07 | 2026-04-20
H84 | MENA | GG10608 | Generator | 152601 | Major Inspection (Rotor Out) | 523705 | 2026-01-08 | 2026-02-21
H84 | NAM North America | GG10478 | Generator | 153567 | Major Inspection (Robotic) | 531749 | 2026-03-16 | 2026-05-23
H84 | NAM North America | SG10199 | Generator | 157633 | Major Inspection (Robotic) | 537204 | 2027-03-04 | 2027-03-20
H84 | MENA | GG10609 | Generator | 158949 | Major Inspection (Robotic) | 533498 | 2027-01-14 | 2027-02-22
H84 | MENA | GG10608 | Generator | 158951 | Minor Inspection | 538136 | 2029-12-01 | 2029-12-29
H84 | MENA | GG10607 | Generator | 158954 | Minor Inspection | 538137 | 2028-12-01 | 2028-12-29
H84 | MENA | GG10688 | Generator | 159564 | Minor Inspection | 538575 | 2026-11-17 | 2026-12-11
H84 | Asia | GG10750 | Generator | 160843 | Minor Inspection | 539423 | 2026-01-21 | 2026-01-25
H84 | Asia | GG10691 | Generator | 160955 | Minor Inspection | 539538 | 2026-08-01 | 2026-08-06
H84 | MENA | GG10609 | Generator | 162696 | Minor Inspection | 540970 | 2030-12-03 | 2030-12-31
H84 | MENA | GG10567 | Generator | 162813 | Minor Inspection | 541057 | 2028-10-01 | 2028-10-30
H84 | MENA | GG10566 | Generator | 162815 | Minor Inspection | 541058 | 2028-10-31 | 2028-11-29
H84 | MENA | GG10560 | Generator | 162825 | Minor Inspection | 541060 | 2028-09-01 | 2028-09-30
H84 | MENA | GG10561 | Generator | 162827 | Minor Inspection | 541061 | 2028-09-01 | 2028-09-30
H84 | MENA | GG10538 | Generator | 162832 | Minor Inspection | 537571 | 2026-04-16 | 2026-04-23
H84 | MENA | GG10537 | Generator | 162833 | Minor Inspection | 540551 | 2026-11-05 | 2026-11-12
H84 | MENA | GG10538 | Generator | 162834 | Minor Inspection | 541063 | 2030-02-01 | 2030-02-22
H84 | MENA | GG10537 | Generator | 162835 | Minor Inspection | 541064 | 2030-02-01 | 2030-02-22
H84 | NAM North America | GG10705 | Generator | 163045 | Minor Inspection | 531581 | 2026-03-09 | 2026-04-10
H84 | NAM North America | GG10705 | Generator | 163048 | Major Inspection (Robotic) | 541177 | 2030-05-14 | 2030-06-11
H84 | NAM North America | GG10625 | Generator | 163057 | Major Inspection (Robotic) | 541180 | 2027-09-22 | 2027-10-20
H84 | NAM North America | GG10532 | Generator | 163102 | Major Inspection (Robotic) | 502953 | 2026-09-12 | 2026-12-08
H84 | NAM North America | GG10533 | Generator | 163103 | Major Inspection (Robotic) | 541219 | 2027-03-01 | 2027-04-30
H84 | MENA | GG10892 | Generator | 169548 | Minor Inspection | 546087 | 2030-04-30 | 2030-05-14
H84 | MENA | GG10875 | Generator | 169622 | Minor Inspection | 546127 | 2030-04-30 | 2030-05-14
H84 | MENA | GG10892 | Generator | 169661 | Minor Inspection | 546140 | 2030-04-30 | 2030-05-14
H84 | MENA | GG10689 | Generator | 176173 | Major Inspection (Robotic) | 550077 | 2029-12-08 | 2030-01-05
H84 | MENA | GG10690 | Generator | 176177 | Major Inspection (Robotic) | 550078 | 2030-11-14 | 2030-12-12
H84 | MENA | GG10689 | Generator | 176593 | Minor Inspection | 550360 | 2027-11-16 | 2027-12-10
H84 | MENA | GG10690 | Generator | 176594 | Minor Inspection | 550361 | 2028-11-15 | 2028-12-09
H84 | NAM North America | SG10227 | Generator | 177196 | Major Inspection (Robotic) | 550814 | 2028-04-03 | 2028-05-19
H84 | NAM North America | GG10477 | Generator | 185447 | Minor Inspection | 555755 | 2027-09-13 | 2027-10-08
H84 | NAM North America | GG10478 | Generator | 185448 | Minor Inspection | 555756 | 2029-03-19 | 2029-04-13
H84 | NAM North America | GG10479 | Generator | 185449 | Minor Inspection | 555757 | 2028-09-11 | 2028-10-06
H84 | NAM North America | GG10479 | Generator | 185452 | Minor Inspection | 555752 | 2028-09-11 | 2028-10-06
H84 | NAM North America | GG10478 | Generator | 185453 | Minor Inspection | 550719 | 2029-03-19 | 2029-04-13
H84 | NAM North America | GG10477 | Generator | 185454 | Minor Inspection | 549435 | 2028-03-06 | 2028-03-31
H84 | NAM North America | SG10266 | Generator | 186185 | Minor Inspection | 552378 | 2027-03-08 | 2027-04-08
H84 | Asia | GG10750 | Generator | 187142 | Minor Inspection | 551948 | 2029-12-31 | 2030-01-14
H84 | Asia | GG10691 | Generator | 188715 | Minor Inspection | 552229 | 2029-01-24 | 2029-02-07
H84 | NAM North America | SG10227 | Generator | 193122 | Major Inspection (Robotic) | 544877 | 2028-04-03 | 2028-05-30
H84 | MENA | GG10567 | Generator | 194034 | Minor Inspection | 540516 | 2027-02-01 | 2027-02-13
H84 | NAM North America | GG10477 | Generator | 194094 | Major Inspection (Robotic) |  | 2030-09-02 | 2030-11-27
H84 | NAM North America | GG10477 | Generator | 194095 | Major Inspection (Robotic) | 561797 | 2030-09-02 | 2030-11-27
H84 | MENA | GG10566 | Generator | 194714 | Minor Inspection | 540515 | 2027-03-15 | 2027-03-27
H84 | NAM North America | GG10866 | Generator | 194907 | Minor Inspection | 562492 | 2030-09-02 | 2030-09-16
HRSG | MENA | 299283-HRSG1 | HRSG | 105970 | Minor Inspection | 502414 | 2028-09-14 | 2028-09-20
HRSG | MENA | 299284-HRSG1 | HRSG | 105971 | Major Inspection (MI) | 502415 | 2028-03-01 | 2028-03-30
HRSG | NAM North America | 299435HRSG | HRSG | 112364 | Minor Inspection | 510277 | 2026-10-01 | 2026-10-15
HRSG | NAM North America | 299434HRSG | HRSG | 146879 | Major Inspection (MI) | 540741 | 2026-10-01 | 2026-10-31
HRSG | NAM North America | 299435HRSG | HRSG | 146880 | Major Inspection (MI) |  | 2027-10-01 | 2027-10-01
HRSG | MENA | 298460-HRSG | HRSG | 151396 | Major Inspection (MI) |  | 2027-09-01 | 2027-09-01
HRSG | MENA | 299307-HRSG | HRSG | 155343 | Minor Inspection | 535718 | 2026-01-24 | 2026-02-02
HRSG | MENA | 299309-HRSG | HRSG | 155344 | Minor Inspection | 542125 | 2027-03-03 | 2027-03-08
HRSG | MENA | 299306-HRSG | HRSG | 155346 | Minor Inspection | 552075 | 2026-12-01 | 2026-12-15
HRSG | MENA | 299308-HRSG | HRSG | 155347 | Minor Inspection |  | 2027-02-01 | 2027-02-10
HRSG | MENA | 299298-HRSG | HRSG | 155349 | Minor Inspection | 546765 | 2027-05-28 | 2027-06-02
HRSG | MENA | 299301-HRSG | HRSG | 155350 | Minor Inspection | 546767 | 2028-02-17 | 2028-03-07
HRSG | MENA | 299300-HRSG | HRSG | 155352 | Minor Inspection | 546227 | 2028-01-17 | 2028-02-05
HRSG | MENA | 299299-HRSG | HRSG | 155353 | Minor Inspection | 546228 | 2028-06-01 | 2028-06-06
HRSG | MENA | 299296-HRSG1 | HRSG | 155354 | Minor Inspection | 546345 | 2029-10-15 | 2029-10-20
HRSG | MENA | 299297-HRSG1 | HRSG | 155355 | Major Inspection (MI) | 544297 | 2028-02-01 | 2028-03-01
HRSG | MENA | 299277-HRSG2 | HRSG | 155356 | Minor Inspection | 560597 | 2029-10-05 | 2029-10-10
HRSG | MENA | 299279-HRSG2 | HRSG | 155358 | Minor Inspection | 560598 | 2030-10-05 | 2030-10-10
HRSG | MENA | 299278-HRSG2 | HRSG | 155359 | Minor Inspection | 560599 | 2029-11-05 | 2029-11-10
HRSG | MENA | 299280-HRSG | HRSG | 155363 | Minor Inspection | 546342 | 2030-11-07 | 2030-11-12
HRSG | NAM North America | HR299404 | HRSG | 158726 | Minor Inspection |  | 2028-04-01 | 2028-04-06
HRSG | NAM North America | HR299405 | HRSG | 158730 | Minor Inspection |  | 2028-04-30 | 2028-05-14
HRSG | NAM North America | HR299406 | HRSG | 158732 | Minor Inspection |  | 2029-04-01 | 2029-04-06
HRSG | MENA | 299296-HRSG1 | HRSG | 159020 | Major Inspection (MI) |  | 2030-03-29 | 2030-04-26
HRSG | MENA | 299297-HRSG1 | HRSG | 159023 | Major Inspection (MI) |  | 2030-04-27 | 2030-05-25
HRSG | NAM North America | 299434HRSG | HRSG | 162356 | Minor Inspection | 540746 | 2027-10-04 | 2027-10-11
HRSG | NAM North America | 299604-HRSG | HRSG | 163107 | Major Inspection (MI) | 562233 | 2029-03-01 | 2029-05-29
HRSG | NAM North America | 299021-HRSG | HRSG | 165159 | Major Inspection (MI) |  | 2029-04-20 | 2029-06-04
HRSG | MENA | 299306-HRSG | HRSG | 169002 | Stand Alone Small Upgrade | 545743 | 2026-02-01 | 2026-02-10
HRSG | MENA | 299307-HRSG | HRSG | 169003 | Stand Alone Small Upgrade | 545744 | 2026-03-01 | 2026-03-10
HRSG | MENA | 299308-HRSG | HRSG | 169004 | Stand Alone Small Upgrade | 545745 | 2026-02-01 | 2026-02-10
HRSG | MENA | 299309-HRSG | HRSG | 169005 | Stand Alone Small Upgrade | 545746 | 2026-03-01 | 2026-03-10
HRSG | MENA | 299301-HRSG | HRSG | 169859 | Borescope Inspection (BI) | 546241 | 2027-02-22 | 2027-02-24
HRSG | NAM North America | 299435HRSG | HRSG | 172043 | Minor Inspection | 547419 | 2027-10-04 | 2027-10-18
HRSG | NAM North America | 299434HRSG | HRSG | 175900 | Major Inspection (MI) |  | 2029-10-01 | 2029-10-28
HRSG | NAM North America | 299435HRSG | HRSG | 175901 | Major Inspection (MI) |  | 2030-10-01 | 2030-10-31
HRSG | NAM North America | 803769-HRSG | HRSG | 182285 | Major Inspection (MI) |  | 2027-01-11 | 2027-02-01
HRSG | NAM North America | 803770-HRSG | HRSG | 182286 | Minor Inspection |  | 2027-12-04 | 2027-12-25
HRSG | NAM North America | 803769-HRSG | HRSG | 182288 | Major Inspection (MI) |  | 2028-07-27 | 2028-08-24
HRSG | NAM North America | 803770-HRSG | HRSG | 182291 | Minor Inspection |  | 2029-09-18 | 2029-09-23
HRSG | NAM North America | 803769-HRSG | HRSG | 182293 | Major Inspection (MI) |  | 2030-05-09 | 2030-06-06
HRSG | MENA | 299306-HRSG | HRSG | 183631 | Major Inspection (MI) | 556255 | 2028-11-01 | 2028-11-28
HRSG | MENA | 298802-HRSG | HRSG | 190937 | Stand Alone Large Upgrade | 559564 | 2026-11-15 | 2027-01-08
HRSG | MENA | 298803-HRSG | HRSG | 190938 | Stand Alone Large Upgrade | 559531 | 2027-11-15 | 2028-01-08
HRSG | MENA | 298801-HRSG | HRSG | 190939 | Stand Alone Large Upgrade | 559563 | 2026-11-15 | 2027-01-08
HRSG | MENA | 298804-HRSG | HRSG | 190940 | Stand Alone Large Upgrade | 559532 | 2027-11-15 | 2028-01-08
HRSG | MENA | 299299-HRSG | HRSG | 193214 | Minor Inspection | 561014 | 2027-09-15 | 2027-09-20
HRSG | MENA | 298460-HRSG | HRSG | 193369 | Minor Inspection | 561142 | 2029-01-20 | 2029-02-03
HRSG | MENA | 298459-HRSG | HRSG | 193370 | Minor Inspection | 561143 | 2029-10-05 | 2029-10-19
HRSG | Europe | 299268-HRSG | HRSG | 195475 | Minor Inspection | 547806 | 2028-09-06 | 2028-09-12
HRSG | Europe | 299268-HRSG | HRSG | 195476 | Major Inspection (MI) | 547807 | 2030-12-15 | 2031-01-12
HRSG | MENA | 299278-HRSG2 | HRSG | 195657 | Minor Inspection | 563039 | 2028-07-25 | 2028-08-08
HRSG | MENA | 299277-HRSG2 | HRSG | 195663 | Minor Inspection | 563040 | 2028-10-03 | 2028-10-17
HRSG | MENA | 299280-HRSG | HRSG | 195664 | Minor Inspection | 538162 | 2029-12-02 | 2029-12-31
HRSG | MENA | 299279-HRSG2 | HRSG | 195667 | Minor Inspection | 563041 | 2030-01-08 | 2030-01-22
HRSG | MENA | 299297-HRSG1 | HRSG | 195731 | Minor Inspection | 500122 | 2029-02-03 | 2029-03-04
HRSG | MENA | 299283-HRSG1 | HRSG | 195732 | Minor Inspection |  | 2030-11-10 | 2030-11-15
HRSG | NAM North America | 299605-HRSG | HRSG | 196489 | Major Inspection (MI) | 563734 | 2029-09-01 | 2029-10-26
JISALT265 | Europe | 819408 | Generator | 165819 | Minor Inspection | 510499 | 2026-02-02 | 2026-02-14
L6 | NAM North America | 170X484 | Steam Turbine | 193245 | Major Inspection (MI) | 561028 | 2028-09-11 | 2028-11-09
L6 | NAM North America | 170X484 | Steam Turbine | 195217 | Major Inspection (MI) | 562718 | 2028-09-11 | 2028-11-28
M501F | Latin America | 980038 | Gas Turbine | 148580 | Hot Gas Path Inspection (HGPI) | 536143 | 2026-03-02 | 2026-03-20
M501F | Latin America | 980037 | Gas Turbine | 148582 | Hot Gas Path Inspection (HGPI) | 536142 | 2026-03-02 | 2026-03-20
M501F | Latin America | 980039 | Gas Turbine | 148583 | Hot Gas Path Inspection (HGPI) | 549828 | 2027-03-02 | 2027-03-20
M501F | Latin America | 980040 | Gas Turbine | 148584 | Hot Gas Path Inspection (HGPI) | 549829 | 2027-03-02 | 2027-03-20
M501F | Latin America | 980040 | Gas Turbine | 196269 | Large Call-Out | 563525 | 2026-07-22 | 2026-08-08
SAC | MENA | 909229 | Steam Turbine | 139963 | Major Inspection (MI) | 525991 | 2027-11-01 | 2027-12-30
SAC | MENA | 818971 | Steam Turbine | 151140 | Major Inspection (MI) | 553066 | 2028-10-01 | 2028-10-22
SAC | MENA | 818973 | Steam Turbine | 151144 | Major Inspection (MI) |  | 2029-09-30 | 2029-10-28
SAC | MENA | 818973 | Steam Turbine | 166423 | Minor Inspection | 546506 | 2027-11-01 | 2027-11-14
SAC | MENA | 909229 | Steam Turbine | 182078 | Major Inspection (MI) |  | 2028-07-01 | 2028-07-29
SAXC | NAM North America | 197856 | Steam Turbine | 151100 | Major Inspection (MI) | 547322 | 2026-02-06 | 2026-06-11
SAXC | NAM North America | 197856 | Steam Turbine | 151104 | Minor Inspection |  | 2028-07-05 | 2028-07-10
SC | MENA | V01718 | Steam Turbine | 103564 | Major Inspection (MI) | 501279 | 2026-12-01 | 2026-12-29
SC | MENA | V01718 | Steam Turbine | 151191 | Minor Inspection |  | 2029-12-01 | 2029-12-06
SC | MENA | V01718 | Steam Turbine | 180679 | Major Inspection (MI) | 552696 | 2026-10-01 | 2026-11-30
SC5 | Latin America | 270T404 | Steam Turbine | 115635 | Major Inspection (MI) | 504858 | 2026-04-02 | 2026-05-15
SC5 | Latin America | 270T404 | Steam Turbine | 133063 | Minor Inspection | 528690 | 2028-04-10 | 2028-05-10
SCMX-400 | Asia | 3183Y760 | Steam Turbine | 150620 | Minor Inspection | 545045 | 2028-05-01 | 2028-05-15
SCMX-400 | Asia | 3183Y780 | Steam Turbine | 190434 | Minor Inspection | 559156 | 2028-08-01 | 2028-08-31
SCSF | NAM North America | 197890 | Steam Turbine | 182287 | Minor Inspection |  | 2027-03-07 | 2027-03-13
SCSF | NAM North America | 197890 | Steam Turbine | 182294 | Major Inspection (MI) |  | 2030-02-24 | 2030-03-30
SCSF | NAM North America | 197890 | Steam Turbine | 193707 | Minor Inspection |  | 2028-03-05 | 2028-03-11
SGEN5 | MENA | 909235 | Generator | 139964 | Major Inspection (Rotor Out) | 525991 | 2029-10-01 | 2029-10-22
SGEN5 | MENA | 818972 | Generator | 181420 | Major Inspection (Robotic) | 553066 | 2028-10-01 | 2028-10-22
SGT-800 | Europe | BD000163U01 | Gas Turbine | 146685 | Major Inspection (MI) |  | 2026-11-20 | 2026-12-18
SGT-800 | Europe | BD000163U02 | Gas Turbine | 146686 | Major Inspection (MI) |  | 2027-05-22 | 2027-06-19
SGT-800 | Europe | BD000076U02 | Gas Turbine | 146694 | Major Inspection (MI) |  | 2027-03-24 | 2027-04-21
SGT-800 | Europe | BD000076U01 | Gas Turbine | 146695 | Major Inspection (MI) |  | 2027-05-07 | 2027-06-04
SGT-800 | Europe | BD000075U01 | Gas Turbine | 146696 | Combustion Inspection (CI) |  | 2027-06-26 | 2027-07-03
SGT-800 | Europe | BD000075U02 | Gas Turbine | 146697 | Combustion Inspection (CI) |  | 2028-05-01 | 2028-05-08
SW501_/D | NAM North America | 800318 | Gas Turbine | 117866 | Combustion Inspection (CI) | 514663 | 2026-02-16 | 2026-04-05
SW501_/D | NAM North America | 800318 | Gas Turbine | 167018 | Major Inspection (MI) | 545832 | 2028-01-15 | 2028-03-13
SW501_/D | NAM North America | 800318 | Gas Turbine | 167020 | Combustion Inspection (CI) |  | 2028-09-17 | 2028-09-24
SXC | NAM North America | 197920 | Steam Turbine | 182382 | Minor Inspection | 553837 | 2026-04-13 | 2026-05-13
T190-240 | Asia | 811308 | Generator | 156834 | Major Inspection (Rotor Out) | 536528 | 2027-01-15 | 2027-02-12
T190-240 | Asia | 92455 | Generator | 165760 | Minor Inspection | 543192 | 2029-12-06 | 2029-12-20
T190-240 | Asia | 811308 | Generator | 166224 | Minor Inspection | 543495 | 2030-09-07 | 2030-10-05
T190-240 | Asia | 92405 | Generator | 179065 | Major Inspection (Robotic) | 551814 | 2029-04-01 | 2029-05-30
T190-240 | Asia | 92456 | Generator | 187514 | Major Inspection (Rotor Out) | 557737 | 2027-04-13 | 2027-05-08
T190-240 | Asia | 92454 | Generator | 191780 | Minor Inspection | 560103 | 2028-11-12 | 2028-11-26
T214-234 | NAM North America | 810816 | Generator | 165116 | Major Inspection (Robotic) | 542818 | 2029-10-01 | 2029-10-29
T214-234 | NAM North America | 810815 | Generator | 165118 | Major Inspection (Robotic) | 542819 | 2030-04-01 | 2030-04-29
T214-234 | Europe | 819346 | Generator | 165951 | Major Inspection (Robotic) | 543311 | 2026-09-01 | 2026-09-29
T214-234 | NAM North America | 810814 | Generator | 165955 | Minor Inspection | 534339 | 2027-04-01 | 2027-04-15
T214-234 | SSA | 811089 | Generator | 166161 | Major Inspection (Robotic) | 540569 | 2027-04-15 | 2027-05-13
T214-234 | SSA | 811087 | Generator | 166162 | Major Inspection (Robotic) | 540568 | 2026-11-13 | 2026-12-12
T214-234 | SSA | 811088 | Generator | 166164 | Major Inspection (Rotor Out) | 543436 | 2028-03-18 | 2028-04-15
T214-234 | SSA | 811086 | Generator | 166166 | Minor Inspection | 543437 | 2028-05-15 | 2028-06-04
T214-234 | SSA | 811089 | Generator | 166167 | Minor Inspection | 543438 | 2030-04-09 | 2030-04-23
T214-234 | Europe | 816464 | Generator | 179866 | Major Inspection (Robotic) | 531312 | 2028-05-22 | 2028-06-19
T214-234 | Europe | 92505 | Generator | 187313 | Major Inspection (Rotor Out) | 557032 | 2029-05-07 | 2029-05-31
T214-234 | SSA | 811087 | Generator | 192457 | Minor Inspection | 560561 | 2029-06-18 | 2029-07-02
T214-269 | NAM North America | 818671 | Generator | 140686 | Stand Alone Small Upgrade | 526354 | 2027-01-01 | 2027-01-26
T214-269 | NAM North America | 818671 | Generator | 150726 | Major Inspection (Rotor Out) | 532263 | 2027-03-25 | 2027-05-10
T214-269 | NAM North America | 818671 | Generator | 158700 | Stand Alone Small Upgrade | 538063 | 2027-05-18 | 2027-06-05
T240-370 | SSA | 811370 | Generator | 104600 | Major Inspection (Rotor Out) | 500871 | 2026-01-13 | 2026-02-07
T240-370 | MENA | 811189 | Generator | 106231 | Major Inspection (Rotor Out) | 502391 | 2026-02-09 | 2026-04-09
T240-370 | MENA | 811191 | Generator | 106234 | Major Inspection (Rotor Out) | 502393 | 2028-11-01 | 2028-12-02
T240-370 | MENA | 811188 | Generator | 106235 | Major Inspection (Rotor Out) | 502397 | 2026-01-05 | 2026-02-06
T240-370 | MENA | 819792 | Generator | 127199 | Minor Inspection | 517950 | 2027-10-04 | 2027-11-02
T240-370 | MENA | 811190 | Generator | 138086 | Major Inspection (Rotor Out) | 502396 | 2028-12-03 | 2029-01-03
T240-370 | SSA | 811371 | Generator | 150288 | Major Inspection (Robotic) | 532023 | 2028-01-10 | 2028-02-07
T240-370 | MENA | 819338 | Generator | 158996 | Major Inspection (Robotic) | 538159 | 2028-01-10 | 2028-02-07
T240-370 | MENA | 819341 | Generator | 158997 | Major Inspection (Robotic) | 538160 | 2029-02-22 | 2029-03-22
T240-370 | Europe | 92401 | Generator | 160986 | Major Inspection (Stator Rewind) | 539571 | 2027-05-24 | 2027-09-05
T240-370 | MENA | 819340 | Generator | 164829 | Minor Inspection | 542643 | 2026-12-21 | 2027-01-05
T240-370 | Asia | 819796 | Generator | 165773 | Minor Inspection | 543204 | 2027-06-05 | 2027-06-26
T240-370 | Asia | 819796 | Generator | 165775 | Major Inspection (Rotor Out) | 543205 | 2030-06-01 | 2030-06-30
T240-370 | Latin America | 811036 | Generator | 166391 | Minor Inspection | 543575 | 2028-11-10 | 2028-11-24
T240-370 | MENA | 811192 | Generator | 166404 | Minor Inspection | 543584 | 2030-11-23 | 2030-12-09
T240-370 | MENA | 819339 | Generator | 174682 | Major Inspection (Robotic) | 549121 | 2028-04-16 | 2028-05-14
T240-370 | Latin America | 811037 | Generator | 174698 | Minor Inspection | 549134 | 2027-11-17 | 2027-11-29
T240-370 | Latin America | 818614 | Generator | 176920 | Major Inspection (Rotor Out) | 539739 | 2027-06-15 | 2027-07-29
T240-370 | Latin America | 818616 | Generator | 182015 | Major Inspection (Rotor Out) | 542907 | 2027-10-27 | 2027-11-24
T240-370 | MENA | 811188 | Generator | 192788 | Minor Inspection | 560749 | 2029-12-14 | 2029-12-28
T255-380 | Asia | 811524 | Generator | 176956 | Minor Inspection | 550580 | 2027-03-01 | 2027-03-20
T255-380 | Asia | 811525 | Generator | 181181 | Minor Inspection | 552903 | 2028-01-05 | 2028-02-03
TAC | NAM North America | 1515009 | Generator | 172818 | Major Inspection (Rotor Out) | 547974 | 2026-10-01 | 2026-10-31
TAKS | NAM North America | 818825 | Generator | 185596 | Major Inspection (Robotic) | 555873 | 2027-10-15 | 2027-11-15
TAKS | NAM North America | 818825 | Generator | 185628 | Minor Inspection | 555632 | 2028-04-03 | 2028-05-03
W84 | NAM North America | GG10706 | Generator | 163043 | Major Inspection (Robotic) | 541174 | 2029-05-31 | 2029-06-28
W84 | NAM North America | GG10718 | Generator | 175825 | Minor Inspection | 544928 | 2027-09-01 | 2027-09-30
W84 | NAM North America | GG10719 | Generator | 175826 | Minor Inspection | 549884 | 2026-10-01 | 2026-10-30
W84 | NAM North America | GG10720 | Generator | 175827 | Minor Inspection | 549885 | 2027-04-01 | 2027-05-01
W84 | NAM North America | GG10765 | Generator | 175991 | Minor Inspection | 530763 | 2027-09-25 | 2027-10-24
W84 | NAM North America | GG10764 | Generator | 175992 | Minor Inspection | 530764 | 2027-10-23 | 2027-11-21
W86 | NAM North America | GG10827 | Generator | 189833 | Minor Inspection | 558691 | 2030-02-18 | 2030-03-06
W88 | Asia | GG10701 | Generator | 111616 | Major Inspection (Robotic) | 514125 | 2026-05-16 | 2026-06-11
W88 | Asia | GG10701 | Generator | 131775 | Minor Inspection | 521686 | 2028-03-19 | 2028-04-15
W88 | Latin America | 390T013 | Generator | 136597 | Minor Inspection | 524031 | 2026-04-18 | 2026-04-21
W88 | Asia | GG10631 | Generator | 155408 | Major Inspection (Robotic) | 562945 | 2028-02-05 | 2028-03-18
W88 | Europe | GG10829 | Generator | 159117 | Minor Inspection | 538215 | 2030-09-04 | 2030-09-18
W88 | Asia | GG10701 | Generator | 159226 | Minor Inspection | 538294 | 2028-12-01 | 2028-12-27
W88 | Asia | GG10702 | Generator | 159227 | Minor Inspection | 538295 | 2028-07-01 | 2028-07-27
W88 | Asia | GG10799 | Generator | 175379 | Minor Inspection | 549572 | 2028-11-07 | 2028-11-30
W88 | Europe | GG10729 | Generator | 176329 | Minor Inspection | 550184 | 2028-04-02 | 2028-04-28
W88 | Asia | GG10825 | Generator | 176993 | Minor Inspection | 550623 | 2029-06-26 | 2029-07-29
W88 | Asia | GG10826 | Generator | 176995 | Minor Inspection | 550624 | 2029-08-07 | 2029-09-09
W88 | Asia | GG10631 | Generator | 179076 | Major Inspection (Rotor Out) |  | 2027-10-18 | 2027-10-24
W88 | Asia | GG10673 | Generator | 184165 | Major Inspection (Robotic) | 554804 | 2027-10-09 | 2027-11-20
W88 | Asia | GG10674 | Generator | 184364 | Major Inspection (Robotic) | 554992 | 2027-07-03 | 2027-08-14
W88 | Asia | GG10675 | Generator | 184365 | Major Inspection (Robotic) | 554993 | 2027-08-14 | 2027-09-25
W88 | Europe | GG10759 | Generator | 186012 | Minor Inspection | 556152 | 2029-08-14 | 2029-09-10
W88 | Europe | GG10760 | Generator | 186013 | Minor Inspection | 556153 | 2029-09-30 | 2029-10-27
W88 | Asia | GG10800 | Generator | 187171 | Minor Inspection | 556807 | 2028-12-01 | 2028-12-24
W88 | Europe | GG10766 | Generator | 187880 | Major Inspection (Robotic) | 560164 | 2027-04-18 | 2027-05-16
W88 | Europe | GG10729 | Generator | 188352 | Minor Inspection | 557687 | 2028-04-02 | 2028-04-28
W88 | Europe | GG10766 | Generator | 188542 | Minor Inspection | 557935 | 2029-05-06 | 2029-06-07
W88 | Europe | GG10748 | Generator | 190741 | Minor Inspection | 556904 | 2028-03-20 | 2028-04-03
W88 | Asia | GG10674 | Generator | 194684 | Major Inspection (Robotic) | 556741 | 2027-06-19 | 2027-07-31
W88 | Asia | GG10674 | Generator | 194685 | Major Inspection (Robotic) | 556741 | 2027-06-19 | 2027-07-31
WATER-COOLE | NAM North America | 180X484 | Generator | 117907 | Major Inspection (Rotor Out) | 503562 | 2028-04-17 | 2028-05-16
WATER-COOLE | NAM North America | 180X484 | Generator | 195216 | Major Inspection (Rotor Out) | 562718 | 2028-09-11 | 2028-11-28